## Instructions
Instructions
The stakeholder communication plan should be managed by the organizational change manager, reviewed regularly with the project manager and re-evaluated and updated at regular intervals based on stakeholder response to the change triggered by the project.
1. Identify the project's stakeholders and what they need to know about the project and about changes to their work processes. - The template includes an initial list of information to document about each stakeholder. - Focus more on roles or groups than individuals. - Think through everyone impacted by the project – this includes sponsors, the project team, SMEs and end users.
2. Plan communications. - Plan communications based on the project phase and where stakeholders are on the organizational change management ADKAR (Awareness, Desire, Knowledge, Ability, Reinforcement) curve.
3. Optional: Create a communications calendar view. - Identify when communications are sent by Month, Week and Day.
Note on A2: Lenser, Leslie: Definition updated
Note on A4: Lenser, Leslie: Definition updated with ADKAR

## Project Info
[Project Name]
Project Summary
Communication Goals | 1.
2.
3.
4.
5.

## Stakeholder Information
Stakeholder Information and Communication Preferences
# | Stakeholder Group or Individual | Functional / Change Impact Role or Title | What is Changing for the Stakeholder? | Concerns and Information Needs | Frequency of Communication | Communication Format / Channel | Notes

## Communication Plan
# | Stakeholder / CM Event | Type | Objective(s) | Message / Key Topics | Target Audience(s) | Delivery Date(s) | Channel | Presenter / Messenger | Content Developer | Reviewer / Approver | Status | Follow Up Plan
PROJECT KICK-OFF
01 | [Project Kick-Off Announcement] | Project Champion | [*Broadcast project initiation to all stakeholders *Build awareness of the need for the project] | [*Overview of project scope and high-level timeline] | [All Project Stakeholders] |  | [Email Campus Newsletter Digital Signage] | [Executive Sponsor] | [Project Manager] | [Executive Sponsor] |  |  | Author: | PC = Project Champion
02 | [Coach Leadership on Change Management] | Member Champion | [*Train project team leadership on criticality of incorporating change management practices *Begin to build data for change management initiatives] | [*Leadership messaging is critical to project success *Teams want to hear WIIFM from their direct supervisor] | [Managers] |  | [Leadership Team Meeting] | [Change Manager] | [Change Manager] | [Executive Sponsor, Project Manager] |  |  |  | CA = Change Agent
03 | [Core Team Kick-Off Meeting] | Change Target | [*Establish project team roles and share scope *Get team buy in and understanding of what the project is working to accomplish] | [*Scope *Vendor Involvement *Project Team standards of behavior] | [Core Project Team] |  | [In Person Meeting w/Follow Up Meeting Notes] | [Project Manager] | [Project Manager, Business Analyst] | [Executive Sponsor] |  |  |  | CE = Communications and Events
04 | [13 empty] | R = Rollout
05 | [13 empty] | T = Training
06 | [13 empty] | R = Rollout
07 | [13 empty] | T = Training
PROJECT PLANNING
25 | [Executive Sponsor Letter to Leadership] | Change Target | ['*Show sponsor support for project *Set expectations] | ['*Kickoff rollout *Set expectations of senior leaders during Go Live ] | ['President's Cabinet, Shared IT Governance Leadership[ |  | [Email President's Cabinet] | [Executive Sponsor] | [Project Manager] | [Executive Sponsor]
26 | [Executive Sponsor Letter to Most Impacted Staff] | Project Champion | ['*Show sponsor support for Workday *Set rollout expectations] | ['*Kickoff rollout *Set expectations of most impacted staff; acknowledge WIIFM] | ['SMEs Core Project Team] |  | [Email] | [Executive Sponsor] | [Project Manager] | [Executive Sponsor]
27 | [Executive Sponsor Letter to all staff] | Project Champion | ['*Show sponsor support for Workday *Set rollout expectations] | ['*Kickoff rollout *Set expectations of all staff; acknowledge WIIFM] | [All Impacted Staff] |  | [Email] | [Executive Sponsor] | [Project Manager] | [Executive Sponsor]
PROJECT CONFIGURATION PHASE
50
51
52
53
54
55
56
PROJECT USER ACCEPTANCE TESTING PHASE
75
76
77
78
79
80
81
PROJECT TRAINING PHASE
100
101
102
103
104
105
106
PROJECT GO LIVE PHASE
125
126
127
128
129
130
131
PROJECT STABILIZATION PHASE
150
151
152
153
154
155
156

## Comm Calendar View
[Project Name]
Communication Dashboard
|  |  | Sep 19 |  |  |  |  | Oct 19 |  |  |  | Nov 19 |  |  |  | Dec 19 |  |  |  |  | Jan 20 |  |  |  | Feb 20 |  |  |  | Mar 20 |  |  |  |  | Apr 20 |  |  |  | May 20 |  |  |  |  | Jun 20 |  |  |  | Jul 20 |  |  |  | Aug 20 |  |  |  |  | Sep 20
# | Communication Event | Notes | 1 | 8 | 15 | 22 | 29 | 6 | 13 | 20 | 27 | 3 | 10 | 17 | 24 | 1 | 8 | 15 | 22 | 29 | 5 | 12 | 19 | 26 | 2 | 9 | 16 | 23 | 1 | 8 | 15 | 22 | 29 | 5 | 12 | 19 | 26 | 3 | 10 | 17 | 24 | 31 | 7 | 14 | 21 | 28 | 5 | 12 | 19 | 26 | 2 | 9 | 16 | 23 | 30 | 6 | 13 | 20 | 27
PROJECT KICK-OFF
01 | [Project Kick-Off Announcement] |  | Oct 19 27: 30
02 | [Coach Leadership on Change Management] |  | Oct 19 6: 1; Oct 19 27: 30
03 | [Core Team Kick-Off Meeting] |  | Oct 19 13: 8; Oct 19 20: 20; Nov 19 3: 4, 6
PROJECT PLANNING
25 | [Executive Sponsor Letter to Leadership] |  | Oct 19 27: 27; Nov 19 3: 4; Nov 19 10: 11, 15
26 | [Executive Sponsor Letter to Most Impacted Staff] |  | Oct 19 27: 27; Nov 19 3: 4; Nov 19 10: 11, 15
27 | [Executive Sponsor Letter to all staff] |  | Oct 19 27: 1; Nov 19 3: 7; Nov 19 10: 13; Nov 19 17: 18
PROJECT CONFIGURATION PHASE
PROJECT USER ACCEPTANCE TESTING PHASE
PROJECT TRAINING PHASE
PROJECT GO LIVE PHASE
PROJECT STABILIZATION PHASE