Texas Commitment to

Prairie View A&M University

OCR Priority Plan Semiannual Report

January-June 2006

Submitted July 2006

TABLE OF CONTENTS

Plan Component 1.1:     University College			3

Plan Component 1.2:	Expand Project ACCESS			5

Plan Component 1.3:	Student Development and Support Center			7

Plan Component 1.4:	Merit-Based Honors Scholarship Program			9

Plan Component 2.1:	Strengthen Information Technology Services	11

Plan Component 2.2:	Strengthen Human Resources Function and Infrastructure	16

Plan Component 3.1:	Accreditation Support	18

Plan Component 4.1:	College of Nursing Building	20

Plan Component 4.2:     Enhance the College of Nursing	22

Plan Component 5.1:	Enhance the College of Engineering 	24

Plan Component 5.2a:    MS Program in Electrical Engineering	26

Plan Component 5.2b:	PhD Program in Electrical Engineering	28

Plan Component 5.3:	Engineering Facilities	30

Plan Component 6.1:	Enhance Educator Preparation Programs	33

Plan Component 7.1:	BS in Construction Science	36

Plan Component 7.2:	Master of Architecture	39

Plan Component 7.3:	School of Architecture Building	42

Plan Component 8.1:	Master Plan Renovations	44

Plan Component 9.1:	Strengthen Institutional Development Office	46

Plan Component 10.1:	Endowed Chairs	50

Plan Component 11.1:	PhD Program in Juvenile Forensic Psychology	52

Plan Component 11.2:	New Building for Juvenile Justice-Related Programs	55

Plan Component 12.1:	PhD in Educational Leadership	57

Plan Component 12.2:	MS in Computer Science	60

Plan Component 12.3:	MS in Information Systems	62

Plan Component 13.1:	Statutory Mission Texas Education Code, Section 87.104	64

Plan Component 13.2:	Institutional Mission Statement	65

Additional Plan Components Funded by the Texas State Legislature	66

Plan Component 14.1:	MS in Accounting	67

Plan Component 14.2:	MS in Community Development	69

Plan Component 14.3:	Community and Urban Rural Extension Service Center	72

Plan Component 14.4:	Faculty Recruitment, Retention and Development	74

Plan Component 14.5:	Texas Institute for the Preservation of History and Culture	76

Plan Component 15.1:	Texas Undergraduate Medical Academy	78

Appendix A:	OCR Priority Plan Items Expenditure Trends	80

Appendix B:	University College Residential Retention Rates	81

Appendix C:	Funding Revenues Generated through Formulas and Tuition, Actual: Fall 2001 through Spring 2006, Projected: Summer 2006, Fall 2006, and Spring 2007	82

Plan Component: 1.1 Create the University College, which provides an academically focused, student-centered environment for the entire University community with an emphasis on freshmen.

| Designated Institution Staff: |  |
| --- | --- |
| Name | Mrs. Lettie Raab |
| Title | Executive Director, University College |
| Address | Prairie View A&M University |
| Phone | 936-857-4448 |
| Fax | 936-857-2261 |
| E-mail | lmraab@pvamu.edu |

| Designated Board Staff: |  |
| --- | --- |
| Name | Ms. Natalie Coffey |
| Title | Program Director, Participation and Success |
| Address | Texas Higher Education Coordinating Board |
| Phone | 512-427-6227 |
| Fax | 512-427-6127 |
| E-mail | Natalie.Coffey@thecb.state.tx.us |

| Funding: |  |
| --- | --- |
| Appropriated 2002 (millions) | $ 1.20 |
| Appropriated 2003 (millions) | $ 1.20 |
| Appropriated 2004 (millions) | $ 1.08 |
| Appropriated 2005 (millions) | $ 1.02 |
| Expended as of 8/31/05 | $ (3.79) |
| FY 04 Budget Reallocation | $ 0.00 |
| FY 05 Budget Reallocation | $ 0.00 |
| Appropriated 2006 (millions) | $ 1.27 |
| FY 06 Expended & Committed 6/30 | $ (1.48) |
| Available as of 6/30/06 | $ 0.50 |

Summary

University College (UC) is totally operational and will welcome its 8500th student in fall 2006. Freshman advisement and support services’ referrals have been centralized in the UC Division of Advisement; the PVAMU developmental education program, tutoring services, standardized testing services and the Scholars’ Program have been centralized in the UC Division of Academic Enhancement; and freshman residential services have been centralized in the UC Division of Student Life. A recent statistical analysis showed that the aggregate retention rate for the first-time, full-time freshmen living in the UC residential complex has been 71.99% for the five UC classes (See Appendix B). The UC residential retention rate has exceeded the overall Prairie View rate for each year since UC’s implementation, by as little as 3% to nearly 7% depending on the year. During the last six months UC continued to provide services to Katrina evacuees, in addition to providing personnel and resource support for PVAMU recruitment, orientation services, athletics, Multicultural Services and Student Activities. UC developed a Learning Framework Class that was accepted by the UAC and approved by the THECB. UC also honored its freshman scholars at a special banquet in late January. UC personnel made presentations on the UC model at state, regional and national conferences, including FYE and NISOD. University College will be a vital part of the upcoming student orientation sessions and PVAMU Panther Camp. UC will implement its 4th Major’s Fair for the PVAMU student body and its third Sneak Preview for high school seniors.

Implementation Schedule

| Task | Expected Completion Date | Outcome Documentation | Actual Completion Date |
| --- | --- | --- | --- |
| Create University College | September 2000 | Completed residence halls and student center | September 2000 |
| Determine an administrative structure consistent with the mission of University College | September 2001 | Texas Commitment to Prairie View A&M University Strategic Plan | July 2001 |
| Develop strategies for implementation and assessment of the program and support services | October 2001 | Strategic Planning Document | July 2001 |
| Faculty and Staff Recruitment | October 2001 | Faculty and staff numbers and credentials are appropriate for the needs of University College | September 2001 |
| Equipment purchases | November 2001 | Equipment is in place that is appropriate for the University College | September 2001 |
| Train faculty and staff | November 2001 | Training schedule and materials Number and level of staff trained | September 2001 |
| Progress Report | December 2001 | Report to the Coordinating Board | December 2001 |
| Program Implemented | January 2002 | List of students enrolled in University College | September 2001 |
| Progress Report | June 2002 | Report to the Coordinating Board | June 2002 |
| Progress Report | December 2002 | Report to the Coordinating Board | January 2003 |
| Progress Report | June 2003 | Report to the Coordinating Board | July 2003 |
| Component fully implemented | August 2003 | Documentation of freshman retention and success rates | September 2003 |

# Plan Component: 1.2 Expand Project ACCESS, which provides a summer academic program for students prior to their freshmen year and a freshman component that stresses academic advisement and support services for students.

| Designated Institution Staff: |  |
| --- | --- |
| Name | Mrs. Lettie Raab |
| Title | Executive Director, University College |
| Address | Prairie View A&M University |
| Phone | 936-857-4448 |
| Fax | 936-857-2261 |
| E-mail | lmraab@pvamu.edu |

| Designated Board Staff: |  |
| --- | --- |
| Name | Ms. Natalie Coffey |
| Title | Program Director, Participation and Success |
| Address | Texas Higher Education Coordinating Board |
| Phone | 512-427-6227 |
| Fax | 512-427-6127 |
| E-mail | Natalie.Coffey@thecb.state.tx.us |

| Funding: | None requested |
| --- | --- |
| Appropriated 2002 (millions) | $ 0.00 |
| Appropriated 2003 (millions) | $ 0.00 |
| Appropriated 2004 (millions) | $ 0.00 |
| Appropriated 2005 (millions) | $ 0.00 |
| Expended as of 8/31/05 | $ 0.00 |
| FY 04 Budget Reallocation | $ 0.00 |
| FY 05 Budget Reallocation | $ 0.00 |
| Appropriated 2006 (millions) | $ 0.00 |
| FY 06 Expended & Committed 6/30 | $ 0.00 |
| Available as of 6/30/06 | $ 0.00 |

#### Summary and Implementation Schedule

During the last six months ACCESS personnel were invited to disseminate information about the ACCESS program at Alabama A & M University, Arkansas Pine Bluff and Wiley College. ACCESS welcomed its eleventh class and 1,100 student in summer 2006. This year’s theme, Learning Through Service, reflects ACCESS’ focus on Service Learning as an effective learning strategy. This year Service Learning will be a weekly workshop for participants. The students will participate in two service learning projects in the Houston area and spend three days in New Orleans in a capstone experience in July. Students are reading the best-seller Nickled and Dimed in America and were able to view the stage version of this book and discuss the concepts presented with the actors. As in previous years, ACCESS made a concerted effort to recruit more Hispanic students for the 2006 class. This effort will be further increased for 2007. ACCESS faculty and staff will serve as instructors for many of the Panther Camp educational briefings, and staff will train the student Panther Talk Leaders. ACCESS recruiters will assist with the university’s recruitment efforts in the fall.

This year ACCESS will pilot “ACCESS: Year Two.” This program will keep the ACCESS 2005 Professional Advisor as a mentor to that group during its second year at PV. The group will meet with the mentor on a regular basis and participate in a minimum of two educational/cultural activities during the year. We believe that this effort will further improve the graduation rate for this group.

# Plan Component: 1.3 Provide start up funding for the operation of a student development and support center to house all educational and general, non-auxiliary student affairs, enrollment, and support functions.

| Designated Institution Staff: |  |
| --- | --- |
| Name | Mr. Don Byars |
| Title | Associate Provost for Enrollment Management |
| Address | Prairie View A&M University |
| Phone | 936-261-1057 |
| Fax | 936-857-2426 |
| E-mail | dobyars@pvamu.edu |

| Designated Board Staff: |  |
| --- | --- |
| Name | Ms. Natalie Coffey |
| Title | Program Director, Participation and Success |
| Address | Texas Higher Education Coordinating Board |
| Phone | 512-427-6227 |
| Fax | 512-427-6127 |
| E-mail | Natalie.Coffey@thecb.state.tx.us |

| Funding: |  |
| --- | --- |
| Appropriated 2002 (millions) | $ 1.00 |
| Appropriated 2003 (millions) | $ 1.00 |
| Appropriated 2004 (millions) | $ 0.87 |
| Appropriated 2005 (millions) | $ 0.88 |
| Expended as of 8/31/05 | $ (3.15) |
| FY 04 Budget Reallocation | $ (0.17) |
| FY 05 Budget Reallocation | $ (0.22) |
| Appropriated 2006 (millions) | $ 1.01 |
| FY 06 Expended & Committed 6/30 | $ (1.09) |
| Available as of 6/30/06 | $ 0.13 |

Summary

The various units which comprise Enrollment Management are now housed almost entirely on one floor of the new Memorial Student Center.  These units—Admissions, Financial Aid, Orientation, Recruitment & Marketing, and the Registrar’s Office—are physically integrated to improve the enrollment process for all students through centralization of services.  The units also work with other campus entities, such as University College and Project ACCESS, to provide support for freshman orientation and Panther Camp activities, including a one-day physical Challenge Course designed to assist students in being more successful in the classroom.

Implementation Schedule

| Task | Expected Completion Date | Outcome Documentation | Actual Completion Date |
| --- | --- | --- | --- |
| Develop and implement an assessment plan for all enrollment services | September 2001 | Uniform Recruitment and Retention Plan | August 2001 |
| Evaluate the future needs of the Student Development Support Center | September 2001 | Texas Commitment to Prairie View A&M University Strategic Plan | July 2001 |
| Expand the scope of recruitment activities | October 2001 | Comprehensive recruitment and marketing materials | December 2001 |
| Staff Recruitment | November 2001 | Staff numbers and credentials are appropriate for the needs of the center | December 2001 |
| Progress Report | December 2001 | Report to the Coordinating Board | December 2001 |
| Evaluate recruitment and dropout/stop out tracking system | February 2002 | Tracking software is in place and operational | May 2002 |
| Progress Report | June 2002 | Report to the Coordinating Board | June 2002 |
| Equipment purchases | September 2002 | Equipment is in place that is appropriate for the needs of the support center | November 2003 |
| Progress Report | December 2002 | Report to the Coordinating Board | January 2003 |
| Relocation of offices | May 2003 | All general student affairs, enrollment and support offices are located in the Memorial Student Center | July 2003 |
| Progress Report | June 2003 | Report to the Coordinating Board | July 2003 |
| Progress Report | December 2003 | Report to the Coordinating Board | January 2004 |
| Progress Report | June 2004 | Report to the Coordinating Board | July 2004 |
| Progress Report | December 2004 | Report to the Coordinating Board | January 2005 |
| Progress Report | June 2005 | Report to the Coordinating Board | July 2005 |
| Progress Report | December 2005 | Report to the Coordinating Board | January 2006 |
| Progress Report | June 2006 | Report to the Coordinating Board |  |
| Progress Report | December 2006 | Report to the Coordinating Board |  |
| Progress Report | June 2007 | Report to the Coordinating Board |  |
| Component fully implemented | August 2007 | Functional Support Center |  |

# Plan Component: 1.4 Establish a merit-based honors scholarship program.

| Designated Institution Staff: |  |
| --- | --- |
| Name | Mr. Don Byars |
| Title | Associate Provost for Enrollment Management |
| Address | Prairie View A&M University |
| Phone | 936-261-1057 |
| Fax | 936-857-2426 |
| E-mail | dobyars@pvamu.edu |

| Designated Board Staff: |  |
| --- | --- |
| Name | Ms. Amanda Greene |
| Title | Budget and Policy Analyst, Planning and Accountability Division |
| Address | Texas Higher Education Coordinating Board |
| Phone | 512-427-6137 |
| Fax | 512-427-6147 |
| E-mail | amanda.greene@thecb.state.tx.us |

| Funding: |  |
| --- | --- |
| Appropriated 2002 (millions) | $ 0.80 |
| Appropriated 2003 (millions) | $ 0.80 |
| Appropriated 2004 (millions) | $ 0.88 |
| Appropriated 2005 (millions) | $ 1.75 |
| Expended as of 8/31/05 | $ (3.25) |
| FY 04 Budget Reallocation | $ 0.00 |
| FY 05 Budget Reallocation | $ (0.98) |
| Appropriated 2006 (millions) | $ 1.11 |
| FY 06 Expended & Committed 6/30 | $ (1.11) |
| Available as of 6/30/06 | $ 0.00 |

Summary

Under the leadership of the current Director of Student Financial Aid, the office has been restructured and a new module of the Student Information System (SIS PLUS) has been implemented to better track  merit- and need-based financial aid transactions.  With approximately 90% of the institution’s students on financial aid, this service is critical. This new module allows for automatic tracking and packaging of all awards for which students qualify during the academic year.  Financial Aid Awareness Workshops were held in February, as scheduled, and other types of programs were held in several areas of the campus to update students and staff about available opportunities and services.  In addition to the Freshman Scholarship Program, a scholarship for Transfer Students has been initiated—a new student market segment for a largely traditional campus.

#### Implementation Schedule

| Task | Expected Completion Date | Outcome Documentation | Actual Completion Date |
| --- | --- | --- | --- |
| Proceed with plans for a Capital Campaign | July 2001 | Signed contract with campaign council including specific details of planned use of funds | December 2002 |
| Determine program criteria | September 2001 | Program criteria documented and approved by an appropriate University official | September 2001 |
| Progress Report | December 2001 | Report to the Coordinating Board | December 2001 |
| Solicit Cluster corporations for program funding | January 2002 | Funding solicitation proposal including specific details of planned use of funds |  |
| Determine academic requirements for the program | May 2002 | Program approval by the University Academic Council – minutes of a meeting showing the vote of the council |  |
| Progress Report | June 2002 | Report to the Coordinating Board | June 2002 |
| Determine a student governance structure for the program | September 2002 | Program by-laws documented and approved by an appropriate University official | September 2001 |
| Progress Report | December 2002 | Report to the Coordinating Board | January 2003 |
| Expand and strengthen gift acceptance and acknowledgement | February 2003 | Letters used to acknowledge and thank donors for gifts | February 2003 |
| Progress Report | June 2003 | Report to the Coordinating Board | July 2003 |
| Establish a campaign and development budget | November 2003 | Details of the campaign documented and approved by an appropriate University official; approved University budget documents | December 2003 |
| Establish a Planned Giving Program | November 2003 | Announcement posted on the University website and in brochures and pamphlets | March 2004 |
| Progress Report | December 2003 | Report to the Coordinating Board | January 2004 |
| Progress Report | June 2004 | Report to the Coordinating Board | July 2004 |
| Progress Report | December 2004 | Report to the Coordinating Board | January 2005 |
| Progress Report | June 2005 | Report to the Coordinating Board | July 2005 |
| Progress Report | December 2005 | Report to the Coordinating Board | January 2006 |
| Progress Report | June 2006 | Report to the Coordinating Board |  |
| Progress Report | December 2006 | Report to the Coordinating Board |  |
| Progress Report | June 2007 | Report to the Coordinating Board |  |
| Component fully implemented | August 2007 | Enrollment data verifying student enrollment in the program and certified by Registrar |  |

# Plan Component: 2.1 Strengthen information technology services.

| Designated Institution Staff: |  |
| --- | --- |
| Name | Mrs. Mary Lee Hodge |
| Title | Vice President for Business Affairs |
| Address | Prairie View A&M University |
| Phone | 936-261-2150 |
| Fax | 936-261-2159 |
| E-mail | mlhodge@pvamu.edu |

| Designated Board Staff: |  |
| --- | --- |
| Name | Ms. Amanda Greene |
| Title | Budget and Policy Analyst, Planning and Accountability Division |
| Address | Texas Higher Education Coordinating Board |
| Phone | 512-427-6137 |
| Fax | 512-427-6147 |
| E-mail | amanda.greene@thecb.state.tx.us |

| Funding: |  |
| --- | --- |
| Appropriated 2002 (millions) | $ 0.80 |
| Appropriated 2003 (millions) | $ 0.80 |
| Appropriated 2004 (millions) | $ 0.70 |
| Appropriated 2005 (millions) | $ 0.70 |
| Expended as of 8/31/05 | $ (3.80) |
| FY 04 Budget Reallocation | $ 0.46 |
| FY 05 Budget Reallocation | $ 0.40 |
| Appropriated 2006 (millions) | $ 2.12 |
| FY 06 Expended & Committed 6/30 | $ (1.62) |
| Available as of 6/30/06 | $ 0.56 |

Summary

Below are the noteworthy accomplishments realized during the last twelve (12) months under the leadership and guidance of the SunGard/Collegis team:

Administrative Accomplishments

  - Acquired, installed, and brought up a replacement mainframe to support the university’s Student Information Management System, thus resolving problematic mainframe lockups and slowdowns during registration, advising and grading periods.

  - Replaced mainframe 3270 emulation connectivity software with “Blue Zone” 3270 emulation to ensure license compliance across the university at a cost savings.

  - Provided consultation and support for migrating Financial Aid from EDE based processing into SIS.

  - Spearheaded the signing of the SIS to Banner Leap agreement with SunGard SCT to take advantage of significant Banner migration savings for the university.

  - Upgraded the web for student and web for faculty hardware platforms to eliminate slowdowns and server crashes in the student administrative system environment.

  - Spearheaded a power distribution upgrade for cleaner, more reliable power to mission critical computer resources.

  - Engaged the university community in a comprehensive method of testing software applied maintenance in the administrative systems environment.

  - Installed an online payment gateway to allow student payments over the Internet.

  - Provided and continue to support the incorporation of technology into the Health Center’s daily operations and the implementation of electronic medical records.

  - Load Financial Aid for 2005-2006 award year into SIS Plus for aid award and distribution.

  - Developed extracts for Student Health Medicat System.

  - Developed extracts for TK20 Application.

  - Roll SunGard Collegis ERIS Reporting Solution into production

  - Assisting in identifying and evaluating an automated payment gateway for Fiscal department.

  - Begin planning for Banner Student install and implementation.

  - Conducted a Business Process Analysis (BPA) for the Financial Aid department to provide process assistance as required.

Network Management Accomplishments

  - Installed high speed wireless infrastructure and connectivity in University College.

  - Upgraded network switching infrastructure to improve network connectivity across campus.

  - Upgraded the Cisco Pix 515 firewall and installed redundant Cisco Pix 525 firewalls to provide more robust performance, greater reliability, improved fault tolerance, greater protection of enterprise applications and to afford firewall protection for future expansion of networked resources.

  - Replaced the Physical Plant and Coleman Library core routers with state of the art routers to provide better performance and increased reliability of the network infrastructure.

  - Acquired and installed Cisco Works Enterprise network management software and hardware platform to provide for increased network management capabilities.

  - Completed a Microsoft Exchange pilot project and initiated the production rollout of Exchange.

  - Provided technical support and consultation for new construction projects on campus.

  - Provided support and consultation for upgrade and centralized security system to be housed in the Department of Public Safety.

  - Provided support and consultation for the development and implementation of a shared resource environment with Human Resources.

  - Upgraded McAfee Enterprise anti-virus solution to version 8.

  - Provided IT infrastructure and network connectivity for newly constructed buildings at PVAMU:

    - Electrical Engineering

    - Architecture

    - Nursing School

    - Athletics Administration

  - Provided network connectivity for Harrington Science building renovation.

  - Provided High Speed wireless infrastructure, network connectivity and ongoing technical support for all PVAMU student housing phases.

  - Implemented Microsoft Active Directory on PVAMU local area network.

  - Provided network connectivity to the following labs:

    - Animal Industries computer lab

    - Computer Science graduate computer lab

    - Texas Pre-Medical Academy computer lab

  - Upgrade fiber backbone between core locations.

  - Installed and implemented Voice Over IP (VOIP) telephony in newly constructed buildings at PVAMU and migrating to campuswide deployment.

  - Provide enhanced network security and intrusion protection for campus network.

  - Provide network support for environmental controls project campuswide.

  - Created and maintained a Network Operations Center (NOC) in the SR Collins data center which provisions 24 x 7 PVAMU network monitoring and control.

User Services and Lab Support Accomplishments

  - Established Central Help Desk services which provide 24/7 technical support to students and daily support to faculty and staff.

  - Established a collaborative learning space for students in the Coleman Library with the rollout of the “Panther Trek” project which provides wireless laptop checkout and use in the library.

  - Resolved problematic, pervasive and frustrating pc downtime issues in the open computer labs by introducing hardware and software solutions designed to improve efficiencies and reliability to the lab systems.

  - Installed and implemented Print Manager Plus technology which provides comprehensive and effective management of network printing resources and reporting capability for the open lab environment.

  - Instituted a user authentication process in the open computer labs to facilitate authorized access and protection of lab resources.

  - Addressed the need for additional computing capacity in the open labs by increasing the number of lab computers from 100 to 170.

  - Established a new computer lab in Farrell Hall to support student computing needs and requirements by providing 38 additional pc workstations on campus with targeted 24 by 7 availability and access.

  - Provided planning, implementation, equipment and support for the SGA student voting and elections.

  - Provided Microsoft Outlook end user training to email users.

  - Provided a total renovation facelift for the student computing lab in Coleman Library.

  - Installed web cams in student computing labs for security.

  - Relocated printers in student computing lab in Coleman Library to facilitate student usage patterns.

  - Continue to provide daily desktop support and assistance to PVAMU community on demand through help desk requests.

  - Implementing remote desktop management support and services for the entire PVAMU community.

  - Researched and implemented printer paper tracking and usage in student computer labs.

Academic Services and Support Accomplishments

  - Provided and continue to provide individual Web CT training for faculty.

  - Moved to a scheduled Student Information System training system with attendance tracking and satisfaction surveys.

  - Met with the Registrar and Provost’s offices to discuss the impacts of current drop procedures on enrollments in Web CT.

  - Met with the Registrar’s office to discuss SIS training changes and to forge a partnership for the improvement of that training.

  - Conducted a marketplace and opportunity assessment of the related to the online Masters degree in Juvenile Justice.

  - Provided technology leadership, guidance and support to the academic technology systems administrators as necessary.

  - Working with the Academic administration to create a PVAMU Instructional Technology strategic plan.

  - Working with the Academic administration to identify Resource Development services (grants) that would be beneficial to PVAMU.

  - Provisioned academic technology training on distance learning and the infusion of technology in the curriculum with the College of Nursing.

Web Integration Projects

  - Installed the SunGard Collegis Site Builder web content management service to provide web content management and creation for the university community.

  - Spearheaded the total redesign and deployment of a new PVAMU web presence via SunGard Collegis Site Builder.

  - Provided Onsite Site Builder training to PVAMU web content providers.

  - Conducted PVAMU migration of legacy web content to new web presence.

Leadership Projects

  - Established IT Governance Structure.

  - Created and published IT Disaster Recovery Plan.

  - Created and publish an IT Communications Plan.

  - Working with PVAMU to create and publish an IT Strategic Plan for Technology.

Implementation Schedule

| Task | Expected Completion Date | Outcome Documentation | Actual Completion Date |
| --- | --- | --- | --- |
| Reevaluate current and future needs and opportunities for Information Technology | September 2001 | Texas Commitment to Prairie View A&M University Strategic Plan | July 2001 |
| Acquire Equipment and Hire Consultants | December 2001 | Paid invoices for equipment purchases related to goal; contracts with consultants including the specific nature of their objectives | December 2001 |
| Progress Report | December 2001 | Report to the Coordinating Board | December 2001 |
| Staff Recruitment | March 2002 | Written justification for hiring individuals for Information Technology positions | March 2002 |
| Progress Report | June 2002 | Report to the Coordinating Board | June 2002 |
| Component fully implemented | September 2002 | Texas Commitment to Prairie View A&M University Strategic Plan with accomplishments identified | September 2002 |
| Information Technology Management outsourced to SunGard Collegis, Inc. effective June 1, 2004. All PVAMU IT employees to SunGard Collegis, Inc. by July 31, 2004 | June 1, 2004 | Report to Coordinating Board Staff advised of plan to re-allocate funds to support ITS component 2.1 | June 2004 |
| Outsourcing of Information Technology to SunGard Collegis completed by September 1, 2004 | September 1, 2004 | Progress/Status Report from SunGard Collegis CIO to PVAMU Executive Vice President/CFO | September 1, 2004 |
| Extension of Internet service to students residing in University College facilities started during summer 2004 | September 1, 2004 | Progress/Status Report from SunGard Collegis CIO to PVAMU Executive Vice President/CFO | November 1, 2004 |

# Plan Component: 2.2 Strengthen human resources function and infrastructure and develop a competitive faculty compensation and benefit structure.

| Designated Institution Staff: |  |
| --- | --- |
| Name | Mrs. Mary Lee Hodge |
| Title | Vice President for Business Affairs |
| Address | Prairie View A&M University |
| Phone | 936-261-2150 |
| Fax | 936-261-2159 |
| E-mail | mlhodge@pvamu.edu |

| Designated Board Staff: |  |
| --- | --- |
| Name | Ms. Natalie Coffey |
| Title | Program Director, Participation and Success |
| Address | Texas Higher Education Coordinating Board |
| Phone | 512-427-6227 |
| Fax | 512-427-6147 |
| E-mail | Natalie.Coffey@thecb.state.tx.us |

| Funding: | None Required |
| --- | --- |
| Appropriated 2002 (millions) | $ 0.00 |
| Appropriated 2003 (millions) | $ 0.00 |
| Appropriated 2004 (millions) | $ 0.00 |
| Appropriated 2005 (millions) | $ 0.00 |
| Expended as of 8/31/05 | $ 0.00 |
| FY 04 Budget Reallocation | $ 0.00 |
| FY 05 Budget Reallocation | $ 0.00 |
| Appropriated 2006 (millions) | $ 0.00 |
| FY 06 Expended & Committed 6/30 | $ 0.00 |
| Available as of 6/30/06 | $ 0.00 |

Summary

During FY2005 the outside consulting firm of McConnell Jones Lanier and Murphy (MJLM) from Houston, Texas was awarded a contract to conduct a comprehensive compensation and job classification study of all classified staff positions and of administrative and professional positions (non-faculty) below the level of vice president, dean, associate and assistant vice president and associate and assistant dean.  The MJLM report showing the results of the study has been received so that any salary adjustments (subject to availability of funds) may be incorporated into planning for the FY2007 Annual Operating Budget.

In addition, the rollout of the People Admin system took place in the spring 2006 semester.  The system will automate position audits, position requests, the application process, and the hiring process.

Implementation Schedule

| Task | Expected Completion Date | Outcome Documentation | Actual Completion Date |
| --- | --- | --- | --- |
| Develop an assessment plan for review of faculty compensation and benefit structure and other human resources functions | September 2001 | Texas Commitment to Prairie View A&M University Strategic Plan | July 2001 |
| Progress Report | December 2001 | Report to the Coordinating Board | December 2001 |
| Create strategies to improve human resources functions | January 2002 | Customer satisfaction survey results | January 2002 |
| Develop and implement a compensation and benefits structure | February 2002 | Documentation on file | February 2002 |
| Develop and implement an employee evaluation and rewards system | April 2002 | Documentation on file of the number and level of employees receiving awards | April 2002 |
| Create and implement an employee training and development program | May 2002 | Training schedule and materials. Documentation on file of the number and level of employees trained | May 2002 |
| Progress Report | June 2002 | Report to the Coordinating Board | June 2002 |
| Faculty Recruitment | September 2002 | Faculty with appropriate terminal degrees are hired |  |
| Component fully implemented | October 2002 | Competitive faculty and staff compensation and benefits on file | October 2002 |

# Plan Component: 3.1 Maintain accreditation of programs currently accredited; as appropriate, obtain accreditation for programs that are not currently accredited.

| Designated Institution Staff: |  |
| --- | --- |
| Name | Dr. Munir Quddus |
| Title | Dean, College of Business |
| Address | Prairie View A&M University |
| Phone | 936-857-4310 |
| Fax | 936-857-2797 |
| E-mail | muquddus@pvamu.edu |

| Designated Board Staff: |  |
| --- | --- |
| Name | Dr. Roger Alford |
| Title | Program Director, Universities and Health-Related Institutions Division |
| Address | Texas Higher Education Coordinating Board |
| Phone | 512-427-6216 |
| Fax | 512-427-6168 |
| E-mail | Roger.alford@thecb.state.tx.us |

| Funding: |  |
| --- | --- |
| Appropriated 2002 (millions) | $ 0.20 |
| Appropriated 2003 (millions) | $ 0.20 |
| Appropriated 2004 (millions) | $ 0.87 |
| Appropriated 2005 (millions) | $ 0.88 |
| Expended as of 8/31/05 | $ (1.76) |
| FY 04 Budget Reallocation | $ (0.09) |
| FY 05 Budget Reallocation | $ (0.22) |
| Appropriated 2006 (millions) | $ 0.95 |
| FY 06 Expended & Committed 6/30 | $ (0.91) |
| Available as of 6/30/06 | $ 0.12 |

Summary

The Self-Evaluation Report (SER) was submitted to the Association to Advance Collegiate Schools of Business (AACSB) in August 2005.  On December 19, 2005, the Peer Review Team (PRT) sent their official pre-visit letter.  A visit was recommended by the team and supported by the AACSB Initial Accreditation Committee.   The College submitted its formal “Response to the Pre-Visit” letter on January 20, 2006.

The final visit by the PRT took place in February 5-8, 2006; the team recommended unconditional initial accreditation of all undergraduate and graduate programs. The Initial Accreditation Committee and the AACSB Board accepted the Team’s recommendations and the certificate of AACSB accreditation was received. President George C. Wright and Dean Munir Quddus attended the Annual Meeting in Paris in April to meet the AACSB leadership.

Implementation Schedule

| Task | Expected Completion Date | Outcome Documentation | Actual Completion Date |
| --- | --- | --- | --- |
| Develop a plan to attain AACSB accreditation for the College of Business | September 2001 | Texas Commitment to Prairie View A&M University Strategic Plan | July 2001 |
| Progress Report | December 2001 | Report to the Coordinating Board | December 2001 |
| Assess the Business faculty and the Business curriculum | March 2002 | Faculty and curricula are in place that meet accreditation standards | April 2002 |
| Conduct mock self-study | May 2002 | Self-study | May 2002 |
| Progress Report | June 2002 | Report to the Coordinating Board | June 2002 |
| Progress Report | December 2002 | Report to the Coordinating Board | January 2003 |
| Apply for candidacy to AACSB | January 2003 | Certificate of candidacy | October 2002 |
| Progress Report | June 2003 | Report to the Coordinating Board | July 2003 |
| Progress Report | December 2003 | Report to the Coordinating Board | January 2004 |
| Progress Report | June 2004 | Report to the Coordinating Board | June 2004 |
| Plan for initial accreditation visit | August 2004 | Application submitted and acceptance received for an initial accreditation visit in Spring 2006 | July 2004 |
| Progress with AACSB | August 2004 | Second year annual Candidacy Report submitted and acceptance received (October 2004) | August 2004 |
| Progress Report | December 2004 | Report to the Coordinating Board | December 2004 |
| Mock visit completed | Fall 2004 | Mock visit team post-visit Report Received | March 2005 |
| Progress Report |  | Submitted on June 2005 to the Office of VP Business | June/July 2005 |
| Self-Evaluation Report Submitted |  | This document was completed over the summer with extensive faculty participation | August 1, 2005 |
| Pre-Visit Letter Received |  | This letter, as is the norm, identified certain issues (major concerns, standard by standard analysis) and requested information and clarifications | December 19, 2005 |
| Respond to the Pre-Visit Letter Submitted |  | Document addresses all of the concerns and questions raised in the Pre-Visit letter | January 20, 2006 |
| Progress Report |  | Submitted on time | January 23, 2006 |
| Component fully implemented | May 2005 | The final visit by the PRT took place in February (5-8) 2006; The AACSB Board accepted the Team’s recommendations; the certificate of AACSB accreditation was received | April 12, 2006 |

# Plan Component: 4.1 Construct new College of Nursing Building.

| Designated Institution Staff: |  |
| --- | --- |
| Name | Mr. Larry Raab |
| Title | Director for Facilities Planning, Construction & Special Projects |
| Address | Prairie View A&M University |
| Phone | 936-261-1750 |
| Fax | 936-857-2350 |
| E-mail | llraab@pvamu.edu |

| Designated Board Staff: |  |
| --- | --- |
| Name | Ms. Lillian Wanjagi |
| Title | Program Director, Resource Planning |
| Address | Texas Higher Education Coordinating Board |
| Phone | 512-427-6125 |
| Fax | 512-427-6147 |
| E-mail | Lillian.Wanjagi@thecb.state.tx.us |

| Funding: |  |
| --- | --- |
| PUF (millions) | $ 41.77 |
| Expended and committed as of 3/31/06 | $ (40.61) |

Note:  Building only ($10 million garage is separate.  Funding provided from Hermann Memorial Hospital for garage.)

Summary

The overall construction of the Nursing Building was completed on 5 January 2006.  The College of Nursing began their “move-in” on 13 January 2006 and classes for spring 2006 were held in the new building. Minor ‘punch-list’ and warranty work will continue during the building’s first year of occupancy. A formal building dedication and ribbon cutting ceremony was held on 11 May 2006.

#### Implementation Schedule

| Task | Expected Completion Date | Outcome Documentation | Actual Completion Date |
| --- | --- | --- | --- |
| Project Initiation | July 2001 | Form C-1 (PVAMU) | July 2001 |
| Needs Assessment | August 2001 | Preliminary Program of Requirements | August 2001 |
| Send preliminary Program of Requirements to short list of Architect/Engineer Firms | September 2001 | Letters to Architect/Engineer Firms | September 2001 |
| Architect/Engineer Selection | October 2001 | TAMUS F, P&C & PVAMU User Coordinator | October 2001 |
| Program of Requirements | November 2001 | TAMUS F, P &C & PVAMU College of Nursing User Coordinator | October 2001 |
| Negotiate Architect/Engineer Contract | December 2001 | Architect/Engineer Contract | December 2001 |
| Progress Report | December 2001 | Report to the Coordinating Board | December 2001 |
| Initiate Concept Design | January 2002 | Architectural Drawings | January 2002 |
| Approve Concept Design | May 2002 | Letter of Approval | May 2002 |
| Authorize Construction Documents Preparation | May 2002 | Letter of Authorization | July 2002 |
| Progress Report | June 2002 | Report to the Coordinating Board | June 2002 |
| Construction Documents | October 2002 | Architectural & MEP Drawings | January 2003 |
| Accept contractor proposals | December 2002 | Proposals received | March 2003 |
| Progress Report | December 2002 | Report to the Coordinating Board | January 2003 |
| Bidding and Negotiations | January 2003 | TAMUS F, P&C & PVAMU User Coordinator | June 2003 |
| Contract Administration | February 2003 | TAMUS F, P&C & PVAMU User Coordinator | July 2003 |
| Construction Commencement | March 2003 | TAMUS F, P&C & PVAMU User Coordinator | September 2003 |
| Progress Report | June 2003 | Report to the Coordinating Board | July 2003 |
| Progress Report | December 2003 | Report to the Coordinating Board | January 2004 |
| Progress Report | June 2004 | Report to the Coordinating Board | July 2004 |
| Progress Report | December 2004 | Report to the Coordinating Board | December 2004 |
| Construction Complete | June 2005 | TAMUS Form 111300 | January 2006 |
| Progress Report | June 2005 | Report to the Coordinating Board | July 2005 |
| Install Movable Furnishings | July 2005 | Furnishings installed | January 2006 |
| Beneficial Occupancy | August 2005 | TAMUS Form C-13A | January 2006 |

# Plan Component: 4.2 Enhance the College of Nursing by strengthening existing nursing and related programs.

| Designated Institution Staff: |  |
| --- | --- |
| Name | Dr. Betty Adams |
| Title | Dean, College of Nursing |
| Address | Prairie View A&M University |
| Phone | 713-797-7007 |
| Fax | 713-797-7013 |
| E-mail | bnadams@pvamu.edu |

| Designated Board Staff: |  |
| --- | --- |
| Name | Dr. Roger Alford |
| Title | Program Director, Universities and Health-Related Institutions Division |
| Address | Texas Higher Education Coordinating Board |
| Phone | 512-427-6216 |
| Fax | 512-427-6168 |
| E-mail | Roger.alford@thecb.state.tx.us |

| Funding: |  |
| --- | --- |
| Appropriated 2002 (millions) | $ 0.50 |
| Appropriated 2003 (millions) | $ 0.50 |
| Appropriated 2004 (millions) | $ 0.44 |
| Appropriated 2005 (millions) | $ 0.44 |
| Expended as of 8/31/05 | $ (3.84) |
| FY 04 Budget Reallocation | $ 0.97 |
| FY 05 Budget Reallocation | $ 1.03 |
| Appropriated 2006 (millions) | $ 0.95 |
| FY 06 Expended & Committed 6/30 | $ (0.98) |
| Available as of 6/30/06 | $ 0.01 |

Summary

In meeting the OCR goal of enhancement, the College of Nursing has made the following progress in the last six months:  (1) achievement of two national accreditations by the National League for Nursing Accrediting Commission and the Commission on Collegiate Nursing Education; (2) commendation from the Texas Board of Nurse Examiners on the 95.6% licensing pass rate of nursing graduates, surpassing the State and National pass rate; (3) THECB approval to offer two new master of science degree programs:  nurse education and nurse administration; and (4) TAMUS Board of Regents preliminary approval to add a PhD in Nursing to the listing of program offerings.

Implementation Schedule (Date Added)

| Task | Expected Completion Date | Outcome Documentation | Actual Completion Date |
| --- | --- | --- | --- |
| Needs assessment for enhancement of programs and faculty productivity | September 2001 | Texas Commitment to Prairie View A&M University Strategic Plan | July 2001 |
| Progress Report | December 2001 | Report to the Coordinating Board | December 2001 |
| Program Evaluation | February 2002 | Academic department reports; external evaluation reports | April 2002 |
| Selection of Programs | April 2002 | University Academic Council approval | April 2002 |
| Progress Report | June 2002 | Report to the Coordinating Board | June 2002 |
| Prepare any proposals requiring approval by the Board of Regents | September 2002 | Board of Regents approval | NA |
| Progress Report | December 2002 | Report to the Coordinating Board | January 2003 |
| Progress Report | June 2003 | Report to the Coordinating Board | July 2003 |
| Selection of a Faculty Practice Model | September 2003 | Program presentation by the College of Nursing faculty | March 17, 2004 |
| Prepare proposal for a Research and Faculty Development Center | September 2003 | TAMUS approval of a Research and Faculty Development Center | December 2004 & continuing |
| Progress Report | December 2003 | Report to the Coordinating Board | January 2004 |
| Progress Report | June 2004 | Report to the Coordinating Board | July 2004 |
| Progress Report | June 2005 | Report to the Coordinating Board | June 2005 |
| Progress Report | December 2005 | Report to the Coordinating Board | December 2005 |
| Progress Report | June 2006 | Report to the Coordinating Board | June 2006 |
| Progress Report | December 2006 | Report to the Coordinating Board |  |
| Progress Report | June 2007 | Report to the Coordinating Board |  |
| Component fully implemented | August 2007 | Texas Commitment to Prairie View A&M University Strategic Plan with accomplishments identified |  |

# Plan Component: 5.1 Enhance the College of Engineering by strengthening existing engineering and related programs.

| Designated Institution Staff: |  |
| --- | --- |
| Name | Dr. Milton R. Bryant |
| Title | Dean, College of Engineering |
| Address | Prairie View A&M University |
| Phone | 936-857-2211 |
| Fax | 936-857-2222 |
| E-mail | mrbryant@pvamu.edu |

| Designated Board Staff: |  |
| --- | --- |
| Name | Dr. Roger Alford |
| Title | Program Director, Universities and Health-Related Institutions Division |
| Address | Texas Higher Education Coordinating Board |
| Phone | 512-427-6216 |
| Fax | 512-427-6168 |
| E-mail | Roger.alford@thecb.state.tx.us |

| Funding: |  |
| --- | --- |
| Appropriated 2002 (millions) | $ 0.50 |
| Appropriated 2003 (millions) | $ 0.50 |
| Appropriated 2004 (millions) | $ 0.44 |
| Appropriated 2005 (millions) | $ 0.17 |
| Expended as of 8/31/05 | $ (1.47) |
| FY 04 Budget Reallocation | $ (0.07) |
| FY 05 Budget Reallocation | $ (0.04) |
| Appropriated 2006 (millions) | $ 0.37 |
| FY 06 Expended & Committed 6/30 | $ (0.28 |
| Available as of 6/30/06 | $ 0.12 |

Summary

As part of the plan to enhance the College of Engineering, a continuing effort to improve the College’s presence in the business community and among prospective students has been made through committed website enhancements.  Support to the Assistant Dean enables a more careful monitoring of a grant received from the National Action Council for Minorities in Engineering, a competitive grant provided to a select few engineering colleges or universities. Support for faculty development and faculty/administrative travel to professional meetings contributed to the strengthening of the student retention initiative.  The robotic initiative support continued.  Professional services, including ABET annual maintenance fees as well as National Student Benchmark Assessment, also continued.  Support continued for the College ABET Assessment Committee chair, who monitors the college’s continuing quality improvement practices.  Dr. Paul Biney, chair of the ABET Assessment Committee, completed the actions on the Engineering and Engineering Technology academic program curriculum assessment for fall 2005 and spring 2006.  The college continues to monitor its Senior Design courses to accommodate comments provided by ABET during its last visit.

Implementation Schedule

| Task | Expected Completion Date | Outcome Documentation | Actual Completion Date |
| --- | --- | --- | --- |
| Evaluate future needs and opportunities for the College of Engineering | September 2001 | Texas Commitment to Prairie View A&M University Strategic Plan | July 2001 |
| Evaluate all academic programs | September 2001 | Annual academic department reports | September 2001 |
| Progress Report | December 2001 | Report to the Coordinating Board | December 2001 |
| Determine non-substantive programmatic changes | January 2002 | University Academic/Graduate Council approval | NA* |
| Determine substantive programmatic changes | January 2002 | University Academic/Graduate Council approval | NA* |
| Prepare any proposals requiring approval by the Board of Regents | March 2002 | Board of Regents approval | NA* |
| Prepare any proposals requiring approval by the Coordinating Board | June 2002 | Coordinating Board approval (Note: CB approval would only be needed if major changes are made to programs or if new programs are developed.) | NA* |
| Progress Report | June 2002 | Report to the Coordinating Board | June 2002 |
| Faculty/Staff Recruitment | July 2002 | Faculty/Staff numbers and credentials are appropriate for the needs of the College | October 2002 |
| Progress Report | December 2002 | Report to the Coordinating Board | January 2003 |
| Progress Report | June 2003 | Report to the Coordinating Board | July 2003 |
| Progress Report | December 2003 | Report to the Coordinating Board | January 2004 |
| Progress Report | June 2004 | Report to the Coordinating Board | July 2004 |
| Progress Report | December 2004 | Report to the Coordinating Board | December 2004 |
| Progress Report | June 2005 | Report to the Coordinating Board | June 2005 |
| Progress Report | December 2005 | Report to the Coordinating Board | January 2006 |
| Progress Report | June 2006 | Report to the Coordinating Board | June 2006 |
| Progress Report | December 2006 | Report to the Coordinating Board |  |
| Progress Report | June 2007 | Report to the Coordinating Board |  |
| Component fully implemented | August 2007 | Texas Commitment to Prairie View A&M University Strategic Plan with accomplishments identified |  |

# Plan Component: 5.2a Develop new MS program in Electrical Engineering.

| Designated Institution Staff: |  |
| --- | --- |
| Name | Dr. Milton R. Bryant |
| Title | Dean, College of Engineering |
| Address | Prairie View A&M University |
| Phone | 936-857-2211 |
| Fax | 936-857-2222 |
| E-mail | mrbryant@pvamu.edu |

| Designated Board Staff: |  |
| --- | --- |
| Name | Dr. Roger Alford |
| Title | Program Director, Universities and Health-Related Institutions Division |
| Address | Texas Higher Education Coordinating Board |
| Phone | 512-427-6216 |
| Fax | 512-427-6168 |
| E-mail | Roger.alford@thecb.state.tx.us |

| Funding: |  |
| --- | --- |
| Appropriated 2002 (millions) | $ 0.45 |
| Appropriated 2003 (millions) | $ 0.45 |
| Appropriated 2004 (millions) | $ 0.40 |
| Appropriated 2005 (millions) | $ 0.40 |
| Expended as of 8/31/05 | $ (1.32) |
| FY 04 Budget Reallocation | $ (0.12) |
| FY 05 Budget Reallocation | $ (0.10) |
| Appropriated 2006 (millions) | $ 0.30 |
| FY 06 Expended & Committed 6/30 | $ (0.38) |
| Available as of 6/30/06 | $ 0.07 |

Summary

A CREST proposal was submitted to the National Science Foundation (NSF) in spring 2006 for the support of research activities in the electrical engineering masters program.  During the spring 2006 semester, seventeen (17) students were enrolled in the program, which continues to show steady growth.  A student recruitment plan has been developed and is being implemented to attract more students into the program, and faculty visited several universities in Texas and outside the state as part of this recruitment effort.

Implementation Schedule

| Task | Expected Completion Date | Outcome Documentation | Actual Completion Date |
| --- | --- | --- | --- |
| Assign faculty to the program and assess faculty recruitment needs | March 2001 | Faculty Contracts | March 2001 |
| Prepare program proposal | June 2001 | Program proposal (Draft proposal sent to System and CB) | June 2001 |
| Submit proposal to the Graduate Council | June 2001 | Graduate Council approval | June 2001 |
| Prepare proposal for the Board of Regents | September 2001 | Board of Regents approval | September 2001 |
| Progress Report | December 2001 | Report to the Coordinating Board | December 2001 |
| Prepare proposal for the Coordinating Board | January 2002 | Coordinating Board approval | January 2002 |
| Progress Report | June 2002 | Report to the Coordinating Board | June 2002 |
| Faculty Recruitment | July 2002 | Faculty numbers and credentials are appropriate for the needs of the program | July 2002 |
| Accept first students into the program | September 2002 | Student registration information | August 2002 |
| Progress Report | December 2002 | Report to the Coordinating Board | January 2003 |
| Progress Report | June 2003 | Report to the Coordinating Board | June 2003 |
| Progress Report | December 2003 | Report to the Coordinating Board | January 2004 |
| Progress Report | June 2004 | Report to the Coordinating Board | June 2004 |
| Progress Report | December 2004 | Report to the Coordinating Board | December 2004 |
| Progress Report | June 2005 | Report to the Coordinating Board | July 2005 |
| Program Evaluation | October 2005 | Panel of Evaluators Report | October 2005 |
| Progress Report | December 2005 | Report to the Coordinating Board | December 2005 |
| Progress Report | June 2006 | Report to the Coordinating Board | June 2006 |
| Progress Report | December 2006 | Report to the Coordinating Board |  |
| Progress Report | June 2007 | Report to the Coordinating Board |  |
| Program Evaluation | September 2007 | Student graduation and success rates |  |
| Component fully implemented | September 2007 | Program supported through formula funding |  |
| Progress Report | June 2008 | Report to the Coordinating Board |  |
| Component fully implemented | September 2008 | Program supported through formula funding |  |

# Plan Component: 5.2b Develop new PhD program in Electrical Engineering.

| Designated Institution Staff: |  |
| --- | --- |
| Name | Dr. Milton R. Bryant |
| Title | Dean, College of Engineering |
| Address | Prairie View A&M University |
| Phone | 936-857-2211 |
| Fax | 936-857-2222 |
| E-mail | mrbryant@pvamu.edu |

| Designated Board Staff: |  |
| --- | --- |
| Name | Dr. Roger Alford |
| Title | Program Director, Universities and Health-Related Institutions Division |
| Address | Texas Higher Education Coordinating Board |
| Phone | 512-427-6216 |
| Fax | 512-427-6168 |
| E-mail | Roger.alford@thecb.state.tx.us |

| Funding: |  |
| --- | --- |
| Appropriated 2002 (millions) | $ 0.45 |
| Appropriated 2003 (millions) | $ 0.45 |
| Appropriated 2004 (millions) | $ 0.40 |
| Appropriated 2005 (millions) | $ 0.40 |
| Expended as of 8/31/05 | $ (1.32) |
| FY 04 Budget Reallocation | $ (0.12) |
| FY 05 Budget Reallocation | $ (0.10) |
| Appropriated 2006 (millions) | $ 0.55 |
| FY 06 Expended & Committed 6/30 | $ (0.52) |
| Available as of 6/30/06 | $ 0.19 |

Summary

The program admitted its first students in fall 2003 and enrolled sixteen (16) students in the program during spring 2006 semester.  To bolster our recruitment efforts, faculty members visited several universities in Texas and outside the state to provide interface with potential students and will continue to do so. In addition, faculty members also recruited students at national conferences.  The Department of Electrical Engineering interviewed several prospective candidates for faculty positions during this six month period. In the next six months, faculty members will be submitting a multi-million dollar proposal to the Defense Advanced Research Projects Agency (DARPA).  In addition, the Department will be implementing its formal recruitment plan to attract more students into the program.

Implementation Schedule

| Task | Expected Completion Date | Outcome Documentation | Actual Completion Date |
| --- | --- | --- | --- |
| Assign faculty to the program and assess faculty recruitment needs | August 2001 | Faculty Contracts | August 2001 |
| Prepare program proposal | August 2001 | Program proposal (Draft proposal sent to System and CB) | August 2001 |
| Submit proposal to the University Graduate Council | September 2001 | Graduate Council approval | September 2001 |
| Prepare proposal for the Board of Regents | December 2001 | Board of Regents approval | March 2002 |
| Progress Report | December 2001 | Report to the Coordinating Board | December 2001 |
| Prepare proposal for the Coordinating Board | January 2002 | Proposal submitted to the Coordinating Board | March 2002 |
| Progress Report | June 2002 | Report to the Coordinating Board | June 2002 |
| First Proposal Review | July 2002 | Out-of-State Reviewers Report | December 2002 |
| Progress Report | December 2002 | Report to the Coordinating Board | January 2003 |
| Second Proposal Review by the Coordinating Board | April 2003 | Coordinating Board approval | NA |
| Progress Report | June 2003 | Report to the Coordinating Board | July 2003 |
| Prepare substantive change request for SACS | August 2003 | SACS approval | August 2003 |
| Faculty Recruitment | August 2003 | Faculty numbers and credentials are appropriate for the needs of the program | September 2003 |
| Accept first students into the program | September 2003 | Student registration information | September 2003 |
| Progress Report | December 2003 | Report to the Coordinating Board | January 2004 |
| Progress Report | June 2004 | Report to the Coordinating Board | June 2004 |
| Program Evaluation | September 2004 | Student retention and success rates | December 2004 |
| Progress Report | December 2004 | Report to the Coordinating Board | December 2004 |
| Progress Report | June 2005 | Report to the Coordinating Board | July 2005 |
| Progress Report | December 2005 | Report to the Coordinating Board | December 2005 |
| Progress Report | June 2006 | Report to the Coordinating Board | June 2006 |
| Progress Report | December 2006 | Report to the Coordinating Board |  |
| Progress Report | June 2007 | Report to the Coordinating Board |  |
| Program Evaluation | September 2007 | Student graduation and success rates |  |
| Component fully implemented | September 2007 | Program supported through formula funding |  |

# Plan Component: 5.3 Upgrade or build additional Engineering facilities as needed.

| Designated Institution Staff: |  |
| --- | --- |
| Name | Mr. Larry Raab |
| Title | Director for Facilities Planning, Construction & Special Projects |
| Address | Prairie View A&M University |
| Phone | 936-261-1750 |
| Fax | 936-857-2350 |
| E-mail | llraab@pvamu.edu |

| Designated Board Staff: |  |
| --- | --- |
| Name | Ms. Lillian Wanjagi |
| Title | Program Director, Resource Planning |
| Address | Texas Higher Education Coordinating Board |
| Phone | 512-427-6125 |
| Fax | 512-427-6147 |
| E-mail | Lillian.Wanjagi@thecb.state.tx.us |
| Funding: |  |
| TRB (millions) | $ 12.62 |
| Expended and committed as of 3/31/06 | $ (12.19) |

Summary

Substantial completion of the new Electrical Engineering Building occurred on March 31, 2005, while overall construction completion occurred on November 11, 2005. Move-in and occupancy occurred in July 2005. Classes were held in the building during the fall 2005 term. An official dedication and ribbon cutting ceremony was held on August 25, 2005. This project was completed on time and under budget.

Implementation Schedule

| Task | Expected Completion Date | Outcome Documentation | Actual Completion Date |
| --- | --- | --- | --- |
| Each department in the College evaluates needs for classroom, research, and graduate student office space and submits report to Dean | April 2001 | Reports to Dean with details of plan for growth and additional facility needs for the department | April 2001 |
| Department heads and dean meet and determine needs and priorities | May 2001 | Report detailing priorities | May 2001 |
| Appoint College Committee to receive comments from faculty, research directors and others | June 2001 | Selection of Members, Chair and delegate charge to committee | June 2001 |
| Committee Meetings and solicitation of comments and Recommendation to Dean | June 2001 | Recommendations to Dean | June 2001 |
| Evaluate future needs and opportunities for the College of Engineering | July 2001 | Texas Commitment to Prairie View A&M University Strategic Plan | July 2001 |
| Determine the future space and equipment needs for the College of Engineering | August 2001 | College of Engineering Master Plan | August 2001 |
| Decision made whether to build or renovate | August 2001 | Report to the Coordinating Board | August 2001 |
| Progress Report | December 2001 | Report to the Coordinating Board | December 2001 |
| Project Initiation | January 2002 | Form C-1 (PVAMU) | January 2002 |
| Needs Assessment | February 2002 | Preliminary Program of Requirements | February 2002 |
| Send preliminary Program of Requirements to short list of Architect/Engineer Firms | March 2002 | Letters to Architect/Engineer Firms | March 2002 |
| Architect/Engineer Selection | April 2002 | TAMUS F, P&C & PVAMU User Coordinator Form C-31 | April 2002 |
| Program of Requirements | May 2002 | TAMUS F, P &C & PVAMU College of Engineering User Coordinator | May 2002 |
| Negotiate Architect/Engineer Contract | June 2002 | Architect/Engineer Contract | June 2002 |
| Progress Report | June 2002 | Report to the Coordinating Board | June 2002 |
| Initiate Concept Design | July 2002 | Architectural Drawings | July 2002 |
| Approve Concept Design | August 2002 | Letter of Approval | November 2002 |
| Authorize Construction Documents Preparation | October 2002 | Letter of Authorization | December 2002 |
| Progress Report | December 2002 | Report to the Coordinating Board | January 2003 |
| Construction Documents | March 2003 | Architectural & MEP Drawings | May 2003 |
| Accept contractor proposals | May 2003 | Proposals received | June 2003 |
| Bidding and Negotiations | June 2003 | TAMUS F, P&C & PVAMU User Coordinator | June 2003 |
| Progress Report | June 2003 | Report to the Coordinating Board | July 2003 |
| Contract Administration | July 2003 | TAMUS F, P&C & PVAMU User Coordinator | December 2003 |
| Construction Commencement | August 2003 | TAMUS F, P&C & PVAMU User Coordinator | January 2004 |
| Progress Report | December 2003 | Report to the Coordinating Board | January 2004 |
| Progress Report | June 2004 | Report to the Coordinating Board | July 2004 |
| Construction Complete | November 2004 | TAMUS Form 111300 | May 2005 |
| Install Movable Furnishings | December 2004 | Furnishings installed | June 2005 |
| Progress Report | December 2004 | Report to the Coordinating Board | December 2004 |
| Beneficial Occupancy | January 2005 | TAMUS Form C-13A | June 2005 |

# Plan Component: 6.1 Enhance Educator Preparation programs.

| Designated Institution Staff: |  |
| --- | --- |
| Name | Dr. M. Paul Mehta |
| Title | Dean, College of Education |
| Address | Prairie View A&M University |
| Phone | 936-857-2918 |
| Fax | 936-857-2911 |
| E-mail | mpmehta@pvamu.edu |

| Designated Board Staff: |  |
| --- | --- |
| Name | Dr. Roger Alford |
| Title | Program Director, Universities and Health-Related Institutions Division |
| Address | Texas Higher Education Coordinating Board |
| Phone | 512-427-6216 |
| Fax | 512-427-6168 |
| E-mail | Roger.alford@thecb.state.tx.us |

| Funding: |  |
| --- | --- |
| Appropriated 2002 (millions) | $ 0.40 |
| Appropriated 2003 (millions) | $ 0.40 |
| Appropriated 2004 (millions) | $ 0.35 |
| Appropriated 2005 (millions) | $ 0.35 |
| Expended as of 8/31/05 | $ (1.30) |
| FY 04 Budget Reallocation | $ (0.06) |
| FY 05 Budget Reallocation | $ (0.09) |
| Appropriated 2006 (millions) | $ 0.37 |
| FY 06 Expended & Committed 6/30 | $ (0.29) |
| Available as of 6/30/06 | $ 0.13 |

Summary

The College of Education hosted an accreditation visit by the National Council for Accreditation of Teacher Education (NCATE) Board of Examiners (BOD) on April 22-26, 2006.  The BOD report was received in the middle of June 2006 and a rejoinder to the BOD report is being submitted to NCATE. The final decision will be made by the NCATE Unit Accreditation Board in September/October 2006.

Implementation Schedule

| Task | Expected Completion Date | Outcome Documentation | Actual Completion Date |
| --- | --- | --- | --- |
| Site visit by NCATE Board of Examiners | May 2001 | NCATE Board of Examiners Report | May 2001 |
| Annual determination of accreditation status by the State Board for Educator Certification (SBEC) | September 2001 | Memorandum from the Executive Director of SBEC indicating accreditation status | October 2001 |
| Evaluate future needs and opportunities for the College of Education | September 2001 | Texas Commitment to Prairie View A&M University Strategic Plan | July 2001 |
| Action by the NCATE Unit Accreditation Board | October 2001 | Memorandum of compliance with NCATE standards | November 2001 |
| Evaluate all academic programs | November 2001 | Annual academic department reports | November 2001 |
| Progress Report | December 2001 | Report to the Coordinating Board | December 2001 |
| Progress Report | June 2002 | Report to the Coordinating Board | June 2002 |
| Faculty Recruitment | September 2002 | Faculty numbers and credentials are appropriate for the needs of the College | August 2002 |
| Progress Report | December 2002 | Report to the Coordinating Board | January 2003 |
| Determine non-substantive programmatic changes | January 2003 | University Academic/Graduate Council approval | January 2003 |
| Determine substantive programmatic changes | May 2003 | University Academic/Graduate Council approval | February 2003 |
| Progress Report | June 2003 | Report to the Coordinating Board | July 2003 |
| Prepare any proposals requiring approval by the Board of Regents | September 2003 | Board of Regents approval | NA |
| Progress Report | December 2003 | Report to the Coordinating Board | January 2004 |
| Prepare any proposals requiring approval by the Coordinating Board | January 2004 | Coordinating Board approval (if needed) | NA |
| Progress Report | June 2004 | Report to the Coordinating Board | July 2004 |
| Progress Report | December 2004 | Report to the Coordinating Board | December 2004 |
| Progress Report | June 2005 | Report to the Coordinating Board | June 2005 |
| Progress Report | December 2005 | Report to the Coordinating Board | December 2005 |
| Site Visit by NCATE | April 2006 | NCATE Board of Examiner’s Report | June 2006 |
| Rejoinder to NCATE Board of Examiner’s Report | June 2006 | Rejoinder to NCATE Board of Examiner’s Report | June 2006 |
| Progress Report | June 2006 | Report to the Coordinating Board |  |
| Progress Report | December 2006 | Report to the Coordinating Board |  |
| Progress Report | June 2007 | Report to the Coordinating Board |  |
| Component fully implemented | August 2007 | Texas Commitment to Prairie View A&M University Strategic Plan with accomplishments identified |  |

# Plan Component: 7.1 Develop new BS in Construction Science.

| Designated Institution Staff: |  |
| --- | --- |
| Name | Dr. Ikhlas Sabouni |
| Title | Dean, School of Architecture |
| Address | Prairie View A&M University |
| Phone | 936-261-9810 |
| Fax | 936-261-9826 |
| E-mail | isabouni@pvamu.edu |

| Designated Board Staff: |  |
| --- | --- |
| Name | Dr. Roger Alford |
| Title | Program Director, Universities and Health-Related Institutions Division |
| Address | Texas Higher Education Coordinating Board |
| Phone | 512-427-6216 |
| Fax | 512-427-6168 |
| E-mail | Roger.alford@thecb.state.tx.us |

| Funding: |  |
| --- | --- |
| Appropriated 2002 (millions) | $ 0.50 |
| Appropriated 2003 (millions) | $ 0.50 |
| Appropriated 2004 (millions) | $ 0.00 |
| Appropriated 2005 (millions) | $ 0.00 |
| Expended as of 8/31/05 | $ (0.71) |
| FY 04 Budget Reallocation | $ (0.12) |
| FY 05 Budget Reallocation | $ 0.00 |
| Appropriated 2006 (millions) | $ 0.00 |
| FY 06 Expended & Committed 6/30 | $ (0.11) |
| Available as of 6/30/06 | 0.06 |

#### Summary

The School is recruiting for the Construction Science program/major from incoming freshmen students as well as transfer and change-of major students.  The program now has about 50 students, and is generating considerable formula dollars (see Appendix C).  Dr. James Smith, former Department Head of the Construction Science Program at Texas A&M University, was hired as a special consultant to lead the program.  His focus for the fall 2005 term was to advise on curriculum changes, program accreditation, student advising, faculty recruiting, and establishing the program’s Construction Industry Advisory Council; Dr. Smith also taught two courses.  Discussions were held with the American Council for Construction Education (ACCE) concerning accreditation; the Executive Director for ACCE visited the program at PVAMU, and an application to enter candidate status with ACCE was forwarded to the Provost.  The Construction Industry Advisory Council, comprised of major construction firms and suppliers to the building industry, met and adopted by-laws. The Coordinator position has been posted to recruit a permanent hire for the position that Dr. Smith assumed temporarily in the fall 2005; candidates are currently being interviewed and a permanent hire is expected to be made in summer 2006.  For the fall 2005 semester, the program hired three professors from the Construction Science program at Texas A&M to teach courses.  Recommended changes to the curriculum to bring it into conformance with ACCE accreditation requirements were approved by the Dean and by the University’s Academic Affairs Committee for implementation in fall 2006.  These changes reduce degree program hours to 121, including 6 hours for two summer internships. With the growing demand for workers in the construction industry and the increased use of design/build firms, Dr. Smith identified 10 core courses that could be taken to earn a second degree in Construction Science while also completing a degree in Architecture.

Bachelor of Science in Construction Science Degree - Program is in its third year as of 05-06

| CATEGORY | YEAR 3 05 - 06 |
| --- | --- |
| Total Projected Enrollment, in Proposal | 55 *** |
| Total Enrolled Students, Spring 2006 | 46 ** |
| Graduates, Fall 2005 & Spring 2006 | 6 |

**Less than projections

***Includes projected 18 Community College (CC) Transfer students (not implemented yet)

PVAMU articulation agreement with North Harris Community College  has been established & awaits university approval

Implementation Schedule

| Task | Expected Completion Date | Outcome Documentation | Actual Completion Date |
| --- | --- | --- | --- |
| Assign faculty to the program and assess faculty recruitment needs | November 2000 | Faculty Contracts | November 2000 |
| Prepare program proposal | December 2000 | Program proposal (Draft proposal sent to CB) | December 2000 |
| Submit proposal to the University Academic Council | January 2001 | Academic Council approval | January 2001 |
| Prepare proposal for the Board of Regents | March 2001 | Board of Regents approval | March 2001 |
| Prepare proposal for the Coordinating Board | June 2001 | Coordinating Board approval | June 2002 |
| Faculty Recruitment | August 2001 | Faculty numbers and credentials are appropriate for the needs of the program | June 2002 |
| Accept first students into the program | September 2001 | Student registration information | September 2002 |
| Progress Report | December 2001 | Report to the Coordinating Board | December 2001 |
| Progress Report | June 2002 | Report to the Coordinating Board | June 2002 |
| Progress Report | December 2002 | Report to the Coordinating Board | January 2003 |
| Progress Report | June 2003 | Report to the Coordinating Board | July 2003 |
| Program Evaluated | September 2003 | Student retention and success rates | February 2004 |
| Progress Report | December 2003 | Report to the Coordinating Board | January 2004 |
| Progress Report | June 2004 | Report to the Coordinating Board | July 2004 |
| Progress Report | December 2004 | Report to the Coordinating Board | December 2004 |
| Progress Report | June 2005 | Report to the Coordinating Board | July 2005 |
| Program Evaluated | September 2005 | Student graduation and success rates |  |
| Progress Report | December 2005 | Report to the Coordinating Board | December 2005 |
| Progress Report | June 2006 | Report to the Coordinating Board | July 2006 |
| Progress Report | December 2006 | Report to the Coordinating Board |  |
| Progress Report | June 2007 | Report to the Coordinating Board |  |
| Component fully implemented | September 2007 | Program supported through formula funding |  |

# Plan Component: 7.2 Develop new Master of Architecture.

| Designated Institution Staff: |  |
| --- | --- |
| Name | Dr. Ikhlas Sabouni |
| Title | Dean, School of Architecture |
| Address | Prairie View A&M University |
| Phone | 936-261-9810 |
| Fax | 936-261-9826 |
| E-mail | isabouni@pvamu.edu |

| Designated Board Staff: |  |
| --- | --- |
| Name | Dr. Roger Alford |
| Title | Program Director, Universities and Health-Related Institutions Division |
| Address | Texas Higher Education Coordinating Board |
| Phone | 512-427-6216 |
| Fax | 512-427-6168 |
| E-mail | Roger.alford@thecb.state.tx.us |

| Funding: |  |
| --- | --- |
| Appropriated 2002 (millions) | $ 0.50 |
| Appropriated 2003 (millions) | $ 0.50 |
| Appropriated 2004 (millions) | $ 0.44 |
| Appropriated 2005 (millions) | $ 0.44 |
| Expended as of 8/31/05 | $ (1.47) |
| FY 04 Budget Reallocation | $ (0.07) |
| FY 05 Budget Reallocation | $ (0.11) |
| Appropriated 2006 (millions) | $ 0.42 |
| FY 06 Expended & Committed 6/30 | $ (0.59) |
| Available as of 6/30/06 | $ 0.06 |

#### Summary

The School of Architecture admitted eighty (80) freshmen students in Fall Semester 2005 to pursue the five-year Master of Architecture degree program adopted in 2002.  Retention was above the university average as approximately 75% of these students successfully completed their studies in spring 2006.  Currently over 200 students are pursuing degrees in architecture.  The School continued its successful placement of graduates as those leaving with their professional architecture degrees in December 2005 and May 2006 had all obtained full employment upon completing their studies at PVAMU.  Their employers are located in Houston, Dallas, and San Antonio. The school received its scheduled re-accreditation visit by the National Architectural Accreditation Board (NAAB) in April 2006, with the goal of obtaining full accreditation for another six-year term.   The NAAB report is due to the School in July 2006.

Our student team competed and won the 9th Annual Sand Castle Competition sponsored by the Houston AIA Chapter held in Galveston.  This marks the 4th time in the last five years the School of Architecture has won the Challenge, and two consecutive years.

Five-year Masters of Architecture Degree Program is in its fourth year as of 05-06

| CATEGORY | YEAR 4 05 - 06 |
| --- | --- |
| Total Projected Enrollment, in Proposal | 234 |
| Total Enrolled Students, Spring 2006 | 276 * |
| Graduates, Fall 2005 & Spring 2006 | 28 |

* Exceeded projections

Implementation Schedule

| Task | Expected Completion Date | Outcome Documentation | Actual Completion Date |
| --- | --- | --- | --- |
| Assign faculty to the program and assess faculty recruitment needs | March 2001 | Faculty Contracts | March 2001 |
| Prepare program proposal | March 2001 | Program proposal (Draft proposal sent to CB) | July 2001 |
| Submit proposal to the University Graduate Council | May 2001 | Graduate Council approval | July 2001 |
| Prepare proposal for the Board of Regents | July 2001 | Board of Regents approval | September 2001 |
| Prepare proposal for the Coordinating Board | October 2001 | Coordinating Board approval | October 2001 |
| Faculty Recruitment | December 2001 | Faculty numbers and credentials are appropriate for the needs of the program | December 2001 |
| Progress Report | December 2001 | Report to the Coordinating Board | December 2001 |
| Accept first students into the program | January 2002 | Student registration information | January 2002 |
| Progress Report | June 2002 | Report to the Coordinating Board | June 2002 |
| Progress Report | December 2002 | Report to the Coordinating Board | January 2003 |
| Program self-study | January 2003 | Application for professional accreditation | January 2003 |
| Progress Report | June 2003 | Report to the Coordinating Board | July 2003 |
| Progress Report | December 2003 | Report to the Coordinating Board | January 2004 |
| Progress Report | June 2004 | Report to the Coordinating Board | July 2004 |
| Progress Report | December 2004 | Report to the Coordinating Board | December 2004 |
| Progress Report | June 2005 | Report to the Coordinating Board | June 2005 |
| Progress Report | December 2005 | Report to the Coordinating Board | December 2005 |
| Progress Report | June 2006 | Report to the Coordinating Board | June 2006 |
| Program Evaluation | October 2006 | Professional accreditation approved |  |
| Progress Report | December 2006 | Report to the Coordinating Board |  |
| Progress Report | June 2007 | Report to the Coordinating Board |  |
| Program Evaluation | September 2007 | Student graduation and success rates |  |
| Progress Report | December 2007 | Report to the Coordinating Board |  |
| Component fully implemented | January 2008 | Program supported through formula funding |  |

# Plan Component: 7.3 Construct new School of Architecture building.

| Designated Institution Staff: |  |
| --- | --- |
| Name | Dr. Ikhlas Sabouni |
| Title | Dean, School of Architecture |
| Address | Prairie View A&M University |
| Phone | 936-261-9810 |
| Fax | 936-261-9826 |
| E-mail | isabouni@pvamu.edu |

| Designated Board Staff: |  |
| --- | --- |
| Name | Ms. Lillian Wanjagi |
| Title | Program Director, Resource Planning |
| Address | Texas Higher Education Coordinating Board |
| Phone | 512-427-6125 |
| Fax | 512-427-6147 |
| E-mail | Lillian.Wanjagi@thecb.state.tx.us |

| Funding: |  |
| --- | --- |
| TRB (millions) | $ 25.20 |
| Expended and committed as of 3/31/06 | $ (24.76) |

Summary

The construction of the new Architecture Building is complete, with the building being occupied on August 15, 2005. Classes taught for the fall 2005 semester began August 22, 2005.  The Grand Opening and Dedication for the facility was held on October 27, 2005.  The January 2006 issue of Texas Architect features a cover story on the new building, which was also the subject of a featured article in the January 2005 issue of Architectural Record.   The Spring issue of Cite: the Architecture and Design Review of Houston magazine featured another article about the new building.  Several tours by different groups and interested individuals visited the School and viewed the new building.  The Texas Society of Architects is planning to conduct its Summer Board Meeting in the School in July 2006.  A conference by the College of Juvenile Justice was conducted in the new building in April.  A conference by the Texas A& M University System is planned in the building for spring 2007.  The distinct architecture of this building has brought considerable positive publicity and visibility to the University and the Architecture Program.

Implementation Schedule

| Task | Expected Completion Date | Outcome Documentation | Actual Completion Date |
| --- | --- | --- | --- |
| Project Initiation | July 2001 | Form C-1 (PVAMU) | July 2001 |
| Needs Assessment | August 2001 | Preliminary Program of Requirements | August 2001 |
| Send preliminary Program of Requirements to short list of Architect/Engineer Firms | September 2001 | Letters to Architect/Engineer Firms | September 2001 |
| Architect/Engineer Selection | October 2001 | TAMUS F, P&C & PVAMU User Coordinator Form C-31 | October 2001 |
| Program of Requirements | November 2001 | TAMUS F, P &C & PVAMU School of Architecture User Coordinator | October 2001 |
| Negotiate Architect/Engineer Contract | December 2001 | Architect/Engineer Contract | December 2001 |
| Progress Report | December 2001 | Report to the Coordinating Board | December 2001 |
| Initiate Concept Design | January 2002 | Architectural Drawings | January 2002 |
| Approve Concept Design | June 2002 | Letter of Approval | May 2002 |
| Authorize Construction Documents Preparation | June 2002 | Letter of Authorization | July 2002 |
| Progress Report | June 2002 | Report to the Coordinating Board | June 2002 |
| Construction Documents | December 2002 | Architectural & MEP Drawings | December 2002 |
| Progress Report | December 2002 | Report to the Coordinating Board | January 2003 |
| Accept contractor proposals | February 2003 | Proposals received | February 2003 |
| Bidding and Negotiations | March 2003 | TAMUS F, P&C & PVAMU User Coordinator | March 2003 |
| Contract Administration | April 2003 | TAMUS F, P&C & PVAMU User Coordinator | June 2003 |
| Construction Commencement | May 2003 | TAMUS F, P&C & PVAMU User Coordinator | July 2003 |
| Progress Report | June 2003 | Report to the Coordinating Board | July 2003 |
| Progress Report | December 2003 | Report to the Coordinating Board | January 2004 |
| Progress Report | June 2004 | Report to the Coordinating Board | July 2004 |
| Progress Report | December 2004 | Report to the Coordinating Board | December 2004 |
| Construction Complete | February 2005 | TAMUS Form 111300 | August 2005 |
| Install Movable Furnishings | March 2005 | Furnishings installed | August 2005 |
| Beneficial Occupancy | April 2005 | TAMUS Form C-13A |  |

# Plan Component: 8.1 Carry out renovations identified in Master Plan.

| Designated Institution Staff: |  |
| --- | --- |
| Name | Mr. Larry L. Raab |
| Title | Director for Facilities, Planning, Construction and Special Projects |
| Address | Prairie View A&M University |
| Phone | 936-261-1750 |
| Fax | 936-857-4888 |
| E-mail | llraab@pvamu.edu |

| Designated Board Staff: |  |
| --- | --- |
| Name | Ms. Lillian Wanjagi |
| Title | Program Director, Resource Planning |
| Address | Texas Higher Education Coordinating Board |
| Phone | 512-427-6125 |
| Fax | 512-427-6147 |
| E-mail | lillian.wanjagi@thecb.state.tx.us |

| Funding: |  |
| --- | --- |
| TRB (millions) | $ 15.01 |
| Expended and committed as of 3/31/06 | $ (12.14) |

Summary

Priority Packages 1, 2 and 3 have been completed. Package 3 was completed in May 2006. Package 4, the total replacement of the masonry exterior of the JB Coleman Library has been removed from this package and has been placed in a separate package that is anticipated to be discussed at the next Texas A&M University Board of Regents meeting in July 2006.

Implementation Schedule

| Task | Expected Completion Date | Outcome Documentation | Actual Completion Date |
| --- | --- | --- | --- |
| Identify projects | June 2001 | PVAMU Master Plan projects list | June 2001 |
| Initiate FY 2002 projects | June 2006 | PVAMU individual project file |  |
| Progress Report | December 2001 | Report to the Coordinating Board | December 2001 |
| Revalidate update project listing | May 2002 | PVAMU Master Plan projects list | April 2002 |
| Identify projects | June 2002 | PVAMU Master Plan projects list | April 2002 |
| Progress Report | June 2002 | Report to the Coordinating Board | June 2002 |
| Initiate FY 2002 projects | June 2006 | PVAMU individual project file |  |
| Progress Report | December 2002 | Report to the Coordinating Board | January 2003 |
| Revalidate update project listing | May 2003 | PVAMU Master Plan projects list | May 2003 |
| Identify projects | June 2003 | PVAMU Master Plan projects list | June 2003 |
| Progress Report | June 2003 | Report to the Coordinating Board | July 2004 |
| Initiate FY 2002 projects | June 2006 | PVAMU individual project file |  |
| Progress Report | December 2003 | Report to the Coordinating Board | January 2004 |
| Revalidate update project listing | May 2004 | PVAMU Master Plan projects list | May 2004 |
| Identify projects | June 2004 | PVAMU Master Plan projects list | June 2004 |
| Progress Report | June 2004 | Report to the Coordinating Board | July 2004 |
| Progress Report | December 2004 | Report to the Coordinating Board | December 2004 |
| Initiate FY 2002 projects | June 2006 | PVAMU individual project file |  |
| Revalidate update project listing | May 2005 | PVAMU Master Plan projects list | May 2005 |
| Progress Report | June 2005 | Report to the Coordinating Board | July 2005 |
| Component fully implemented | September 2005 | PVAMU Master Plan Completion Document | May 2006 |

# Plan Component: 9.1 Strengthen institutional development office.

| Designated Institution Staff: |  |
| --- | --- |
| Name | Dr. Willie Trotty |
| Title | Vice President for Research and Development |
| Address | Prairie View A&M University |
| Phone | 936-857-4494 |
| Fax | 936-857-2225 |
| E-mail | wftrotty@pvamu.edu |

| Designated Board Staff: |  |
| --- | --- |
| Name | Ms. Amanda Greene |
| Title | Budget and Policy Analyst, Planning and Accountability Division |
| Address | Texas Higher Education Coordinating Board |
| Phone | 512-427-6137 |
| Fax | 512-427-6147 |
| E-mail | amanda.greene@thecb.state.tx.us |

| Funding: | None Requested |
| --- | --- |
| Appropriated 2002 (millions) | $ 0.00 |
| Appropriated 2003 (millions) | $ 0.00 |
| Appropriated 2004 (millions) | $ 0.00 |
| Appropriated 2005 (millions) | $ 0.00 |
| Expended as of 8/31/05 | $ 0.00 |
| FY 04 Budget Reallocation | $ 0.00 |
| FY 05 Budget Reallocation | $ 0.00 |
| Appropriated 2006 (millions) | $ 0.00 |
| FY 06 Expended & Committed 6/30 | $ 0.00 |
| Available as of 6/30/06 | $ 0.00 |

Summary

Ketchum, Inc. continues to serve as the Institution’s Capital Campaign Council. Their contract was extended as of May 2006. The campaign is now in its public phase with heavy emphasis on gifts from alumni. The campaign cabinet continues to meet monthly to review results, chart the progress of the campaign and prepare for future campaign related events.  In support of the campaign, the university has sponsored two galas that attracted needed financial backing for scholarships and endowed chairs. The first gala, April 2005, recognized the contributions of Whitlow Green, a major contributor, and the University’s past presidents. The April 2006 Gala honored the university’s extensive military history, with emphasis on the nine general officers who were the products of the university’s Army and Navy ROTC programs.

At least two awareness gatherings are held per month with upwards of 30 people in attendance. As part of the Alumni Phase of the campaign, these gatherings are often held in the homes of the alumni. Additionally, campaign awareness activities continue to take place at national and local alumni meetings and with special audiences where the university president, Dr. George C. Wright, has been the keynote speaker.  Dr. Willie Trotty, Vice President for Research and Development, continues to include campaign awareness information in his presentations to corporations and others who partner with the university in its R&D efforts.

Monica Williams was hired as the director of development and in recognition of her expanded role in development and fund-raising; she received a promotion to Associate Vice President for Development.  Since coming to the University, she has helped define the role of college deans in our development activities and identified potential donors for individual colleges’ participation in the campaign.  Ms. Williams has also worked with Ketchum, Inc. to refine the list of potential donors and finalize all capital campaign related print materials. She plans visits and coordinates the follow-up activities of persons who attend the alumni gatherings.

In addition to an associate vice president for development, the Office of Development staff includes an associate director of development, a proposal writer and a prospect researcher.  Effective January 1, 2006, the Office of Alumni Relations was moved to the Office of Development.  This reorganization has helped enhance the current alumni phase of the capital campaign.

Pacesetter and major gifts have been identified and the solicitation process has been implemented.  To date, proposals have been submitted to nearly sixty (60) corporations, foundations and agencies resulting in the university securing nearly $17 million in gifts and pledges. The university now has funding for four endowed chairs (see plan component 10.1 for additional information).  Alumni and friends of the university who have made personal contributions to the campaign are now being encouraged to include Prairie View A&M University in their estate plans. Selected donors have been recognized for their gifts, thus encouraging others to give.

Implementation Schedule

| Task | Expected Completion Date | Outcome Documentation | Actual Completion Date |
| --- | --- | --- | --- |
| Evaluate future needs and opportunities for the Development Office | June 2001 | Development Office Strategic Plan incorporating these ideas | June 2001 |
| Proceed with plans for a Capital Campaign | July 2001 | Signed contract with campaign council including specific details of planned use of funds | December 2002 |
| Launch an Internal and External Public Relations Campaign | July 2001 | Public Relations Plan and Schedule of Related Activities | October 2002 |
| Solicitation of campaign leadership from Corporate Cluster, faculty and staff | August 2001 | Public notice naming campaign chair and leadership team | September 2003 |
| Hire additional development staff | September 2001 | Written justification for hiring individuals for Development Office | August 2003 |
| Research to identify 200-250 donor prospects and develop appropriate solicitation strategies | December 2001 | Database file identifying prospects and potential gifts including criteria used to identify these potential donors; appropriate solicitation strategies documented in memo format and approved by an appropriate University official | December 2003 |
| Progress Report | December 2001 | Report to the Coordinating Board | December 2001 |
| Progress Report | June 2002 | Report to the Coordinating Board | June 2002 |
| Progress Report | December 2002 | Report to the Coordinating Board | January 2003 |
| Expand and strengthen gift acceptance and acknowledgement | February 2003 | Letters used to acknowledge and thank donors for gifts | February 2003 |
| Progress Report | June 2003 | Report to the Coordinating Board | July 2003 |
| Establish a campaign and development budget | November 2003 | Details of the campaign documented and approved by an appropriate University official; approved University budget documents | December 2003 |
| Establish a Planned Giving Program | November 2003 | Announcement posted on the University website and in brochures and pamphlets | March 2004 |
| Progress Report | December 2003 | Report to the Coordinating Board | January 2004 |
| Progress Report | June 2004 | Report to the Coordinating Board | July 2004 |
| Progress Report | December 2004 | Report to the Coordinating Board | December 2004 |
| Progress Report | June 2005 | Report to the Coordinating Board | July 2005 |
| Continued Assessment of Effectiveness and use of data to strengthen the development function | August 2005 | Reports to the President, Development Council and Stakeholders | August 2005 |
| Progress Report | December 2005 | Report to the Coordinating Board | December 2005 |
| Progress Report | June 2006 | Report to the Coordinating Board | July 2006 |
| Continued Assessment of Effectiveness and use of data to strengthen the development function | August 2006 | Reports to the President, Development Council and Stakeholders |  |
| Progress Report | December 2006 | Report to the Coordinating Board |  |
| Progress Report | June 2007 | Report to the Coordinating Board |  |
| Continued Assessment of Effectiveness and use of data to strengthen the development function | August 2007 | Reports to the President, Development Council and Stakeholders |  |
| Component fully implemented | August 2007 | Office of Research and Development Annual Report |  |

# Plan Component: 10.1 Create 12 endowed chairs for new and existing programs.

| Designated Institution Staff: |  |
| --- | --- |
| Name | Dr. Joahanne Thomas-Smith |
| Title | Provost and Senior Vice President for Academic and Student Affairs |
| Address | Prairie View A&M University |
| Phone | 936-261-2174 |
| Fax | 936-261-2176 |
| E-mail | ejthomas-smith@pvamu.edu |

| Designated Board Staff: |  |
| --- | --- |
| Name | Ms. Amanda Greene |
| Title | Budget and Policy Analyst, Planning and Accountability Division |
| Address | Texas Higher Education Coordinating Board |
| Phone | 512-427-6137 |
| Fax | 512-427-6147 |
| E-mail | amanda.greene@thecb.state.tx.us |

| Funding: |  |
| --- | --- |
| Appropriated 2002 (millions) | $ 1.00 |
| Appropriated 2003 (millions) | $ 1.00 |
| Appropriated 2004 (millions) | $ 0.88 |
| Appropriated 2005 (millions) | $ 0.87 |
| Expended as of 8/31/05 | $ (3.53) |
| FY 04 Budget Reallocation | $ 0.00 |
| FY 05 Budget Reallocation | $ (0.22) |
| Appropriated 2006 (millions) | $ 0.53 |
| FY 06 Expended & Committed 6/30 | $ (053) |
| Available as of 6/30/06 | $ 0.00 |

Summary

As noted in the most recent progress report, establishing and filling the twelve (12) endowed chairs in the following broad array of disciplines remains a high priority for the university: computer science (1), electrical engineering (1), biology (1), business (2), architecture (1), juvenile justice (2), educational leadership (1), history/political science (1), and nursing (2).  The projected number of chairs in biology changed from two to one, and educational leadership was added as a discipline in which a chair would be established, now that a PhD is offered in that area.  The primary capital campaign strategy for attracting funding for the chairs has been that of seeking support from philanthropic agencies, foundations, federal entities and individuals.  As of spring 2006, funding has been acquired to provide the required match and thereby establish endowed chairs in four disciplines:  architecture (1), biology (1), educational leadership (1), and nursing (1). Proposal development teams led by the deans of the respective schools and colleges are vigorously seeking training in methods of pursuing financial support for additional endowed chairs.  It is anticipated that at least one and perhaps two of the additional chairs will be filled by the opening of the 2006-2007 academic year.

Implementation Schedule

| Task | Expected Completion Date | Outcome Documentation | Actual Completion Date |
| --- | --- | --- | --- |
| Evaluate needs for endowed chairs | September 2001 | Texas Commitment to Prairie View A&M University Strategic Plan | July 2001 |
| Progress Report | December 2001 | Report to the Coordinating Board | December 2001 |
| Progress Report | June 2002 | Report to the Coordinating Board | June 2002 |
| Proceed with plans for a Capital Campaign | July 2002 | Signed contract with campaign council including specific details of planned use of funds | December 2002 |
| Begin fund-raising | December 2002 | Endowed Chair Fund-Raising Plan and action plan for fund-raising activities | January 2005 |
| Progress Report | December 2002 | Report to the Coordinating Board | January 2003 |
| Progress Report | June 2003 | Report to the Coordinating Board | July 2003 |
| Identify funding for 4 Chairs | September 2003 | Capital Campaign budget specifically identifying funding sources | January 2005 |
| Endowed Chair recruitment | September 2003 | Four faculty members hired into endowed chairs positions |  |
| Progress Report | December 2003 | Report to the Coordinating Board | January 2004 |
| Progress Report | June 2004 | Report to the Coordinating Board | July 2004 |
| Progress Report | December 2004 | Report to the Coordinating Board | January 2005 |
| Progress Report | June 2005 | Report to the Coordinating Board | July 2005 |
| Identify funding for 4 Chairs | September 2005 | Capital Campaign budget specifically identifying funding sources |  |
| Endowed Chair recruitment | September 2005 | Four faculty members hired into endowed chairs positions |  |
| Progress Report | October 2005 | Report to the Coordinating Board | October 2005 |
| Progress Report | December 2005 | Report to the Coordinating Board | December 2005 |
| Progress Report | June 2006 | Report to the Coordinating Board | July 2006 |
| Progress Report | December 2006 | Report to the Coordinating Board |  |
| Progress Report | June 2007 | Report to the Coordinating Board |  |
| Identify funding for 4 Chairs | September 2007 | Capital Campaign budget specifically identifying funding sources |  |
| Component fully implemented | September 2007 | Four faculty members hired into endowed chairs positions |  |

# Plan Component: 11.1 Develop new PhD program in Juvenile Forensic Psychology.

| Designated Institution Staff: |  |
| --- | --- |
| Name | Dr. H.Elaine Rodney |
| Title | Dean, College of Juvenile Justice and Psychology |
| Address | Prairie View A&M University |
| Phone | 936-857-4938 |
| Fax | 936-857-4941 |
| E-mail | herodney@pvamu.edu |

| Designated Board Staff: |  |
| --- | --- |
| Name | Dr. Roger Alford |
| Title | Program Director, Universities and Health-Related Institutions Division |
| Address | Texas Higher Education Coordinating Board |
| Phone | 512-427-6216 |
| Fax | 512-427-6168 |
| E-mail | Roger.alford@thecb.state.tx.us |

| Funding: |  |
| --- | --- |
| Appropriated 2002 (millions) | $ 0.00 |
| Appropriated 2003 (millions) | $ 0.00 |
| Appropriated 2004 (millions) | $ 0.67 |
| Appropriated 2005 (millions) | $ 0.66 |
| Expended as of 8/31/05 | $ (0.39) |
| FY 04 Budget Reallocation | $ (0.14) |
| FY 05 Budget Reallocation | $ (0.17) |
| Appropriated 2006 (millions) | $ 0.64 |
| FY 06 Expended & Committed 6/30 | $ (0.50) |
| Available as of 6/30/06 | $ 0.77 |

Summary

The program admitted its first cohort of students in August 2004 and its second cohort in August 2005.  Twelve students are enrolled currently, with one on leave of absence. All students are making satisfactory progress.  Five will complete their course work this summer and are expected to take their comprehensive examinations this fall. Five students have been admitted for fall 2006.  Practicum training sites include:  Ben Taub Hospital, Fort Bend and Harris County Juvenile Probation Departments, the HISD, Sheldon Harbor Refuge Center and Touchstone Neuro Recovery Center. Faculty and students have attended the American Psychological Association Conference, Washington DC, August 2005; the Texas A&M University System Research Symposium in Corpus Christi, November 2005; the Strengthening Youth and Families Conference in Austin, November 2005; and the Southwest Psychological Association Conference in Austin, March 2006.  Ms. Nedra Francis placed 3rd as best graduate presenter at the latter conference.

Implementation Schedule

| Task | Expected Completion Date | Outcome Documentation | Actual Completion Date |
| --- | --- | --- | --- |
| Accept contractor proposals | November 2003 | Proposal received | October 2004 |
| Bidding and Negotiations | December 2003 | TAMUS F, P&C & PVAMU User Coordinator | November 2004 |
| Contract Administration | January 2004 | TAMUS F, P&C & PVAMU User Coordinator | November 2004 |
| Assign faculty to the program and assess faculty recruitment needs | September 2004 | Faculty Contracts | July 2003 |
| Prepare program proposal | October 2004 | Program proposal | February 2003 |
| Progress Report | June 2004 | Report to the Coordinating Board | July 2004 |
| Progress Report | December 2004 | Report to the Coordinating Board | December 2004 |
| Progress Report | June 2005 | Report to the Coordinating Board | June 2004 |
| Submit proposal to the University Graduate Council | September 2005 | Graduate Council approval | May 2003 |
| Progress Report | December 2005 | Report to the Coordinating Board | December 2003 |
| Prepare proposal for the Board of Regents | January 2006 | Board of Regents approval | September 2003 |
| Prepare proposal for the Coordinating Board | April 28, 2006 | Proposal submitted to the Coordinating Board | October 2003 |
| Progress Report | June 2006 | Report to the Coordinating Board | June 2004 |
| First Proposal Review | October 2006 | Out-of-State Reviewers Report | April 2004 |
| Progress Report | December 2006 | Report to the Coordinating Board | December 2004 |
| Second Proposal Review by the Coordinating Board | January 2007 | Coordinating Board approval | April 2004 |
| Progress Report | June 2007 | Report to the Coordinating Board | June 2004 |
| Prepare substantive change request for SACS | July 2007 | SACS approval | May 2004 |
| Progress Report | December 2007 | Report to the Coordinating Board | April 2003 |
| Faculty Recruitment | June 2008 | Faculty numbers and credentials are appropriate for the needs of the program | February 2004 |
| Progress Report | June 2008 | Report to the Coordinating Board | June 2004 |
| Accept first students into the program | September 2008 | Student registration information | August 2004 |
| Progress Report | December 2008 | Report to the Coordinating Board | December 2004 |
| Progress Report | June 2009 | Report to the Coordinating Board | June 2005 |
| Progress Report | December 2009 | Report to the Coordinating Board | December 2005 |
| Progress Report | June 2010 | Report to the Coordinating Board | June 2006 |
| Program Evaluation | September 2010 | Student retention and success rates | June 2006 |
| Progress Report | October 2010 | Report to the Coordinating Board |  |
| Progress Report | December 2010 | Report to the Coordinating Board |  |
| Progress Report | June 2011 | Report to the Coordinating Board |  |
| Progress Report | December 2011 | Report to the Coordinating Board |  |
| Progress Report | June 2012 | Report to the Coordinating Board |  |
| Program Evaluation | September 2012 | Student graduation and success rates |  |
| Component fully implemented | September 2012 | Program supported through formula funding |  |

# Plan Component: 11.2 New building for juvenile justice-related programs.

| Designated Institution Staff: |  |
| --- | --- |
| Name | Mr. Larry Raab |
| Title | Director for Facilities Planning, Construction and Special Projects |
| Address | Prairie View A&M University |
| Phone | 936-261-1750 |
| Fax | 936-857-2350 |
| E-mail | llraab@pvamu.edu |

| Designated Board Staff: |  |
| --- | --- |
| Name | Ms. Lillian Wanjagi |
| Title | Program Director, Resource Planning |
| Address | Texas Higher Education Coordinating Board |
| Phone | 512-427-6125 |
| Fax | 512-427-6147 |
| E-mail | lillian.wanjagi@thecb.state.tx.us |

| Funding: |  |
| --- | --- |
| TRB (millions) | $ 16.00 |
| Expended and committed as of 3/31/06 | $ (8.49) |

Summary

Construction of the new Juvenile Justice Building is nearly complete. Substantial construction should be completed by July 2006. Furniture will begin to be moved into the building in early July 2006, and the College of Juvenile Justice and Psychology will begin moving their faculty and staff into the new building during the first week of August 2006. Fall 2006 classes will be held in the new building.

second floor slab.  Construction is proceeding ahead of schedule, with final completion scheduled for June 2006, pending any weather days that may be added to the contract time.  Occupancy could occur as early as July 2006.

.  Since that time, they have mobilized onto the site, and have poured structural concrete up to and including the second floor slab.  Construction is proceeding ahead of schedule, with final completion scheduled for June 2006, pending any weather days that may be added to the contract time.  Occupancy could occur as early as July 2006.

Implementation Schedule

| Task | Expected Completion Date | Outcome Documentation | Actual Completion Date |
| --- | --- | --- | --- |
| Project Initiation | July 2002 | Form C-1 (PVAMU) | July 2002 |
| Needs Assessment | August 2002 | Preliminary Program of Requirements | August 2002 |
| Send preliminary Program of Requirements to short list of Architect/Engineer Firms | September 2002 | Letters to Architect/Engineer Firms | September 2002 |
| Architect/Engineer Selection | November 2002 | TAMUS F, P&C & PVAMU User Coordinator Form C-31 | November 2002 |
| Program of Requirements | November 2002 | TAMUS F, P &C & PVAMU College of Nursing User Coordinator | November 2002 |
| Negotiate Architect/Engineer Contract | December 2002 | Architect/Engineer Contract | December 2002 |
| Progress Report | December 2002 | Report to the Coordinating Board | January 2003 |
| Initiate Concept Design | January 2003 | Architectural Drawings | February 2003 |
| Approve Concept Design | May 2003 | Letter of Approval | April 2003 |
| Authorize Construction Documents Preparation | May 2003 | Letter of Authorization | September 2003 |
| Progress Report | June 2003 | Report to the Coordinating Board | July 2003 |
| Construction Documents | September 2003 | Architectural & MEP Drawings | June 2004 |
| Accept contractor proposals | November 2003 | Proposals received | October 2004 |
| Bidding and Negotiations | December 2003 | TAMUS F, P&C & PVAMU User Coordinator | November 2004 |
| Progress Report | December 2003 | Report to the Coordinating Board | January 2004 |
| Contract Administration | January 2004 | TAMUS F, P&C & PVAMU User Coordinator | November 2004 |
| Construction Commencement | February 2004 | TAMUS F, P&C & PVAMU User Coordinator | February 2005 |
| Progress Report | June 2004 | Report to the Coordinating Board | July 2004 |
| Progress Report | December 2004 | Report to the Coordinating Board | December 2004 |
| Progress Report | June 2005 | Report to the Coordinating Board | July 2005 |
| Construction Complete | September 2005 | TAMUS Form 111300 | July 2006 |
| Install Movable Furnishings | October 2005 | Furnishings installed | July 2006 |
| Beneficial Occupancy | November 2005 | TAMUS Form C-13A | August 2006 |

# Plan Component: 12.1 Develop new PhD in Educational Leadership.

| Designated Institution Staff: |  |
| --- | --- |
| Name | Dr. Paul Mehta |
| Title | Dean, College of Education |
| Address | Prairie View A&M University |
| Phone | 936-857-2918 |
| Fax | 936-857-2911 |
| E-mail | mpmehta@pvamu.edu |

| Designated Board Staff: |  |
| --- | --- |
| Name | Dr. Roger Alford |
| Title | Program Director, Universities and Health-Related Institutions Division |
| Address | Texas Higher Education Coordinating Board |
| Phone | 512-427-6216 |
| Fax | 512-427-6168 |
| E-mail | Roger.alford@thecb.state.tx.us |

| Funding: |  |
| --- | --- |
| Appropriated 2002 (millions) | $ 0.60 |
| Appropriated 2003 (millions) | $ 0.60 |
| Appropriated 2004 (millions) | $ 0.00 |
| Appropriated 2005 (millions) | $ 0.00 |
| Expended as of 8/31/05 | $ (1.03) |
| FY 04 Budget Reallocation | $ 0.00 |
| FY 05 Budget Reallocation | $ 0.00 |
| Appropriated 2006 (millions) | $ 0.00 |
| FY 06 Expended & Committed 6/30 | $ (0.16) |
| Available as of 6/30/06 | 0.01 |

Summary

The PhD program in Educational Leadership has now been fully implemented.  The third cohort of students, consisting of 24 students, has commenced their program of study beginning May 30, 2006.  All students from the first and second cohorts have published articles in refereed scholarly journals.  The award of the first PhD degree is expected to be granted as early as December 2006.

Implementation Schedule

| Task | Expected Completion Date | Outcome Documentation | Actual Completion Date |
| --- | --- | --- | --- |
| Assign faculty to the program and assess faculty recruitment needs | July 2001 | Faculty Contracts | August 2001 |
| Prepare program proposal | August 2001 | Program proposal (Draft proposal sent to CB) | September 2001 |
| Submit proposal to the University Graduate Council | September 2001 | Graduate Council approval | September 2001 |
| Prepare proposal for the Board of Regents | November 2001 | Board of Regents approval | December 2001 |
| Prepare proposal for the Coordinating Board | December 2001 | Final Proposal submitted to the Coordinating Board | December 2001 |
| Progress Report | December 2001 | Report to the Coordinating Board | December 2001 |
| First Proposal Review | May 2002 | Out-of-State Reviewers Report | May 2002 |
| Progress Report | June 2002 | Report to the Coordinating Board | July 2002 |
| First Reading at CB | July 2002 | Initial Approval of program | July 2002 |
| Second Proposal Review by the Coordinating Board | October 2002 | Final Coordinating Board approval | January 2003 |
| Prepare substantive change request for SACS | December 2002 | SACS approval | May 2004 |
| Faculty Recruitment | December 2002 | Faculty numbers and credentials are appropriate for the needs of the program | August 2004 |
| Progress Report | December 2002 | Report to the Coordinating Board | January 2003 |
| Accept first students into the program | January 2003 | Student registration information | August 2004 |
| Progress Report | June 2003 | Report to the Coordinating Board | July 2003 |
| Progress Report | December 2003 | Report to the Coordinating Board | January 2004 |
| Progress Report | June 2004 | Report to the Coordinating Board | July 2004 |
| Program Evaluation | September 2004 | Panel of Evaluators Report | September 2004 |
| Progress Report | December 2004 | Report to the Coordinating Board | December 2004 |
| Progress Report | June 2005 | Report to the Coordinating Board | June 2005 |
| Progress Report | December 2005 | Report to the Coordinating Board | December 2005 |
| Progress Report | June 2006 | Report to the Coordinating Board |  |
| Program Evaluation | September 2006 | Student graduation and success rates |  |
| Component fully implemented | September 2006 | Program supported through formula funding |  |
| Component fully implemented | June 2006 | All OCR funds will be expended by August 31, 2006 | June 2006 |

# Plan Component: 12.2 Develop new MS in Computer Science.

| Designated Institution Staff: |  |
| --- | --- |
| Name | Dr. Milton R. Bryant |
| Title | Dean, College of Engineering |
| Address | Prairie View A&M University |
| Phone | 936-857-2211 |
| Fax | 936-857-2222 |
| E-mail | mrbryant@pvamu.edu |

| Designated Board Staff: |  |
| --- | --- |
| Name | Dr. Roger Alford |
| Title | Program Director, Universities and Health-Related Institutions Division |
| Address | Texas Higher Education Coordinating Board |
| Phone | 512-427-6216 |
| Fax | 512-427-6168 |
| E-mail | Roger.alford@thecb.state.tx.us |

| Funding: |  |
| --- | --- |
| Appropriated 2002 (millions) | $ 0.40 |
| Appropriated 2003 (millions) | $ 0.40 |
| Appropriated 2004 (millions) | $ 0.35 |
| Appropriated 2005 (millions) | $ 0.35 |
| Expended as of 8/31/05 | $ (0.98) |
| FY 04 Budget Reallocation | $ (0.12) |
| FY 05 Budget Reallocation | $ (0.09) |
| Appropriated 2006 (millions) | $ 0.32 |
| FY 06 Expended & Committed 6/30 | $ (0.06) |
| Available as of 6/30/06 | $ 0.57 |

Summary

Nine graduate students are enrolled currently in the MS in Computer Science program.  From summer 2005 to spring 2006, four students graduated with an MS in Computer Science. Two additional students are scheduled to graduate in summer 2006.  The student retention rate since 2002 has been over 90%.  Of the four graduates, one has applied for entrance to a PhD program, two are employed in the industry, and one is self-employed.  Some of the current projects/theses are in the process of being published.  One graduate student actively participated in research grants in the department.  In the spring 2006 semester, five assistantships / scholarships were offered for conducting research and teaching computer science service courses under the supervision of faculty members.  One graduate course was offered via distance learning in spring 2006.

Focusing on the next six months, the college plans to recruit more graduate students, maintain the laboratory facilities, continue expanding use of the distance learning facilities, and offer more web based and evening courses.

Implementation Schedule

| Task | Expected Completion Date | Outcome Documentation | Actual Completion Date |
| --- | --- | --- | --- |
| Assign faculty to the program and assess faculty recruitment needs | August 2001 | Faculty Contracts | June 2001 |
| Prepare program proposal | November 2001 | Program proposal (Draft proposal sent to CB) | July 2001 |
| Submit proposal to the University Graduate Council | December 2001 | Graduate Council approval | July 2001 |
| Progress Report | December 2001 | Report to the Coordinating Board | December 2001 |
| Prepare proposal for the Board of Regents | January 2002 | Board of Regents approval | October 2001 |
| Prepare proposal for the Coordinating Board | April 2002 | Coordinating Board approval | April 2002 |
| Progress Report | June 2002 | Report to the Coordinating Board | June 2002 |
| Faculty Recruitment | August 2002 | Faculty numbers and credentials are appropriate for the needs of the program | June 2002 |
| Accept first students into the program | September 2002 | Student registration information | September 2002 |
| Progress Report | December 2002 | Report to the Coordinating Board | January 2003 |
| Progress Report | June 2003 | Report to the Coordinating Board | July 2003 |
| Progress Report | December 2003 | Report to the Coordinating Board | January 2004 |
| Progress Report | June 2004 | Report to the Coordinating Board | July 2004 |
| Program Evaluation | October 2004 | Student retention and success rates | October 2004 |
| Progress Report | December 2004 | Report to the Coordinating Board | January 2005 |
| Progress Report | June 2005 | Report to the Coordinating Board | July 2005 |
| Progress Report | December 2005 | Report to the Coordinating Board | December 2005 |
| Progress Report | June 2006 | Report to the Coordinating Board | June 2006 |
| Progress Report | December 2006 | Report to the Coordinating Board |  |
| Progress Report | June 2007 | Report to the Coordinating Board |  |
| Progress Report | December 2007 | Report to the Coordinating Board |  |
| Progress Report | June 2008 | Report to the Coordinating Board |  |
| Program Evaluation | September 2008 | Student graduation and success rates |  |
| Component fully implemented | September 2008 | Program supported through formula funding |  |

# Plan Component: 12.3 Develop new MS in Information Systems.

| Designated Institution Staff: |  |
| --- | --- |
| Name | Dr. Milton R. Bryant |
| Title | Dean, College of Engineering |
| Address | Prairie View A&M University |
| Phone | 936-857-2211 |
| Fax | 936-857-2222 |
| E-mail | mrbryant@pvamu.edu |

| Designated Board Staff: |  |
| --- | --- |
| Name | Dr. Roger Alford |
| Title | Program Director, Universities and Health-Related Institutions Division |
| Address | Texas Higher Education Coordinating Board |
| Phone | 512-427-6216 |
| Fax | 512-427-6168 |
| E-mail | Roger.alford@thecb.state.tx.us |

| Funding: |  |
| --- | --- |
| Appropriated 2002 (millions) | $ 0.70 |
| Appropriated 2003 (millions) | $ 0.70 |
| Appropriated 2004 (millions) | $ 0.61 |
| Appropriated 2005 (millions) | $ 0.07 |
| Expended as of 8/31/05 | $ (1.89) |
| FY 04 Budget Reallocation | $ (0.17) |
| FY 05 Budget Reallocation | $ (0.02) |
| Appropriated 2006 (millions) | $ 0.53 |
| FY 06 Expended & Committed 6/30 | $ (0.47) |
| Available as of 6/30/06 | $ 0.06 |

Summary

Thirteen graduate students are enrolled currently in the Information Systems MS program. From summer 2005 to spring 2006, one student graduated with an MS in Computer Information Systems (another student completed all requirements except the project and did not graduate). Two additional students are expected to graduate in summer 2006.  Over the last year, one student transferred out of the program (retention rate of over 90%).  The historic retention rate since 2002 has been over 90%.  The graduating student is employed in the industry. The two students expected to graduate in summer have admissions into PhD programs.  In spring 2006, two students were conducting research and teaching computer science service courses under the supervision of faculty members.  One graduate course was offered via distance learning in spring 2006.

Focusing on the next six months, the college plans to recruit more graduate students, maintain the laboratory facilities, continue expanding use of the distance learning facilities, and offer more web based and evening courses.

Implementation Schedule

| Task | Expected Completion Date | Outcome Documentation | Actual Completion Date |
| --- | --- | --- | --- |
| Assign faculty to the program and assess faculty recruitment needs | August 2001 | Faculty Contracts | June 2001 |
| Prepare program proposal | November 2001 | Program proposal (Draft proposal sent to CB) | July 2001 |
| Submit proposal to the University Graduate Council | December 2001 | Graduate Council approval | July 2001 |
| Progress Report | December 2001 | Report to the Coordinating Board | December 2001 |
| Prepare proposal for the Board of Regents | January 2002 | Board of Regents approval | October 2001 |
| Prepare proposal for the Coordinating Board | April 2002 | Coordinating Board approval | April 2002 |
| Progress Report | June 2002 | Report to the Coordinating Board | June 2002 |
| Faculty Recruitment | August 2002 | Faculty numbers and credentials are appropriate for the needs of the program | June 2002 |
| Accept first students into the program | September 2002 | Student registration information | September 2002 |
| Progress Report | December 2002 | Report to the Coordinating Board | January 2003 |
| Progress Report | June 2003 | Report to the Coordinating Board | July 2003 |
| Progress Report | December 2003 | Report to the Coordinating Board | January 2004 |
| Progress Report | June 2004 | Report to the Coordinating Board | July 2004 |
| Progress Report | December 2004 | Report to the Coordinating Board | January 2005 |
| Progress Report | June 2005 | Report to the Coordinating Board | July 2005 |
| Program Evaluation | October 2005 | Student retention and success rates (Achievements report) | February 2006 |
| Progress Report | December 2005 | Report to the Coordinating Board | December 2005 |
| Progress Report | June 2006 | Report to the Coordinating Board | June 2006 |
| Progress Report | December 2006 | Report to the Coordinating Board |  |
| Progress Report | June 2007 | Report to the Coordinating Board |  |
| Program Evaluation | July 2007 | Student graduation and success rates |  |
| Progress Report | December 2007 | Report to the Coordinating Board |  |
| Progress Report | June 2008 | Report to the Coordinating Board |  |
| Component fully implemented | September 2008 | Program supported through formula funding |  |

# Plan Component: 13.1 Delete language in the statutory mission Texas Education Code, Section 87.104.

| Designated Institution Staff: |  |
| --- | --- |
| Name | Mr. Frank Jackson |
| Title | Governmental Relations Officer |
| Address | Prairie View A&M University |
| Phone | 936-857-4298 |
| Fax | 936-857-2598 |
| E-mail | fdjackson@pvamu.edu |

| Designated Board Staff: |  |
| --- | --- |
| Name | Dr. Roger Alford |
| Title | Program Director, Universities and Health-Related Institutions Division |
| Address | Texas Higher Education Coordinating Board |
| Phone | 512-427-6216 |
| Fax | 512-427-6168 |
| E-mail | Roger.alfordl@thecb.state.tx.us |

| Funding: | None Requested |
| --- | --- |
| Appropriated (millions) | $ 0.00 |
| Expended as of12/31/04 | $ 0.00 |
| Committed as of 12/31/04 | $ 0.00 |
| Committed as of 6/30/05 | $ 0.00 |

Summary

Exclusionary and race-specific language has been removed via legislation from the statutory mission statement of Prairie View A&M University.  Task completed.

Implementation Schedule

| Task | Expected Completion Date | Outcome Documentation | Actual Completion Date |
| --- | --- | --- | --- |
| Work with legislature to amend legislation | June 2001 | Legislation enacted | June 2001 |
| Component fully implemented | June 2001 | Amended mission in place | June 2001 |

# Plan Component: 13.2 Delete race specific or exclusionary language in the institutional mission statement.

| Designated Institution Staff: |  |
| --- | --- |
| Name | Mr. Frank Jackson |
| Title | Governmental Relations Officer |
| Address | Prairie View A&M University |
| Phone | 936-857-4298 |
| Fax | 936-857-2598 |
| E-mail | fdjackson@pvamu.edu |

| Designated Board Staff: |  |
| --- | --- |
| Name | Dr. Roger Alford |
| Title | Program Director, Universities and Health-Related Institutions Division |
| Address | Texas Higher Education Coordinating Board |
| Phone | 512-427-6216 |
| Fax | 512-427-6168 |
| E-mail | Roger.alfordl@thecb.state.tx.us |

| Funding: | None Requested |
| --- | --- |
| Appropriated 2004 (millions) | $ 0.00 |
| Expended as of 12/31/04 | $ 0.00 |
| Committed as of 12/31/04 | $ 0.00 |
| Committed as of 6/30/05 | $ 0.00 |

Summary

A proposal to delete race-specific and exclusionary language from the institutional mission statement of Prairie View A&M University has been approved by the Texas A&M University System Board of Regents.  The proposal was approved at the July 2002 meeting of the Texas Higher Education Coordinating Board.  The institution’s mission has now been changed as prescribed in the Priority Plan.  Task completed.

Implementation Schedule

| Task | Expected Completion Date | Outcome Documentation | Actual Completion Date |
| --- | --- | --- | --- |
| Craft new mission language | June 2001 | New institutional mission | June 2001 |
| Prepare proposal for the Board of Regents | August 2001 | Board of Regents approval | December 2001 |
| Component fully implemented | October 2001 | Coordinating Board approval | July 2002 |

# Additional Plan Components Funded by the Texas State Legislature

## Plan Component: 14.1 Develop new MS in Accounting.

| Designated Institution Staff: |  |
| --- | --- |
| Name | Dr. Munir Quddus |
| Title | Dean, College of Business |
| Address | Prairie View A&M University |
| Phone | 936-857-4310 |
| Fax | 936-857-2797 |
| E-mail | muquddus@pvamu.edu |

| Designated Board Staff: |  |
| --- | --- |
| Name | Dr. Roger Alford |
| Title | Program Director, Universities and Health-Related Institutions Division |
| Address | Texas Higher Education Coordinating Board |
| Phone | 512-427-6216 |
| Fax | 512-427-6168 |
| E-mail | Roger.alford@thecb.state.tx.us |

| Funding: |  |
| --- | --- |
| Appropriated 2002 (millions) | $ 0.00 |
| Appropriated 2003 (millions) | $ 0.30 |
| Appropriated 2004 (millions) | $ 0.26 |
| Appropriated 2005 (millions) | $ 0.26 |
| Expended as of 8/31/05 | $ (0.68) |
| FY 04 Budget Reallocation | $ (0.05) |
| FY 05 Budget Reallocation | $ (0.07) |
| Appropriated 2006 (millions) | $ 0.24 |
| FY 06 Expended & Committed 6/30 | $ (0.22) |
| Available as of 6/30/06 | $ 0.04 |

#### Summary

By June 2006, the eight students have graduated from this program.  Dr. Brian Lee, Coordinator of the MSA Program, has moved aggressively to increase the program’s enrollment.  He was also hired during regular semesters and in summer to assist the Director of Graduate Programs in Business in recruiting and retaining students in the MSA program.  His charge is to grow the program to at least 30 students by fall 2007.  A new staff (Recruitment and Placement Officer) position has been advertised and is being funded from an increase in designated tuition. Accounting faculty members are also working with the Texas CPA Society to strengthen the program. ACCT 5163 (Law and Ethics in Accounting) has been approved by the Texas CPA  unit for the program. A strategic planning document on this program was submitted in December 2005 by Dean Quddus to President Wright and Provost Thomas-Smith. Mrs. Mary Lee Hodge, a former Associate Dean of Business and the Vice President for Business Affairs, also has provided feedback on this document.

Implementation Schedule

| Task | Expected Completion Date | Outcome Documentation | Actual Completion Date |
| --- | --- | --- | --- |
| Prepare program proposal | November 2002 | Program proposal (Draft Proposal to CB) | November 2002 |
| Submit proposal to the University Graduate Council | December 2002 | Graduate Council approval | February 2003 |
| Progress Report | December 2002 | Report to the Coordinating Board | January 2003 |
| Prepare proposal for the Board of Regents | January 2003 | Board of Regents approval | March 2003 |
| Progress Report | June 2003 | Report to the Coordinating Board | July 2003 |
| Faculty Recruitment | August 2003 | Faculty numbers and credentials are appropriate for the needs of the program | August 2003 |
| Progress Report | December 2003 |  | January 2004 |
| Accept first students into the program | June 2004 | Student registration information | August 2003 |
| Progress Report | June 2004 | Report to the Coordinating Board | June 2004 |
| Progress Report | December 2004 | Report to the Coordinating Board | December 2004 |
| Progress Report | June 2005 | Report to the Coordinating Board | June 2005 |
| Progress Report | December 2005 | Report to the Coordinating Board | January 2006 |
| Progress Report | June 2006 | Report to the Coordinating Board | June 16, 2006 |
| Program Evaluation | October 2006 | Student retention and success rates |  |
| Progress Report | December 2006 | Report to the Coordinating Board |  |
| Progress Report | June 2007 | Report to the Coordinating Board |  |
| Progress Report | December 2007 | Report to the Coordinating Board |  |
| Progress Report | June 2008 | Report to the Coordinating Board |  |
| Program Evaluation | July 2008 | Student graduation and success rates |  |
| Progress Report | December 2008 | Report to the Coordinating Board |  |
| Progress Report | June 2009 | Report to the Coordinating Board |  |
| Progress Report | December 2009 | Report to the Coordinating Board |  |
| Progress Report | June 2010 | Report to the Coordinating Board |  |
| Component fully implemented | September 2010 | Program supported through formula funding |  |

## Plan Component: 14.2 Develop new MS in Community Development.

| Designated Institution Staff: |  |
| --- | --- |
| Name | Dr. Ikhlas Sabouni |
| Title | Dean, School of Architecture |
| Address | Prairie View A&M University |
| Phone | 936-261-9810 |
| Fax | 936-261-9826 |
| E-mail | isabouni@pvamu.edu |

| Designated Board Staff: |  |
| --- | --- |
| Name | Dr. Roger Alford |
| Title | Program Director, Universities and Health-Related Institutions Division |
| Address | Texas Higher Education Coordinating Board |
| Phone | 512-427-6216 |
| Fax | 512-427-6168 |
| E-mail | Roger.alford@thecb.state.tx.us |

| Funding: |  |
| --- | --- |
| Appropriated 2002 (millions) | $ 0.40 |
| Appropriated 2003 (millions) | $ 0.40 |
| Appropriated 2004 (millions) | $ 0.00 |
| Appropriated 2005 (millions) | $ 0.00 |
| Expended as of 8/31/05 | $ (0.80) |
| FY 04 Budget Reallocation | $ 0.00 |
| FY 05 Budget Reallocation | $ 0.00 |
| Appropriated 2006 (millions) | $ 0.00 |
| FY 06 Expended & Committed 6/30 | 0.00 |
| Available as of 6/30/06 | 0.00 |

Summary

Enrollment in the Community Development program has leveled out at the sixty-seventy student range. Based on the size of the current faculty teaching in this program, this enrollment ceiling is appropriate to continue to offer a high quality program. The Community Development program and its students and graduates have made a significant early impact in promoting and developing the community development profession. For example, the students and faculty have been instrumental in developing collaborative partnerships between the University and its surrounding communities. This year alone, students’ research projects and community development projects have assisted area communities to attract developers and investors to create economic development in the surrounding communities. In addition, as a means to develop professionally, community development students have established two student organizations (Association of Fundraising Professionals and Community Development Graduate Students Association) to enhance their professional development. Because of this program’s interdisciplinary approach, students have conducted studies that address social, economic and physical needs of communities. Due to the challenges faced by numerous communities in meeting these needs, the Community Development program is enhancing its community involvement by conducting community research symposiums that will address both international community development and small town and rural community developments. It is our intent to also develop an international community development component in the school that will support the development of a doctoral program in community development by 2008.

Masters of Community Development Degree - Program is in its fifth year as of 05-06

| CATEGORY | YEAR 5 05 - 06 |
| --- | --- |
| Total Projected Enrollment, in Proposal | 20 |
| Total Enrolled Students, Spring 2006 | 69 * |
| Graduates, Fall 2005 & Spring 2006 | 25 |

* Exceeded projections

Implementation Schedule

| Task | Expected Completion Date | Outcome Documentation | Actual Completion Date |
| --- | --- | --- | --- |
| Prepare program proposal | November 2002 | Program proposal (Draft proposal to CB) | April 2001 |
| Submit proposal to the University Graduate Council | December 2002 | Graduate Council approval | May 2001 |
| Progress Report | December 2002 | Report to the Coordinating Board | January 2003 |
| Prepare proposal for the Board of Regents | January 2003 | Board of Regents approval | July 2001 |
| Prepare proposal for the Coordinating Board | April 2003 | Coordinating Board approval | September 2001 |
| Progress Report | June 2003 | Report to the Coordinating Board | July 2003 |
| Faculty Recruitment | August 2003 | Faculty numbers and credentials are appropriate for the needs of the program | August 2001 |
| Progress Report | December 2003 | Report to the Coordinating Board | January 2004 |
| Accept first students into the program | June 2004 | Student registration information | September 2001 |
| Progress Report | June 2004 | Report to the Coordinating Board | July 2004 |
| Progress Report | December 2004 | Report to the Coordinating Board | December 2004 |
| Progress Report | June 2005 | Report to the Coordinating Board | July 2005 |
| Progress Report | December 2005 | Report to the Coordinating Board | December 2005 |
| Progress Report | June 2006 | Report to the Coordinating Board | June 2006 |
| Progress Report | October 2006 | Report to the Coordinating Board |  |
| Progress Report | December 2006 | Report to the Coordinating Board |  |
| Progress Report | June 2007 | Report to the Coordinating Board |  |
| Progress Report | December 2007 | Report to the Coordinating Board |  |
| Progress Report | June 2008 | Report to the Coordinating Board |  |
| Program Evaluation | July 2008 | Student graduation and success rates |  |
| Progress Report | December 2008 | Report to the Coordinating Board |  |
| Progress Report | June 2009 | Report to the Coordinating Board |  |
| Progress Report | December 2009 | Report to the Coordinating Board |  |
| Progress Report | June 2010 | Report to the Coordinating Board |  |
| Component fully implemented | September 2010 | Program supported through formula funding |  |

## Plan Component: 14.3 Create the Community and Urban Rural Enhancement Studies (CURES) Center.

| Designated Institution Staff: |  |
| --- | --- |
| Name | Dr. Ikhlas Sabouni |
| Title | Dean, School of Architecture |
| Address | Prairie View A&M University |
| Phone | 936-261-9810 |
| Fax | 936-261-9826 |
| E-mail | isabouni@pvamu.edu |

| Designated Board Staff: |  |
| --- | --- |
| Name | Ms. Natalie Coffey |
| Title | Program Director, Participation and Success |
| Address | Texas Higher Education Coordinating Board |
| Phone | 512-427-6227 |
| Fax | 512-427-6522 |
| E-mail | Natalie.Coffey@thecb.state.tx.us |

| Funding: |  |
| --- | --- |
| Appropriated 2002 (millions) | $ 0.20 |
| Appropriated 2003 (millions) | $ 0.20 |
| Appropriated 2004 (millions) | $ 0.00 |
| Appropriated 2005 (millions) | $ 0.00 |
| Expended as of 8/31/05 | $ (0.19) |
| FY 04 Budget Reallocation | $ 0.00 |
| FY 05 Budget Reallocation | $ 0.00 |
| Appropriated 2006 (millions) | $ 0.00 |
| FY 06 Expended & Committed 6/30 | $ (0.04) |
| Available as of 6/30/06 | 0.17 |

Summary

The Community Urban and Rural Enhancement Service Center (CURES) continues its active role in completing the application for the historical Marker for Dr. James Lee Dickey’s personal residence (the first African American medical doctor in Taylor), Williamson County, Texas.  The Center is awaiting collaboration with area community preservation associations.   In the last six months, the Center provided the completion of an application to the Historical Commission of Texas for a grant to support the Mary Ellen seminary project in Crockett Texas.  The Municipal Radio Station has included a feature on the RBH Yates Museum, on “Volunteer Journal' Ch. 16”. It will air in June each Tuesday and Thursday at 7am, 1pm, 7pm, and 1am. The program also features Mr. Cody Akadie, an architecture student working with the Center, discussing the architecture program and the work performed with the Museum on behalf of the CURES Center.  The Director attended the Association of Collegiate Schools of Architecture teaching seminar on preservation.  The symposium titled exploring preservation in architectural education was held at Cranbrook Academy of Art in Bloomfield Hills, Michigan.  Over the next six months the Center will continue to work in collaboration with the Yates Museum and will continue the documentation of historic structures and landscape of freedmen's town in Houston, Texas.  In addition, the Center will be constructing a three-dimensional model of the entire community of Freedmen Town in Houston, Texas.  This model will illustrate the locale before development. This project is also to be used to support the density survey of the area’s current development vs. 1870 to 1900 historic district urban design; and green space vs. covered & changes in population demographics.

Implementation Schedule

| Task | Expected Completion Date | Outcome Documentation | Actual Completion Date |
| --- | --- | --- | --- |
| Evaluate current and future needs and opportunities for community outreach | October 2001 | Texas Commitment to Prairie View A&M University Strategic Plan | July 2001 |
| Acquire equipment and hire consultants | December 2001 | Equipment is in place and consultants are working on identified projects | December 2001 |
| Progress Report | December 2001 | Report to the Coordinating Board | December 2001 |
| Faculty Recruitment | March 2002 | Faculty numbers and credentials are appropriate for the needs of CURES | March 2002 |
| Staff Recruitment | March 2002 | Staff numbers and credentials are appropriate for the needs of CURES | March 2002 |
| Progress Report | June 2002 | Report to the Coordinating Board | June 2002 |
| Component fully implemented | September 2002 | Texas Commitment to Prairie View A&M University Strategic Plan with accomplishments identified | January 2003 |

## Plan Component: 14.4 Faculty recruitment, retention and development.

| Designated Institution Staff: |  |
| --- | --- |
| Name | Dr. Joahanne Thomas-Smith |
| Title | Provost and Senior Vice President for Academic and Student Affairs |
| Address | Prairie View A&M University |
| Phone | 936-261-2174 |
| Fax | 936-261-2176 |
| E-mail | ejthomas-smith@pvamu.edu |

| Designated Board Staff: |  |
| --- | --- |
| Name | Ms. Natalie Coffey |
| Title | Program Director, Participation and Success |
| Address | Texas Higher Education Coordinating Board |
| Phone | 512-427-6227 |
| Fax | 512-427-6522 |
| E-mail | Natalie.Coffey@thecb.state.tx.us |

| Funding: |  |
| --- | --- |
| Appropriated 2002 (millions) | $ 1.50 |
| Appropriated 2003 (millions) | $ 1.50 |
| Appropriated 2004 (millions) | $ 1.31 |
| Appropriated 2005 (millions) | $ 1.31 |
| Expended as of 8/31/05 | $ (4.41) |
| FY 04 Budget Reallocation | $ (1.05) |
| FY 05 Budget Reallocation | $ 0.00 |
| Appropriated 2006 (millions) | $ 0.85 |
| FY 06 Expended & Committed 6/30 | $ (0.93) |
| Available as of 6/30/06 | 0.08 |

Summary

Improvements in the quality of the faculty is evidenced by the notable acceleration of productivity in research, scholarly and creative endeavors.  Additionally, classroom based instruction has yielded significant improvements in licensure rates, especially in Nursing.  The faculty sabbatical leave program has been activated and workshops and seminars on improving teaching have been offered with greater frequency than in prior years.  During the upcoming quarter a minimum of four faculty who have achieved ABD status will be supported in completing the terminal degree. Responding to changes in market forces, funds have been expended to retain faculty who are receiving more competitive salary offers from other universities.

#### Implementation Schedule

| Task | Expected Completion Date | Outcome Documentation | Actual Completion Date |
| --- | --- | --- | --- |
| Determine faculty recruitment priorities | September 2001 | Faculty recruitment plan | September 2001 |
| Create instruments for evaluation of faculty development needs | November 2001 | Faculty assessment instruments | September 2001 |
| Create faculty merit pay evaluation instruments | December 2001 | Faculty merit pay evaluation instruments | September 2001 |
| Progress Report | December 2001 | Report to the Coordinating Board | December 2001 |
| Initiate searches for faculty in all areas identified | February 2002 | General advertisement for faculty positions in the Chronicle for Higher Education | March 2001 |
| Carry out faculty assessment for development needs | March 2002 | Completed faculty assessment forms | December 2001 |
| Carry out faculty merit pay evaluations | April 2002 | Completed faculty merit pay evaluation forms | December 2001 |
| Progress Report | June 2002 | Report to the Coordinating Board | June 2002 |
| Hire tenure-track faculty with appropriate credentials | September 2002 | Faculty contracts | August 2001 |
| Apply faculty merit pay increases | September 2002 | Faculty contracts | December 2001 |
| Re-evaluate faculty recruitment needs | December 2002 | Revised faculty recruitment plan |  |
| Progress Report | December 2002 | Report to the Coordinating Board | January 2003 |
| Enroll three faculty members in PhD programs | January 2003 | Faculty development contracts |  |
| Carry out targeted faculty recruitment searches | February 2003 | Advertisements for faculty positions in scholarly and professional journals |  |
| Carry out faculty assessment for development needs | March 2003 | Completed faculty assessment forms |  |
| Carry out faculty merit pay evaluations | April 2003 | Completed faculty merit pay evaluation forms | July 2003 |
| Progress Report | June 2003 | Report to the Coordinating Board | July 2003 |
| Hire tenure-track faculty with appropriate credentials | September 2003 | Faculty contracts | September 2003 |
| Apply faculty merit pay increases | September 2003 | Faculty contracts | January 2004 |
| Component fully implemented | September 2003 | 90% of all faculty have terminal degrees appropriate to the teaching discipline | September 2005 |
| Support for ABD Faculty with Terminal Degree completion | August 2005 | Number and percent increase in terminally degreed nursing faculty |  |
| Increase workshops and seminars for faculty instructional improvement | August 2009 | Student retention increases |  |

## Plan Component: 14.5 Create the Texas Institute for the Preservation of History and Culture.

| Designated Institution Staff: |  |
| --- | --- |
| Name | Dr. Ikhlas Sabouni |
| Title | Dean, School of Architecture |
| Address | Prairie View A&M University |
| Phone | 936-261-9810 |
| Fax | 936-261-9826 |
| E-mail | isabouni@pvamu.edu |

| Designated Board Staff: |  |
| --- | --- |
| Name | Ms. Natalie Coffey |
| Title | Program Director, Participation and Success |
| Address | Texas Higher Education Coordinating Board |
| Phone | 512-427-6227 |
| Fax | 512-427-6522 |
| E-mail | Natalie.Coffey@thecb.state.tx.us |

| Funding: |  |
| --- | --- |
| Appropriated 2002 (millions) | $ 0.25 |
| Appropriated 2003 (millions) | $ 0.25 |
| Appropriated 2004 (millions) | $ 0.00 |
| Appropriated 2005 (millions) | $ 0.00 |
| Expended as of 8/31/05 | $ (0.23) |
| FY 04 Budget Reallocation | $ (0.07) |
| FY 05 Budget Reallocation | $ 0.00 |
| Appropriated 2006 (millions) | $ 0.00 |
| FY 06 Expended & Committed 6/30 | $ (0.11) |
| Available as of 6/30/06 | 0.09 |

TIPHC was hired in early September of this year, the Institute has

Summary

The Institute for the Preservation of History and Culture continues to meet its objectives and involvement in several projects in collaboration with the CURES Center that preserve the history and culture of communities and individuals in Texas.  The School of Architecture submitted a grant to the Brown Foundation and received funding in the amount of $1,000,000, evidence of the program’s competitiveness. The Center will receive $500,000 from the grant to conduct research, exhibits, lecture series, and media productions that will exhibit and document the contributions of African-Americans to the State.  The other $500,000 will be used for an Endowed Chair in the School of Architecture with expertise in Architecture History and Historical Preservation.  This funding will be matched with $500,000 from the OCR money that is earmarked for University Endowed Chairs.  Advertisement for this new position is in progress.  This individual will provide leadership and vast opportunities for research and service.  The Center developed last fall an exhibit titled “Common Ground”.  It was opened with a reception during the grand opening of the School of Architecture new building.  Similar exhibits in the TIPHC Gallery, traveling exhibits, and video productions will be developed in the coming month that will be viewed by the people of Texas.  This activity will help preserve and make accessible information about African-American history, and life and culture to the people of Texas.   The Brown Foundation grant will help considerably to make this happen.  The Institute is continuing to seek additional outside funding sources to continue enhancing its contribution in preserving history and culture.

Implementation Schedule

| Task | Expected Completion Date | Outcome Documentation | Actual Completion Date |
| --- | --- | --- | --- |
| Evaluate current and future needs and opportunities for collection and preservation of Texas historical artifacts | October 2001 | Texas Commitment to Prairie View A&M University Strategic Plan | July 2001 |
| Acquire equipment and hire consultants | December 2001 | Equipment is in place and consultants are working on identified projects | December 2001 |
| Progress Report | December 2001 | Report to the Coordinating Board | December 2001 |
| Faculty Recruitment | March 2002 | Faculty numbers and credentials are appropriate for the needs of the Institute | March 2002 |
| Staff Recruitment | March 2002 | Staff numbers and credentials are appropriate for the needs of the Institute | December 2002 |
| Progress Report | June 2002 | Report to the Coordinating Board | June 2002 |
| Component fully implemented | September 2002 | Texas Institute for the Preservation of History and Culture strategic plan with accomplishments identified | January 2003 |

Plan Component: 15.1 Texas Undergraduate Medical Academy

| Designated Institution Staff: |  |
| --- | --- |
| Name | Dr. Dennis E. Daniels |
| Title | Director, Undergraduate Medical Academy |
| Address | Prairie View A&M University |
| Phone | 936-857-3005 |
| Fax | 936-857-2118 |
| E-mail | Dennis_daniels@pvamu.edu |

| Designated Board Staff: |  |
| --- | --- |
| Name | Roger Alford |
| Title | Program Director, Universities and Health-Related Institutions Division |
| Address | Texas Higher Education Coordinating Board |
| Phone | 512-427-6216 |
| Fax | 512-427-6168 |
| E-mail | roger.alford@thecb.state.tx.us |

| Funding: |  |
| --- | --- |
| Appropriated 2002 (millions) | $ 0.00 |
| Appropriated 2003 (millions) | $ 0.00 |
| Appropriated 2004 (millions) | $ 0.00 |
| Appropriated 2005 (millions) | $ 0.00 |
| Expended as of 8/31/05 | $ (0.12) |
| FY 04 Budget Reallocation | $ 0.98 |
| FY 05 Budget Reallocation | $ 0.98 |
| Appropriated 2006 (millions) | $ 1.28 |
| FY 06 Expended & Committed 6/30 | $ (0.92) |
| Available as of 6/30/06 | 1.20 |

Summary

The University Medical Academy has received a $340,000 dollar grant and the Academy has hosted two initial development events. The first annual golf tournament was held on November 11, 2005, and the Red Ball event was held on February 11, 2006. The third cohort of 23 students has been enrolled with an average class grade point average of 3.8/4.0 scale. The third cohort increases the total Academy student enrollment to 51 students. The charter class has now taken the MCAT preparation course and completed the MCAT exam for admission to medical school. The chemistry faculty position search has reached the finalist stage and a fall 2006 hire is anticipated. The enhanced distance education/learning capabilities for the Academy are on schedule for completion during August 2006.

Implementation Schedule

| Task | Expected Completion Date | Outcome Documentation | Actual Completion Date |
| --- | --- | --- | --- |
| Review legislative intent | September 2003 | Copy of HB 85 | September 2003 |
| Establish organizational structure | September 2003 | A copy of the organizational structure of the Academy | September 2003 |
| Allocate space for the Medical Academy | September 2003 | Coordinating Board Approval | September 2003 |

Appendix A

OCR Priority Plan Items

Expenditure Trends

Appendix B

University College

Residential Retention Rates

Appendix C

Funding Revenues

Generated through

Formulas and Tuition

Actual: Fall 2001 through Spring 2006

Projected: Summer 2006, Fall 2006, and Spring 2007