Texas Commitment to

Prairie View A&M University

OCR Priority Plan Semiannual Report

June-December 2006

Submitted January 2007

TABLE OF CONTENTS

Plan Component 1.1:     University College			3

Plan Component 1.2:	Expand Project ACCESS			5

Plan Component 1.3:	Student Development and Support Center			7

Plan Component 1.4:	Merit-Based Honors Scholarship Program			9

Plan Component 2.1:	Strengthen Information Technology Services	11

Plan Component 2.2:	Strengthen Human Resources Function and Infrastructure	16

Plan Component 3.1:	Accreditation Support	18

Plan Component 4.1:	College of Nursing Building	20

Plan Component 4.2:     Enhance the College of Nursing	22

Plan Component 5.1:	Enhance the College of Engineering 	24

Plan Component 5.2a:    MS Program in Electrical Engineering	26

Plan Component 5.2b:	PhD Program in Electrical Engineering	28

Plan Component 5.3:	Engineering Facilities	30

Plan Component 6.1:	Enhance Educator Preparation Programs	33

Plan Component 7.1:	BS in Construction Science	36

Plan Component 7.2:	Master of Architecture	39

Plan Component 7.3:	School of Architecture Building	42

Plan Component 8.1:	Master Plan Renovations	44

Plan Component 9.1:	Strengthen Institutional Development Office	46

Plan Component 10.1:	Endowed Chairs	50

Plan Component 11.1:	PhD Program in Juvenile Forensic Psychology	52

Plan Component 11.2:	New Building for Juvenile Justice-Related Programs	55

Plan Component 12.1:	PhD in Educational Leadership	57

Plan Component 12.2:	MS in Computer Science	60

Plan Component 12.3:	MS in Information Systems	62

Plan Component 13.1:	Statutory Mission Texas Education Code, Section 87.104	64

Plan Component 13.2:	Institutional Mission Statement	65

Additional Plan Components Funded by the Texas State Legislature	66

Plan Component 14.1:	MS in Accounting	67

Plan Component 14.2:	MS in Community Development	69

Plan Component 14.3:	Community and Urban Rural Extension Service Center	72

Plan Component 14.4:	Faculty Recruitment, Retention and Development	74

Plan Component 14.5:	Texas Institute for the Preservation of History and Culture	76

Plan Component 15.1:	Texas Undergraduate Medical Academy	78

Plan Component: 1.1 Create the University College, which provides an academically focused, student-centered environment for the entire University community with an emphasis on freshmen.

| Designated Institution Staff: |  |
| --- | --- |
| Name | Mrs. Lettie Raab |
| Title | Executive Director, University College |
| Address | Prairie View A&M University |
| Phone | 936-857-4448 |
| Fax | 936-857-2261 |
| E-mail | lmraab@pvamu.edu |

| Designated Board Staff: |  |
| --- | --- |
| Name | Ms. Natalie Coffey |
| Title | Program Director, Participation and Success |
| Address | Texas Higher Education Coordinating Board |
| Phone | 512-427-6227 |
| Fax | 512-427-6127 |
| E-mail | Natalie.Coffey@thecb.state.tx.us |

| Funding: |  |
| --- | --- |
| Appropriated 2002 (millions) | $ 1.20 |
| Appropriated 2003 (millions) | $ 1.20 |
| Appropriated 2004 (millions) | $ 1.08 |
| Appropriated 2005 (millions) | $ 1.02 |
| Appropriated 2006 (millions) | $ 1.27 |
| Expended as of 8/31/06 | $ (5.26) |
| FY 04 Budget Reallocation | $ 0.00 |
| FY 05 Budget Reallocation | $ 0.00 |
| Appropriated 2007 (millions) | $ 1.38 |
| FY 07 Expended & Committed 12/31 | $ (0.98) |
| Available as of 12/31/06 | $ 0.91 |

Summary

University College (UC) is totally operational: freshman advisement has been centralized in the UC Division of Advisement; the PVAMU developmental education program, tutoring services, standardized testing services and the University’s Scholars’ Program (USP) have been centralized in the UC Division of Academic Enhancement and freshman residential services have been centralized in the UC Division of Student Life. A fall 2006 statistical analysis showed that the aggregate retention rate for the 7445 first time, full time freshmen who lived in the UC residential complex from 2000 through 2005 was 72.06%.  Between 1992 and 1998, the year that the PLACE, the pilot program for University College, was initiated, the retention rate for freshmen at PVAMU ranged between 57.7% (1997) to 60.9% (1992.).  During the last six months UC successfully implemented the first Learning Framework classes at PVAMU and the Associate Director of University College formed and is chairing the Achieving the Dream Committee for PVAMU. This group is preparing the PV project(s) to be included in this nationally sponsored initiative. The UC Division of Academic Enhancement is restructuring PV’s Developmental Education program and the UC Director is serving on the THECB’s Developmental Education Advisory Committee. In spring 2006 over 600 of the residents of UC completed the ACT Survey of Academic Advising.  40.5% of the students indicated that their academic advising met their student needs “Exceptionally Well” as compared to the national average of 19.7%. 32.8% indicated they had seen their advisor more than 5 times as compared to the national average of 12.9%.  UC is planning to send a team to the ‘Learning Communities National Summer Institute’ in summer 2007 in preparation for introducing ‘Learning Communities’ as an educational strategy at PVAMU.

Implementation Schedule

| Task | Expected Completion Date | Outcome Documentation | Actual Completion Date |
| --- | --- | --- | --- |
| Create University College | September 2000 | Completed residence halls and student center | September 2000 |
| Determine an administrative structure consistent with the mission of University College | September 2001 | Texas Commitment to Prairie View A&M University Strategic Plan | July 2001 |
| Develop strategies for implementation and assessment of the program and support services | October 2001 | Strategic Planning Document | July 2001 |
| Faculty and Staff Recruitment | October 2001 | Faculty and staff numbers and credentials are appropriate for the needs of University College | September 2001 |
| Equipment purchases | November 2001 | Equipment is in place that is appropriate for the University College | September 2001 |
| Train faculty and staff | November 2001 | Training schedule and materials Number and level of staff trained | September 2001 |
| Progress Report | December 2001 | Report to the Coordinating Board | December 2001 |
| Program Implemented | January 2002 | List of students enrolled in University College | September 2001 |
| Progress Report | June 2002 | Report to the Coordinating Board | June 2002 |
| Progress Report | December 2002 | Report to the Coordinating Board | January 2003 |
| Progress Report | June 2003 | Report to the Coordinating Board | July 2003 |
| Component fully implemented | August 2003 | Documentation of freshman retention and success rates | September 2003 |

# Plan Component: 1.2 Expand Project ACCESS, which provides a summer academic program for students prior to their freshmen year and a freshman component that stresses academic advisement and support services for students.

| Designated Institution Staff: |  |
| --- | --- |
| Name | Mrs. Lettie Raab |
| Title | Executive Director, University College |
| Address | Prairie View A&M University |
| Phone | 936-857-4448 |
| Fax | 936-857-2261 |
| E-mail | lmraab@pvamu.edu |

| Designated Board Staff: |  |
| --- | --- |
| Name | Ms. Natalie Coffey |
| Title | Program Director, Participation and Success |
| Address | Texas Higher Education Coordinating Board |
| Phone | 512-427-6227 |
| Fax | 512-427-6127 |
| E-mail | Natalie.Coffey@thecb.state.tx.us |

| Funding: | None requested |
| --- | --- |
| Appropriated 2002 (millions) | $ 0.00 |
| Appropriated 2003 (millions) | $ 0.00 |
| Appropriated 2004 (millions) | $ 0.00 |
| Appropriated 2005 (millions) | $ 0.00 |
| Expended as of 8/31/05 | $ 0.00 |
| FY 04 Budget Reallocation | $ 0.00 |
| FY 05 Budget Reallocation | $ 0.00 |
| Appropriated 2006 (millions) | $ 0.00 |
| FY 06 Expended & Committed 6/30 | $ 0.00 |
| Available as of 6/30/06 | $ 0.00 |

#### Summary and Implementation Schedule

ACCESS welcomed its 11th class and 1100th student in summer ’06. The theme for ACCESS 2006 was ‘Learning through Service,’ which was reflective of the ACCESS focus on Service Learning as an effective learning strategy. This year Service Learning was a weekly workshop for participants taught by Dr. Everett Penn of the University of Houston who has an extensive background in Service Learning. The students read “Nickled and Dimed in America” and were able to view the stage version of this book and discuss the concepts presented with the actors. The students participated in three service learning projects in the Houston area that were connected to the book. The students worked at a social service agency for families, a home for senior citizens and the Houston Food Bank. The Capstone Activity was a trip to New Orleans where the students spent three days helping to prepare a high school for opening in the fall. The students and staff put in over 2000 hours sanding, priming and painting the hall areas in Lusher Charter School and providing activities to the children and adult clients of the nearby ARC facility.

# Plan Component: 1.3 Provide start up funding for the operation of a student development and support center to house all educational and general, non-auxiliary student affairs, enrollment, and support functions.

| Designated Institution Staff: |  |
| --- | --- |
| Name | Mr. Don Byars |
| Title | Associate Provost for Enrollment Management |
| Address | Prairie View A&M University |
| Phone | 936-261-1060 |
| Fax | 936-857-2426 |
| E-mail | dobyars@pvamu.edu |

| Designated Board Staff: |  |
| --- | --- |
| Name | Ms. Natalie Coffey |
| Title | Program Director, Participation and Success |
| Address | Texas Higher Education Coordinating Board |
| Phone | 512-427-6227 |
| Fax | 512-427-6127 |
| E-mail | Natalie.Coffey@thecb.state.tx.us |

| Funding: |  |
| --- | --- |
| Appropriated 2002 (millions) | $ 1.00 |
| Appropriated 2003 (millions) | $ 1.00 |
| Appropriated 2004 (millions) | $ 0.87 |
| Appropriated 2005 (millions) | $ 0.88 |
| Appropriated 2006 (millions) | $ 1.01 |
| Expended as of 8/31/06 | $ (4.21) |
| FY 04 Budget Reallocation | $ (0.17) |
| FY 05 Budget Reallocation | $ (0.22) |
| Appropriated 2007 (millions) | $ 1.02 |
| FY 07 Expended & Committed 12/31 | $ (1.16) |
| Available as of 12/31/06 | $ 0.02 |

Summary

The Student Development Center housed in the Memorial Student Center remains the focal point for student services, with fully developed offices to support a wide variety of functions.  Integration of Enrollment Management and Student Affairs activities has strengthened the symbiotic relationship of the two units in providing quality delivery of services to students.  The Enrollment Management unit has hired an Executive Director for Enrollment Management who specifically works with Admissions, Recruitment & Marketing, and Orientation.

Effective June 1, 2004, Student Enrollment Services was split into Student Affairs: Career and Outreach Services, Disability Services, Housing and Residential Services, Judicial Services, Student Activities and Leadership, while Enrollment Management became Undergraduate Admissions, Student Financial Aid, Marketing & Recruitment, Orientation and the Registrar’s Office.  On December 1, 2006, Student Financial Aid began reporting directly to the Provost and Senior Vice President for Academic and Student Affairs while Enrollment Management assumed Graduate School recruitment duties.

The Student Center building itself continues to serve as a major social as well as service center in a rural institution such as Prairie View, which does not have an urban setting environment.

Implementation Schedule

| Task | Expected Completion Date | Outcome Documentation | Actual Completion Date |
| --- | --- | --- | --- |
| Develop and implement an assessment plan for all enrollment services | September 2001 | Uniform Recruitment and Retention Plan | August 2001 |
| Evaluate the future needs of the Student Development Support Center | September 2001 | Texas Commitment to Prairie View A&M University Strategic Plan | July 2001 |
| Expand the scope of recruitment activities | October 2001 | Comprehensive recruitment and marketing materials | December 2001 |
| Staff Recruitment | November 2001 | Staff numbers and credentials are appropriate for the needs of the center | December 2001 |
| Progress Report | December 2001 | Report to the Coordinating Board | December 2001 |
| Evaluate recruitment and dropout/stop out tracking system | February 2002 | Tracking software is in place and operational | May 2002 |
| Progress Report | June 2002 | Report to the Coordinating Board | June 2002 |
| Equipment purchases | September 2002 | Equipment is in place that is appropriate for the needs of the support center | November 2003 |
| Progress Report | December 2002 | Report to the Coordinating Board | January 2003 |
| Relocation of offices | May 2003 | All general student affairs, enrollment and support offices are located in the Memorial Student Center | July 2003 |
| Progress Report | June 2003 | Report to the Coordinating Board | July 2003 |
| Progress Report | December 2003 | Report to the Coordinating Board | January 2004 |
| Progress Report | June 2004 | Report to the Coordinating Board | July 2004 |
| Progress Report | December 2004 | Report to the Coordinating Board | January 2005 |
| Progress Report | June 2005 | Report to the Coordinating Board | July 2005 |
| Progress Report | December 2005 | Report to the Coordinating Board | January 2006 |
| Progress Report | June 2006 | Report to the Coordinating Board | July 2006 |
| Progress Report | December 2006 | Report to the Coordinating Board |  |
| Progress Report | June 2007 | Report to the Coordinating Board |  |
| Component fully implemented | August 2007 | Functional Support Center |  |

# Plan Component: 1.4 Establish a merit-based honors scholarship program.

| Designated Institution Staff: |  |
| --- | --- |
| Name | Mr. Don Byars |
| Title | Associate Provost for Enrollment Management |
| Address | Prairie View A&M University |
| Phone | 936-261-1060 |
| Fax | 936-857-2426 |
| E-mail | dobyars@pvamu.edu |

| Designated Board Staff: |  |
| --- | --- |
| Name | Mr. Jeff Treichel |
| Title | Director, Finance & Resource Planning |
| Address | Texas Higher Education Coordinating Board |
| Phone | 512-427-6122 |
| Fax | 512-427-6147 |
| E-mail | Jeff.Treichel@thecb.state.tx.us |

| Funding: |  |
| --- | --- |
| Appropriated 2002 (millions) | $ 0.80 |
| Appropriated 2003 (millions) | $ 0.80 |
| Appropriated 2004 (millions) | $ 0.88 |
| Appropriated 2005 (millions) | $ 1.75 |
| Appropriated 2006 (millions) | $ 1.11 |
| Expended as of 8/31/06 | $ (4.36) |
| FY 04 Budget Reallocation | $ 0.00 |
| FY 05 Budget Reallocation | $ (0.98) |
| Appropriated 2007 (millions) | $ 1.11 |
| FY 07 Expended & Committed 12/31 | $ 0.00 |
| Available as of 12/31/06 | $ 1.11 |

Summary

The management structure for Scholarships and the Financial Aid Office has undergone major revision since the previous report.  The Director’s position has been upgraded to Assistant Provost for Financial Aid and reports directly to the provost, effective December 1, 2006.  Scholarship funds earmarked for certain majors and programs have been distributed since fall 2005 from the Whitlowe  R. Green donation.  The scholarship funding available is undergoing review to determine the most effective impact the funds can have to support students.   Currently, $1.3 million in honors scholarship funds are available annually.  To improve the scholarship awarding process and introduce students to a variety of funding opportunities, more web-based information has been developed and is being distributed to students.

#### Implementation Schedule

| Task | Expected Completion Date | Outcome Documentation | Actual Completion Date |
| --- | --- | --- | --- |
| Proceed with plans for a Capital Campaign | July 2001 | Signed contract with campaign council including specific details of planned use of funds | December 2002 |
| Determine program criteria | September 2001 | Program criteria documented and approved by an appropriate University official | September 2001 |
| Progress Report | December 2001 | Report to the Coordinating Board | December 2001 |
| Solicit Cluster corporations for program funding | January 2002 | Funding solicitation proposal including specific details of planned use of funds |  |
| Determine academic requirements for the program | May 2002 | Program approval by the University Academic Council – minutes of a meeting showing the vote of the council |  |
| Progress Report | June 2002 | Report to the Coordinating Board | June 2002 |
| Determine a student governance structure for the program | September 2002 | Program by-laws documented and approved by an appropriate University official | September 2001 |
| Progress Report | December 2002 | Report to the Coordinating Board | January 2003 |
| Expand and strengthen gift acceptance and acknowledgement | February 2003 | Letters used to acknowledge and thank donors for gifts | February 2003 |
| Progress Report | June 2003 | Report to the Coordinating Board | July 2003 |
| Establish a campaign and development budget | November 2003 | Details of the campaign documented and approved by an appropriate University official; approved University budget documents | December 2003 |
| Establish a Planned Giving Program | November 2003 | Announcement posted on the University website and in brochures and pamphlets | March 2004 |
| Progress Report | December 2003 | Report to the Coordinating Board | January 2004 |
| Progress Report | June 2004 | Report to the Coordinating Board | July 2004 |
| Progress Report | December 2004 | Report to the Coordinating Board | January 2005 |
| Progress Report | June 2005 | Report to the Coordinating Board | July 2005 |
| Progress Report | December 2005 | Report to the Coordinating Board | January 2006 |
| Progress Report | June 2006 | Report to the Coordinating Board | July 2006 |
| Progress Report | December 2006 | Report to the Coordinating Board |  |
| Progress Report | June 2007 | Report to the Coordinating Board |  |
| Component fully implemented | August 2007 | Enrollment data verifying student enrollment in the program and certified by Registrar |  |

# Plan Component: 2.1 Strengthen information technology services.

| Designated Institution Staff: |  |
| --- | --- |
| Name | Mrs. Mary Lee Hodge |
| Title | Vice President for Business Affairs |
| Address | Prairie View A&M University |
| Phone | 936-261-2150 |
| Fax | 936-261-2159 |
| E-mail | mlhodge@pvamu.edu |

| Designated Board Staff: |  |
| --- | --- |
| Name | Mr. Jeff Treichel |
| Title | Director, Finance & Resource Planning |
| Address | Texas Higher Education Coordinating Board |
| Phone | 512-427-6122 |
| Fax | 512-427-6147 |
| E-mail | Jeff.Treichel@thecb.state.tx.us |

| Funding: |  |
| --- | --- |
| Appropriated 2002 (millions) | $ 0.80 |
| Appropriated 2003 (millions) | $ 0.80 |
| Appropriated 2004 (millions) | $ 0.70 |
| Appropriated 2005 (millions) | $ 0.70 |
| Appropriated 2006 (millions) | $ 2.12 |
| Expended as of 8/31/06 | $ (5.36) |
| FY 04 Budget Reallocation | $ 0.46 |
| FY 05 Budget Reallocation | $ 0.40 |
| Appropriated 2007 (millions) | $ 2.65 |
| FY 07 Expended & Committed 12/31 | $ (2.71) |
| Available as of 12/31/06 | $ 0.56 |

Summary

Below are the noteworthy accomplishments realized during the last six (6) months under the leadership and guidance of the SunGard/Collegis team:

Administrative Accomplishments

  - Initiated Banner implementation project

  - Installed Banner project hardware and software.

  - Implemented on-line payment/deferment agreement notification with tracking through the student self-service module.

  - Implemented web address verification during self-service sign-on process

  - Automated 20th class day drop process significantly reducing the effort  required to drop students for non-payment

  - Automated the process for feeding financial data from the Student Information System to FAMIS

  - Completed implementation of the electronic funds transfer for student refunds.

  - Engaged the university community in a comprehensive method of testing software applied maintenance in the administrative systems environment.

  - Loaded Financial Aid for 2006-2007 award year into SIS Plus for aid award and distribution.

Network Management Accomplishments

  - Installed high speed wireless infrastructure and connectivity in University College.

  - Upgraded network switching infrastructure to improve network connectivity across campus.

  - Upgraded the Cisco Pix 515 firewall and installed redundant Cisco Pix 525 firewalls to provide more robust performance, greater reliability, improved fault tolerance, greater protection of enterprise applications and to afford firewall protection for future expansion of networked resources.

  - Replaced the Physical Plant and Coleman Library core routers with state of the art routers to provide better performance and increased reliability of the network infrastructure.

  - Acquired and installed Cisco Works Enterprise network management software and hardware platform to provide for increased network management capabilities.

  - Completed a Microsoft Exchange project to convert all Faculty/Staff users from Sendmail to Microsoft Exchange email services.

  - Provided technical support and consultation for new construction projects on campus.

  - Provided support and consultation for upgrade and centralized security system to be housed in the Department of Public Safety.

  - Provided support and consultation for the development and implementation of a shared resource environment with Human Resources.

  - Upgraded McAfee Enterprise anti-virus solution to version 8.

  - Provided IT infrastructure and network connectivity for newly constructed buildings at PVAMU:

    - Electrical Engineering

    - Architecture

    - Nursing School

    - Athletics Administration

    - Juvenile Justice and Psychology

  - Provided network connectivity for Harrington Science building renovation.

  - Provided High Speed wireless infrastructure, network connectivity and ongoing technical support for all PVAMU student housing phases.

  - Implemented Microsoft Active Directory on PVAMU LAN.

  - Provided network connectivity to the following labs:

    - Animal Industries computer lab

    - Computer Science graduate computer lab

    - Texas Pre-Medical Academy computer lab

  - Upgraded fiber backbone between core locations.

  - Installed and implemented Voice Over IP (VOIP) telephony in newly constructed buildings at PVAMU and migrating to campus wide deployment.

  - Upgraded all campus buildings to a minimum of Category 5E standards for data connectivity for copper and fiber optic cabling.

  - Provided enhanced network security and intrusion protection for campus network.

  - Provided network support for environmental controls project campus wide.

  - Created and maintained a Network Operations Center (NOC) in the SR Collins data center which provisions 24 x 7 PVAMU network monitoring and control.

  - Upgraded the email system for students from Sendmail to Microsoft Exchange.

User Services and Lab Support Accomplishments

  - Developed a computer hard drive image for the College of Nursing computer labs to help facilitate software updates/upgrades, improve data security and authorized user authentication, ensure computer workstation software consistency and to minimize downtime and maintenance.

  - PVAMU Medical Academy computer lab - updated and repaired computers, installed University standard software, resolved network connectivity issues and placed the computers on the University’s PV network domain resulting in increased security and full-functionality for all computers.

  - Delco Building, College of Education new computer lab - installed University standard software, implemented DeepFreeze computer protection, setup/networked lab printers and placed the computers on the University’s PV network domain resulting in increased security and full-functionality for all computers.

  - Updated the SPSS configuration and licensing on 100 computers in the J.B. Coleman Student Computing Center lab.

  - Developed and implemented a new multimedia computer lab and TTVN enabled conference room in the Harrington Science Building designed to provide needed distance learning and video conferencing facilities, installed full-featured computers on the University’s PV domain that are designed to help facilitate training, presentations and academic enhancement/enrichment programs.

  - Implemented a first-phase deployment of the LANDesk computer management suite on University computers with additions to be made over the next few months to accommodate all computers campus-wide.

  - College of Business new computer lab - setup new computers, installed University standard software, implemented DeepFreeze computer protection and placed the computers on the University’s PV network domain resulting in increased security and full-functionality for all computers.

  - Developed plans and implementation strategies to combat and resolve a major computer virus attack to computers campus-wide.

  - Assisted in the roll-out and deployment of the University’s Microsoft Exchange Server based email system for students that provides full-featured, any-where, any-time, Internet based secure, authenticated access to their email.

  - College of Juvenile Justice – relocated computers from their old building to their new building; deployed a subset of new computers for faculty/staff and setup multiple new multimedia computer labs including deployment of University standard software and placing the computers on the University’s PV network domain.

  - Banner Project – developed and implemented a new computer training lab for the planned Banner academic system deployment and deployed the Banner client software on designated computers for the Banner Benchmarks Team.

  - Animal Industries - setup new computers, installed University standard software and placed the computers on the University’s PV network domain resulting in increased security and full-functionality for all computers.

  - College of Nursing - assisted in the planning and implementation of advanced, computer/networking technology designed to greatly enhance student learning/training, increase productivity and help position the College to more effectively take advantage of 21st Century academic computing.

Academic Services and Support Accomplishments

  - Provided support and consultation for the Houston Endowment Grant for the College of Nursing.

  - Designed the Information Technology Services Newsletter.

  - Provided the following training

    - Voice Over IP training for all PVAMU faculty and staff

    - SIS training for all new faculty at the College of Nursing

    - Time Management Using Microsoft Outlook, in conjunction with Alan Corder, for the staff of the Business Affairs Department

  - Created new documentation for:

    - PVAMU Wireless Network

    - Student Outlook Web Access

    - Faculty Outlook Web Access

  - Conducted the Teaching and Technology Needs Assessment for faculty.

  - Conducted the Faculty and Staff Satisfaction Survey.

  - Facilitated the Teaching & Technology Conference for Faculty and Staff.

  - Created a new Information Technology Services web site.

  - Researched and wrote the Business Process Analysis for the Office of Telecommunications and Distribution Services, in conjunction with Ray Quattlebaum, SunGard Higher Education Consultant.

  - Compiled ITS internal policies and procedures.

  - Review and recommend TTVN online courses and WebCT courses as a member of the Distance Learning Council.

  - Worked with the Academic Sub Committee to provided strategic leadership and direction with regard to an Academic technology Plan.

Web Integration Projects

  - Installed the SunGard Collegis Site Builder web content management service to provide web content management and creation for the university community.

  - Spearheaded the total redesign and deployment of a new PVAMU web presence via SunGard Collegis Site Builder.

  - Provided Onsite Site Builder training to PVAMU web content providers.

  - Conducted PVAMU migration of legacy web content to new web presence.

Summary

During the past six months several large projects have been completed or made significant progress toward completion.  These projects include the deployment of a Voice Over IP phone system, the initiation of the Banner implementation project, the planning and start of implementation of the $2.5 million Nursing grant for academic technology, the switch of all campus email (faculty, staff and students) to Microsoft Exchange, deployment of wireless network access throughout the main campus, automation of data feeds between the financial system (FAMIS) and the student system (SIS), and the upgrade of the wired network campus wide to provide stability and bandwidth control.

Over the next six months the VOIP project will be completed, an estimated 900 new computers will be ordered, imaged and deployed, Banner conversion and implementation of the Nursing project will make significant progress, a “dark fiber” project will be completed expanding the external data access from 60MB to 1GB, and all IT audit findings will be addressed.

Implementation Schedule

| Task | Expected Completion Date | Outcome Documentation | Actual Completion Date |
| --- | --- | --- | --- |
| Reevaluate current and future needs and opportunities for Information Technology | September 2001 | Texas Commitment to Prairie View A&M University Strategic Plan | July 2001 |
| Acquire Equipment and Hire Consultants | December 2001 | Paid invoices for equipment purchases related to goal; contracts with consultants including the specific nature of their objectives | December 2001 |
| Progress Report | December 2001 | Report to the Coordinating Board | December 2001 |
| Staff Recruitment | March 2002 | Written justification for hiring individuals for Information Technology positions | March 2002 |
| Progress Report | June 2002 | Report to the Coordinating Board | June 2002 |
| Component fully implemented | September 2002 | Texas Commitment to Prairie View A&M University Strategic Plan with accomplishments identified | September 2002 |
| Information Technology Management outsourced to SunGard Collegis, Inc. effective June 1, 2004. All PVAMU IT employees to SunGard Collegis, Inc. by July 31, 2004 | June 1, 2004 | Report to Coordinating Board Staff advised of plan to re-allocate funds to support ITS component 2.1 | June 2004 |
| Outsourcing of Information Technology to SunGard Collegis completed by September 1, 2004 | September 1, 2004 | Progress/Status Report from SunGard Collegis CIO to PVAMU Executive Vice President/CFO | September 1, 2004 |
| Extension of Internet service to students residing in University College facilities started during summer 2004 | September 1, 2004 | Progress/Status Report from SunGard Collegis CIO to PVAMU Executive Vice President/CFO | November 1, 2004 |

# Plan Component: 2.2 Strengthen human resources function and infrastructure and develop a competitive faculty compensation and benefit structure.

| Designated Institution Staff: |  |
| --- | --- |
| Name | Mrs. Mary Lee Hodge |
| Title | Vice President for Business Affairs |
| Address | Prairie View A&M University |
| Phone | 936-261-2150 |
| Fax | 936-261-2159 |
| E-mail | mlhodge@pvamu.edu |

| Designated Board Staff: |  |
| --- | --- |
| Name | Ms. Natalie Coffey |
| Title | Program Director, Participation and Success |
| Address | Texas Higher Education Coordinating Board |
| Phone | 512-427-6227 |
| Fax | 512-427-6147 |
| E-mail | Natalie.Coffey@thecb.state.tx.us |

| Funding: | None Required |
| --- | --- |
| Appropriated 2002 (millions) | $ 0.00 |
| Appropriated 2003 (millions) | $ 0.00 |
| Appropriated 2004 (millions) | $ 0.00 |
| Appropriated 2005 (millions) | $ 0.00 |
| Expended as of 8/31/05 | $ 0.00 |
| FY 04 Budget Reallocation | $ 0.00 |
| FY 05 Budget Reallocation | $ 0.00 |
| Appropriated 2006 (millions) | $ 0.00 |
| FY 06 Expended & Committed 6/30 | $ 0.00 |
| Available as of 6/30/06 | $ 0.00 |

Summary

During the past fiscal year (FY2006) the outside consulting firm of McConnell Jones Lanier and Murphy (MJLM) from Houston, Texas conducted a comprehensive compensation and job classification study of all classified staff positions and of administrative and professional positions (non-faculty) below the level of vice president, dean, associate and assistant vice president and associate and assistant dean.  The MJLM report showing the results of the study was presented to the staff during a University-wide meeting in December 2006.  Approximately $900,000 in staff salary equity adjustments was identified.  The University’s Administration has determined that if sufficient financial capacity exists, they will endeavor to make $150,000 of adjustment in the FY08 fiscal year.  The remainder of the adjustments will be made as individuals with higher salaries leave the campus.  The differential between their salary and that of their replacement will be captured centrally.  Each year during the budget preparation process, additional equity adjustments will be made until such time as all pay grades have been adjusted.  The first adjustments will be made at pay grade 1 and continue upward through all pay grades as funds allow.

In addition, the roll out of the People Admin system is complete for all staff positions.  Preparation for a like system to house faculty positions is in process.  Once that is complete, the final component of the system, student employment positions, will be undertaken.

Implementation Schedule

| Task | Expected Completion Date | Outcome Documentation | Actual Completion Date |
| --- | --- | --- | --- |
| Develop an assessment plan for review of faculty compensation and benefit structure and other human resources functions | September 2001 | Texas Commitment to Prairie View A&M University Strategic Plan | July 2001 |
| Progress Report | December 2001 | Report to the Coordinating Board | December 2001 |
| Create strategies to improve human resources functions | January 2002 | Customer satisfaction survey results | January 2002 |
| Develop and implement a compensation and benefits structure | February 2002 | Documentation on file | February 2002 |
| Develop and implement an employee evaluation and rewards system | April 2002 | Documentation on file of the number and level of employees receiving awards | April 2002 |
| Create and implement an employee training and development program | May 2002 | Training schedule and materials. Documentation on file of the number and level of employees trained | May 2002 |
| Progress Report | June 2002 | Report to the Coordinating Board | June 2002 |
| Faculty Recruitment | September 2002 | Faculty with appropriate terminal degrees are hired |  |
| Component fully implemented | October 2002 | Competitive faculty and staff compensation and benefits on file | October 2002 |

# Plan Component: 3.1 Maintain accreditation of programs currently accredited; as appropriate, obtain accreditation for programs that are not currently accredited.

| Designated Institution Staff: |  |
| --- | --- |
| Name | Dr. Munir Quddus |
| Title | Dean, College of Business |
| Address | Prairie View A&M University |
| Phone | 936-261-9200 |
| Fax | 936-261-9241 |
| E-mail | muquddus@pvamu.edu |

| Designated Board Staff: |  |
| --- | --- |
| Name | Dr. Roger Alford |
| Title | Program Director, Universities and Health-Related Institutions Division |
| Address | Texas Higher Education Coordinating Board |
| Phone | 512-427-6216 |
| Fax | 512-427-6168 |
| E-mail | Roger.alford@thecb.state.tx.us |

| Funding: |  |
| --- | --- |
| Appropriated 2002 (millions) | $ 0.20 |
| Appropriated 2003 (millions) | $ 0.20 |
| Appropriated 2004 (millions) | $ 0.87 |
| Appropriated 2005 (millions) | $ 0.88 |
| Appropriated 2006 (millions) | $ 0.95 |
| Expended as of 8/31/06 | $ (2.67) |
| FY 04 Budget Reallocation | $ (0.09) |
| FY 05 Budget Reallocation | $ (0.22) |
| Appropriated 2007 (millions) | $ 0.79 |
| FY 07 Expended & Committed 12/31 | $ (0.76) |
| Available as of 12/31/06 | $ 0.15 |

Summary

The Self-Evaluation Report (SER) was submitted to the Association to Advance Collegiate Schools of Business (AACSB) in August 2005.  On December 19, 2005, the Peer Review Team (PRT) sent their official pre-visit letter.  A visit was recommended by the team and supported by the AACSB Initial Accreditation Committee.   The college sent its formal “Response to the Pre-Visit” letter on January 20, 2006.

The final visit by the Peer Review Team (PRT) took place in February (5-8) 2006; the team recommended unconditional initial accreditation of all undergraduate and graduate programs; The Initial Accreditation Committee and the AACSB Board accepted the Team’s recommendations; the certificate of AACSB accreditation was received. President George C. Wright and Dean Munir Quddus attended the Annual Meeting in Paris in April to meet the AACSB leadership.

Implementation Schedule

| Task | Expected Completion Date | Outcome Documentation | Actual Completion Date |
| --- | --- | --- | --- |
| Develop a plan to attain AACSB accreditation for the College of Business | September 2001 | Texas Commitment to Prairie View A&M University Strategic Plan | July 2001 |
| Progress Report | December 2001 | Report to the Coordinating Board | December 2001 |
| Assess the Business faculty and the Business curriculum | March 2002 | Faculty and curricula are in place that meet accreditation standards | April 2002 |
| Conduct mock self-study | May 2002 | Self-study | May 2002 |
| Progress Report | June 2002 | Report to the Coordinating Board | June 2002 |
| Progress Report | December 2002 | Report to the Coordinating Board | January 2003 |
| Apply for candidacy to AACSB | January 2003 | Certificate of candidacy | October 2002 |
| Progress Report | June 2003 | Report to the Coordinating Board | July 2003 |
| Progress Report | December 2003 | Report to the Coordinating Board | January 2004 |
| Progress Report | June 2004 | Report to the Coordinating Board | June 2004 |
| Plan for initial accreditation visit | August 2004 | Application submitted and acceptance received for an initial accreditation visit in Spring 2006 | July 2004 |
| Progress with AACSB | August 2004 | Second year annual Candidacy Report submitted and acceptance received (October 2004) | August 2004 |
| Progress Report | December 2004 | Report to the Coordinating Board | December 2004 |
| Mock visit completed | Fall 2004 | Mock visit team post-visit Report Received | March 2005 |
| Progress Report |  | Submitted on June 2005 to the Office of VP Business | June/July 2005 |
| Self-Evaluation Report Submitted |  | This document was completed over the summer with extensive faculty participation | August 1, 2005 |
| Pre-Visit Letter Received |  | This letter, as is the norm, identified certain issues (major concerns, standard by standard analysis) and requested information and clarifications | December 19, 2005 |
| Respond to the Pre-Visit Letter Submitted |  | Document addresses all of the concerns and questions raised in the Pre-Visit letter | January 20, 2006 |
| Progress Report |  | Submitted on time | January 23, 2006 |
| Component fully implemented | May 2005 | The final visit by the PRT took place in February (5-8) 2006; The AACSB Board accepted the Team’s recommendations; the certificate of AACSB accreditation was received | April 12, 2006 |

# Plan Component: 4.1 Construct new College of Nursing Building.

| Designated Institution Staff: |  |
| --- | --- |
| Name | Mr. Fred Washington |
| Title | Associate Vice President, Administration & Auxiliary Services |
| Address | Prairie View A&M University |
| Phone | 936-261-2141 |
| Fax | 936-261-2145 |
| E-mail | fewashington@pvamu.edu |

| Designated Board Staff: |  |
| --- | --- |
| Name | Ms. Lillian Wanjagi |
| Title | Program Director, Resource Planning |
| Address | Texas Higher Education Coordinating Board |
| Phone | 512-427-6125 |
| Fax | 512-427-6147 |
| E-mail | Lillian.Wanjagi@thecb.state.tx.us |

| Funding: |  |
| --- | --- |
| PUF (millions) | $ 41.77 |
| Expended and committed as of 12/31/05 | $ (37.89) |

Note:  Building only ($10 million garage is separate.  Funding provided from Hermann Memorial Hospital for garage.)

Summary

Project completed and under budget.  No further action required.

#### Implementation Schedule

| Task | Expected Completion Date | Outcome Documentation | Actual Completion Date |
| --- | --- | --- | --- |
| Project Initiation | July 2001 | Form C-1 (PVAMU) | July 2001 |
| Needs Assessment | August 2001 | Preliminary Program of Requirements | August 2001 |
| Send preliminary Program of Requirements to short list of Architect/Engineer Firms | September 2001 | Letters to Architect/Engineer Firms | September 2001 |
| Architect/Engineer Selection | October 2001 | TAMUS F, P&C & PVAMU User Coordinator | October 2001 |
| Program of Requirements | November 2001 | TAMUS F, P &C & PVAMU College of Nursing User Coordinator | October 2001 |
| Negotiate Architect/Engineer Contract | December 2001 | Architect/Engineer Contract | December 2001 |
| Progress Report | December 2001 | Report to the Coordinating Board | December 2001 |
| Initiate Concept Design | January 2002 | Architectural Drawings | January 2002 |
| Approve Concept Design | May 2002 | Letter of Approval | May 2002 |
| Authorize Construction Documents Preparation | May 2002 | Letter of Authorization | July 2002 |
| Progress Report | June 2002 | Report to the Coordinating Board | June 2002 |
| Construction Documents | October 2002 | Architectural & MEP Drawings | January 2003 |
| Accept contractor proposals | December 2002 | Proposals received | March 2003 |
| Progress Report | December 2002 | Report to the Coordinating Board | January 2003 |
| Bidding and Negotiations | January 2003 | TAMUS F, P&C & PVAMU User Coordinator | June 2003 |
| Contract Administration | February 2003 | TAMUS F, P&C & PVAMU User Coordinator | July 2003 |
| Construction Commencement | March 2003 | TAMUS F, P&C & PVAMU User Coordinator | September 2003 |
| Progress Report | June 2003 | Report to the Coordinating Board | July 2003 |
| Progress Report | December 2003 | Report to the Coordinating Board | January 2004 |
| Progress Report | June 2004 | Report to the Coordinating Board | July 2004 |
| Progress Report | December 2004 | Report to the Coordinating Board | December 2004 |
| Construction Complete | June 2005 | TAMUS Form 111300 | January 2006 |
| Progress Report | June 2005 | Report to the Coordinating Board | July 2005 |
| Install Movable Furnishings | July 2005 | Furnishings installed | January 2006 |
| Beneficial Occupancy | August 2005 | TAMUS Form C-13A | January 2006 |

# Plan Component: 4.2 Enhance the College of Nursing by strengthening existing nursing and related programs.

| Designated Institution Staff: |  |
| --- | --- |
| Name | Dr. Betty Adams |
| Title | Dean, College of Nursing |
| Address | Prairie View A&M University |
| Phone | 713-797-7007 |
| Fax | 713-797-7013 |
| E-mail | bnadams@pvamu.edu |

| Designated Board Staff: |  |
| --- | --- |
| Name | Dr. Roger Alford |
| Title | Program Director, Universities and Health-Related Institutions Division |
| Address | Texas Higher Education Coordinating Board |
| Phone | 512-427-6216 |
| Fax | 512-427-6168 |
| E-mail | Roger.alford@thecb.state.tx.us |

| Funding: |  |
| --- | --- |
| Appropriated 2002 (millions) | $ 0.50 |
| Appropriated 2003 (millions) | $ 0.50 |
| Appropriated 2004 (millions) | $ 0.44 |
| Appropriated 2005 (millions) | $ 0.44 |
| Appropriated 2006 (millions) | $ 0.95 |
| Expended as of 8/31/06 | $ (4.81) |
| FY 04 Budget Reallocation | $ 0.97 |
| FY 05 Budget Reallocation | $ 1.03 |
| Appropriated 2007 (millions) | $ 0.74 |
| FY 07 Expended & Committed 12/31 | $ (0.69) |
| Available as of 12/31/06 | $ 0.07 |

Summary

The College of Nursing continues to be successful in the expansion of programs and increase in enrollment. The following represents outcomes of the college that depict this success:  (1) the December 2006 Commencement Exercise was notable with the inaugural graduates of the LVN-BSN Program and the Master of Science Degree in Nurse Education Program; (2) the overall enrollment for fall 2006 was increased to 416 students matriculating in nursing courses (undergraduate upper division clinical studies and graduate students); (3) the graduates performed at a 100% pass rate on the National Council Licensure Examination for Registered Nurses, and  all of the graduates selected jobs primarily in Houston/Gulf Coast communities, and (4) The Texas Higher Education Coordinating Board gave approval for preliminary planning for a Doctor of Philosophy Degree Program in Nursing.

Implementation Schedule (Date Added)

| Task | Expected Completion Date | Outcome Documentation | Actual Completion Date |
| --- | --- | --- | --- |
| Needs assessment for enhancement of programs and faculty productivity | September 2001 | Texas Commitment to Prairie View A&M University Strategic Plan | July 2001 |
| Progress Report | December 2001 | Report to the Coordinating Board | December 2001 |
| Program Evaluation | February 2002 | Academic department reports; external evaluation reports | April 2002 |
| Selection of Programs | April 2002 | University Academic Council approval | April 2002 |
| Progress Report | June 2002 | Report to the Coordinating Board | June 2002 |
| Prepare any proposals requiring approval by the Board of Regents | September 2002 | Board of Regents approval | NA |
| Progress Report | December 2002 | Report to the Coordinating Board | January 2003 |
| Progress Report | June 2003 | Report to the Coordinating Board | July 2003 |
| Selection of a Faculty Practice Model | September 2003 | Program presentation by the College of Nursing faculty | March 17, 2004 |
| Prepare proposal for a Research and Faculty Development Center | September 2003 | TAMUS approval of a Research and Faculty Development Center | December 2004 & continuing |
| Progress Report | December 2003 | Report to the Coordinating Board | January 2004 |
| Progress Report | June 2004 | Report to the Coordinating Board | July 2004 |
| Progress Report | June 2005 | Report to the Coordinating Board | June 2005 |
| Progress Report | December 2005 | Report to the Coordinating Board | December 2005 |
| Progress Report | June 2006 | Report to the Coordinating Board | July 2006 |
| Progress Report | December 2006 | Report to the Coordinating Board |  |
| Progress Report | June 2007 | Report to the Coordinating Board |  |
| Component fully implemented | August 2007 | Texas Commitment to Prairie View A&M University Strategic Plan with accomplishments identified |  |

# Plan Component: 5.1 Enhance the College of Engineering by strengthening existing engineering and related programs.

| Designated Institution Staff: |  |
| --- | --- |
| Name | Dr. Milton R. Bryant |
| Title | Dean, College of Engineering |
| Address | Prairie View A&M University |
| Phone | 936-261-9900 |
| Fax | 936-261-9946 |
| E-mail | mrbryant@pvamu.edu |

| Designated Board Staff: |  |
| --- | --- |
| Name | Dr. Roger Alford |
| Title | Program Director, Universities and Health-Related Institutions Division |
| Address | Texas Higher Education Coordinating Board |
| Phone | 512-427-6216 |
| Fax | 512-427-6168 |
| E-mail | Roger.alford@thecb.state.tx.us |

| Funding: |  |
| --- | --- |
| Appropriated 2002 (millions) | $ 0.50 |
| Appropriated 2003 (millions) | $ 0.50 |
| Appropriated 2004 (millions) | $ 0.44 |
| Appropriated 2005 (millions) | $ 0.17 |
| Appropriated 2006 (millions) | $ 0.37 |
| Expended as of 8/31/06 | $ (1.75) |
| FY 04 Budget Reallocation | $ (0.07) |
| FY 05 Budget Reallocation | $ (0.04) |
| Appropriated 2007 (millions) | $ 0.32 |
| FY 07 Expended & Committed 12/31 | $ (0.31) |
| Available as of 12/31/06 | $ 0.13 |

Summary

As part of the plan to enhance the College of Engineering, a continuing effort to improve the College’s presence in the business community and among prospective students has been made through committed website enhancements.  Support to the Assistant Dean enables a more careful monitoring of a grant received from the National Action Council for Minorities in Engineering, a competitive grant provided to a select few engineering colleges or universities. Support for faculty development and faculty/administrative travel to professional meetings contributed to the strengthening of the student retention initiative.  Support continued for the College ABET Assessment Committee chair, who monitors the college’s continuing quality improvement practices.  Dr. Paul Biney, chair of the ABET Assessment Committee, continues his efforts to provide continuous quality improvement throughout the College.  New to this initiative is the development of the Teamcenter Laboratory.  To the best of our knowledge, the Lab is the only one in Southeast Texas.  Utilization of the Teamcenter Community Software, provided by UGS through the PACE (Partners for the Advancement of Collaborative Engineering) program,  enables team members from around the world to collaborate and share 2D and 3D visual data, documents, and presentations.  Currently, we are involved in two major projects:  (1) Collaborative engineering-design instructional projects with University of Missouri-Rolla and (2) Design, build, and race a formula car through international collaboration by twenty universities from five continents.

Implementation Schedule

| Task | Expected Completion Date | Outcome Documentation | Actual Completion Date |
| --- | --- | --- | --- |
| Evaluate future needs and opportunities for the College of Engineering | September 2001 | Texas Commitment to Prairie View A&M University Strategic Plan | July 2001 |
| Evaluate all academic programs | September 2001 | Annual academic department reports | September 2001 |
| Progress Report | December 2001 | Report to the Coordinating Board | December 2001 |
| Determine non-substantive programmatic changes | January 2002 | University Academic/Graduate Council approval | NA* |
| Determine substantive programmatic changes | January 2002 | University Academic/Graduate Council approval | NA* |
| Prepare any proposals requiring approval by the Board of Regents | March 2002 | Board of Regents approval | NA* |
| Prepare any proposals requiring approval by the Coordinating Board | June 2002 | Coordinating Board approval (Note: CB approval would only be needed if major changes are made to programs or if new programs are developed.) | NA* |
| Progress Report | June 2002 | Report to the Coordinating Board | June 2002 |
| Faculty/Staff Recruitment | July 2002 | Faculty/Staff numbers and credentials are appropriate for the needs of the College | October 2002 |
| Progress Report | December 2002 | Report to the Coordinating Board | January 2003 |
| Progress Report | June 2003 | Report to the Coordinating Board | July 2003 |
| Progress Report | December 2003 | Report to the Coordinating Board | January 2004 |
| Progress Report | June 2004 | Report to the Coordinating Board | July 2004 |
| Progress Report | December 2004 | Report to the Coordinating Board | December 2004 |
| Progress Report | June 2005 | Report to the Coordinating Board | June 2005 |
| Progress Report | December 2005 | Report to the Coordinating Board | January 2006 |
| Progress Report | June 2006 | Report to the Coordinating Board | July 2006 |
| Progress Report | December 2006 | Report to the Coordinating Board |  |
| Progress Report | June 2007 | Report to the Coordinating Board |  |
| Component fully implemented | August 2007 | Texas Commitment to Prairie View A&M University Strategic Plan with accomplishments identified |  |

# Plan Component: 5.2a Develop new MS program in Electrical Engineering.

| Designated Institution Staff: |  |
| --- | --- |
| Name | Dr. Milton R. Bryant |
| Title | Dean, College of Engineering |
| Address | Prairie View A&M University |
| Phone | 936-261-9900 |
| Fax | 936-261-9946 |
| E-mail | mrbryant@pvamu.edu |

| Designated Board Staff: |  |
| --- | --- |
| Name | Dr. Roger Alford |
| Title | Program Director, Universities and Health-Related Institutions Division |
| Address | Texas Higher Education Coordinating Board |
| Phone | 512-427-6216 |
| Fax | 512-427-6168 |
| E-mail | Roger.alford@thecb.state.tx.us |

| Funding: |  |
| --- | --- |
| Appropriated 2002 (millions) | $ 0.45 |
| Appropriated 2003 (millions) | $ 0.45 |
| Appropriated 2004 (millions) | $ 0.40 |
| Appropriated 2005 (millions) | $ 0.40 |
| Appropriated 2006 (millions) | $ 0.42 |
| Expended as of 8/31/06 | $ (1.87) |
| FY 04 Budget Reallocation | $ (0.12) |
| FY 05 Budget Reallocation | $ (0.10) |
| Appropriated 2007 (millions) | $ 0.42 |
| FY 07 Expended & Committed 12/31 | $ (0.33) |
| Available as of 12/31/06 | $ 0.12 |

Summary

During the fall 2006 semester, twenty two (22) students were enrolled in the program, which continues to show steady growth.  A new faculty member was hired in August 2006 to support the program in the area of Communication & Signal Processing. Faculty members visited several universities to talk to prospective students.  The stipend for MS students was increased to make the program more attractive to prospective students.  One MS student in the program won second place in research presentation at the Texas A&M University System Pathway Symposium that took place on the Prairie View A&M University campus in November 2006.

Implementation Schedule

| Task | Expected Completion Date | Outcome Documentation | Actual Completion Date |
| --- | --- | --- | --- |
| Assign faculty to the program and assess faculty recruitment needs | March 2001 | Faculty Contracts | March 2001 |
| Prepare program proposal | June 2001 | Program proposal (Draft proposal sent to System and CB) | June 2001 |
| Submit proposal to the Graduate Council | June 2001 | Graduate Council approval | June 2001 |
| Prepare proposal for the Board of Regents | September 2001 | Board of Regents approval | September 2001 |
| Progress Report | December 2001 | Report to the Coordinating Board | December 2001 |
| Prepare proposal for the Coordinating Board | January 2002 | Coordinating Board approval | January 2002 |
| Progress Report | June 2002 | Report to the Coordinating Board | June 2002 |
| Faculty Recruitment | July 2002 | Faculty numbers and credentials are appropriate for the needs of the program | July 2002 |
| Accept first students into the program | September 2002 | Student registration information | August 2002 |
| Progress Report | December 2002 | Report to the Coordinating Board | January 2003 |
| Progress Report | June 2003 | Report to the Coordinating Board | June 2003 |
| Progress Report | December 2003 | Report to the Coordinating Board | January 2004 |
| Progress Report | June 2004 | Report to the Coordinating Board | June 2004 |
| Progress Report | December 2004 | Report to the Coordinating Board | December 2004 |
| Progress Report | June 2005 | Report to the Coordinating Board | July 2005 |
| Program Evaluation | October 2005 | Panel of Evaluators Report | October 2005 |
| Progress Report | December 2005 | Report to the Coordinating Board | December 2005 |
| Progress Report | June 2006 | Report to the Coordinating Board | July 2006 |
| Progress Report | December 2006 | Report to the Coordinating Board |  |
| Progress Report | June 2007 | Report to the Coordinating Board |  |
| Program Evaluation | September 2007 | Student graduation and success rates |  |
| Component fully implemented | September 2007 | Program supported through formula funding |  |
| Progress Report | June 2008 | Report to the Coordinating Board |  |
| Component fully implemented | September 2008 | Program supported through formula funding |  |

# Plan Component: 5.2b Develop new PhD program in Electrical Engineering.

| Designated Institution Staff: |  |
| --- | --- |
| Name | Dr. Milton R. Bryant |
| Title | Dean, College of Engineering |
| Address | Prairie View A&M University |
| Phone | 936-261-9900 |
| Fax | 936-261-9946 |
| E-mail | mrbryant@pvamu.edu |

| Designated Board Staff: |  |
| --- | --- |
| Name | Dr. Roger Alford |
| Title | Program Director, Universities and Health-Related Institutions Division |
| Address | Texas Higher Education Coordinating Board |
| Phone | 512-427-6216 |
| Fax | 512-427-6168 |
| E-mail | Roger.alford@thecb.state.tx.us |

| Funding: |  |
| --- | --- |
| Appropriated 2002 (millions) | $ 0.45 |
| Appropriated 2003 (millions) | $ 0.45 |
| Appropriated 2004 (millions) | $ 0.40 |
| Appropriated 2005 (millions) | $ 0.40 |
| Appropriated 2006 (millions) | $ 0.42 |
| Expended as of 8/31/06 | $ (1.67) |
| FY 04 Budget Reallocation | $ (0.12) |
| FY 05 Budget Reallocation | $ (0.10) |
| Appropriated 2007 (millions) | $ 0.42 |
| FY 07 Expended & Committed 12/31 | $ (0.48) |
| Available as of 12/31/06 | $ 0.17 |

Summary

In September 2006, sixteen (16) students were enrolled in the program.  Out of the sixteen students, nine of them have successfully completed the preliminary examinations of the program. In November 2006, the first qualifying examinations of the program were given to one doctoral student.  The student was successful in passing the examinations.  A new faculty member was hired in August 2006 to support the program in the area of Communication & Signal Processing. Faculty members visited several universities to recruit prospective students.  The stipend for the doctoral students in the program was increased to make the program more attractive.  One doctoral student in the program won third place in research presentation at the Texas A&M University System Pathway Symposium that took place on the Prairie View A&M University campus in November 2006.   A multi-million dollar proposal was submitted to the Department of Defense in support of the program.

Implementation Schedule

| Task | Expected Completion Date | Outcome Documentation | Actual Completion Date |
| --- | --- | --- | --- |
| Assign faculty to the program and assess faculty recruitment needs | August 2001 | Faculty Contracts | August 2001 |
| Prepare program proposal | August 2001 | Program proposal (Draft proposal sent to System and CB) | August 2001 |
| Submit proposal to the University Graduate Council | September 2001 | Graduate Council approval | September 2001 |
| Prepare proposal for the Board of Regents | December 2001 | Board of Regents approval | March 2002 |
| Progress Report | December 2001 | Report to the Coordinating Board | December 2001 |
| Prepare proposal for the Coordinating Board | January 2002 | Proposal submitted to the Coordinating Board | March 2002 |
| Progress Report | June 2002 | Report to the Coordinating Board | June 2002 |
| First Proposal Review | July 2002 | Out-of-State Reviewers Report | December 2002 |
| Progress Report | December 2002 | Report to the Coordinating Board | January 2003 |
| Second Proposal Review by the Coordinating Board | April 2003 | Coordinating Board approval | NA |
| Progress Report | June 2003 | Report to the Coordinating Board | July 2003 |
| Prepare substantive change request for SACS | August 2003 | SACS approval | August 2003 |
| Faculty Recruitment | August 2003 | Faculty numbers and credentials are appropriate for the needs of the program | September 2003 |
| Accept first students into the program | September 2003 | Student registration information | September 2003 |
| Progress Report | December 2003 | Report to the Coordinating Board | January 2004 |
| Progress Report | June 2004 | Report to the Coordinating Board | June 2004 |
| Program Evaluation | September 2004 | Student retention and success rates | December 2004 |
| Progress Report | December 2004 | Report to the Coordinating Board | December 2004 |
| Progress Report | June 2005 | Report to the Coordinating Board | July 2005 |
| Progress Report | December 2005 | Report to the Coordinating Board | December 2005 |
| Progress Report | June 2006 | Report to the Coordinating Board | July 2006 |
| Progress Report | December 2006 | Report to the Coordinating Board |  |
| Progress Report | June 2007 | Report to the Coordinating Board |  |
| Program Evaluation | September 2007 | Student graduation and success rates |  |
| Component fully implemented | September 2007 | Program supported through formula funding |  |

# Plan Component: 5.3 Upgrade or build additional Engineering facilities as needed.

| Designated Institution Staff: |  |
| --- | --- |
| Name | Mr. Fred Washington |
| Title | Associate Vice President, Administration and Auxiliary Services |
| Address | Prairie View A&M University |
| Phone | 936-261-2141 |
| Fax | 936-261-2145 |
| E-mail | fewashington@pvamu.edu |

| Designated Board Staff: |  |
| --- | --- |
| Name | Ms. Lillian Wanjagi |
| Title | Program Director, Resource Planning |
| Address | Texas Higher Education Coordinating Board |
| Phone | 512-427-6125 |
| Fax | 512-427-6147 |
| E-mail | Lillian.Wanjagi@thecb.state.tx.us |
| Funding: |  |
| TRB (millions) | $ 12.62 |
| Expended and committed as of 12/31/05 | $ (12.15) |

Summary

Project completed and under budget.  No further action required.

Implementation Schedule

| Task | Expected Completion Date | Outcome Documentation | Actual Completion Date |
| --- | --- | --- | --- |
| Each department in the College evaluates needs for classroom, research, and graduate student office space and submits report to Dean | April 2001 | Reports to Dean with details of plan for growth and additional facility needs for the department | April 2001 |
| Department heads and dean meet and determine needs and priorities | May 2001 | Report detailing priorities | May 2001 |
| Appoint College Committee to receive comments from faculty, research directors and others | June 2001 | Selection of Members, Chair and delegate charge to committee | June 2001 |
| Committee Meetings and solicitation of comments and Recommendation to Dean | June 2001 | Recommendations to Dean | June 2001 |
| Evaluate future needs and opportunities for the College of Engineering | July 2001 | Texas Commitment to Prairie View A&M University Strategic Plan | July 2001 |
| Determine the future space and equipment needs for the College of Engineering | August 2001 | College of Engineering Master Plan | August 2001 |
| Decision made whether to build or renovate | August 2001 | Report to the Coordinating Board | August 2001 |
| Progress Report | December 2001 | Report to the Coordinating Board | December 2001 |
| Project Initiation | January 2002 | Form C-1 (PVAMU) | January 2002 |
| Needs Assessment | February 2002 | Preliminary Program of Requirements | February 2002 |
| Send preliminary Program of Requirements to short list of Architect/Engineer Firms | March 2002 | Letters to Architect/Engineer Firms | March 2002 |
| Architect/Engineer Selection | April 2002 | TAMUS F, P&C & PVAMU User Coordinator Form C-31 | April 2002 |
| Program of Requirements | May 2002 | TAMUS F, P &C & PVAMU College of Engineering User Coordinator | May 2002 |
| Negotiate Architect/Engineer Contract | June 2002 | Architect/Engineer Contract | June 2002 |
| Progress Report | June 2002 | Report to the Coordinating Board | June 2002 |
| Initiate Concept Design | July 2002 | Architectural Drawings | July 2002 |
| Approve Concept Design | August 2002 | Letter of Approval | November 2002 |
| Authorize Construction Documents Preparation | October 2002 | Letter of Authorization | December 2002 |
| Progress Report | December 2002 | Report to the Coordinating Board | January 2003 |
| Construction Documents | March 2003 | Architectural & MEP Drawings | May 2003 |
| Accept contractor proposals | May 2003 | Proposals received | June 2003 |
| Bidding and Negotiations | June 2003 | TAMUS F, P&C & PVAMU User Coordinator | June 2003 |
| Progress Report | June 2003 | Report to the Coordinating Board | July 2003 |
| Contract Administration | July 2003 | TAMUS F, P&C & PVAMU User Coordinator | December 2003 |
| Construction Commencement | August 2003 | TAMUS F, P&C & PVAMU User Coordinator | January 2004 |
| Progress Report | December 2003 | Report to the Coordinating Board | January 2004 |
| Progress Report | June 2004 | Report to the Coordinating Board | July 2004 |
| Construction Complete | November 2004 | TAMUS Form 111300 | May 2005 |
| Install Movable Furnishings | December 2004 | Furnishings installed | June 2005 |
| Progress Report | December 2004 | Report to the Coordinating Board | December 2004 |
| Beneficial Occupancy | January 2005 | TAMUS Form C-13A | June 2005 |

# Plan Component: 6.1 Enhance Educator Preparation programs.

| Designated Institution Staff: |  |
| --- | --- |
| Name | Dr. M. Paul Mehta |
| Title | Dean, College of Education |
| Address | Prairie View A&M University |
| Phone | 936-261-3600 |
| Fax | 936-857-2911 |
| E-mail | mpmehta@pvamu.edu |

| Designated Board Staff: |  |
| --- | --- |
| Name | Dr. Roger Alford |
| Title | Program Director, Universities and Health-Related Institutions Division |
| Address | Texas Higher Education Coordinating Board |
| Phone | 512-427-6216 |
| Fax | 512-427-6168 |
| E-mail | Roger.alford@thecb.state.tx.us |

| Funding: |  |
| --- | --- |
| Appropriated 2002 (millions) | $ 0.40 |
| Appropriated 2003 (millions) | $ 0.40 |
| Appropriated 2004 (millions) | $ 0.35 |
| Appropriated 2005 (millions) | $ 0.35 |
| Appropriated 2006 (millions) | $ 0.37 |
| Expended as of 8/31/06 | $ (1.60) |
| FY 04 Budget Reallocation | $ (0.06) |
| FY 05 Budget Reallocation | $ (0.09) |
| Appropriated 2007 (millions) | $ 0.36 |
| FY 07 Expended & Committed 12/31 | $ (0.32) |
| Available as of 12/31/06 | $ 0.16 |

Summary

The College of Education hosted the accreditation visit by the National Council for Accreditation of Teacher Education (NCATE) on April 22-26, 2006.  The results of the visits were communicated to the institution in October 2006.  The University passed four of the six NCATE Standards (#3-6) without any areas of concern. Areas of concern were cited for the remaining two standards (#1-2) for which NCATE will conduct a focused visit in fall 2008.

For the completion year 2006, the College has met the accreditation requirements of the State Board for Educator Certification (SBEC).  The official ratings will be issued by SBEC in the spring of 2007.

Implementation Schedule

| Task | Expected Completion Date | Outcome Documentation | Actual Completion Date |
| --- | --- | --- | --- |
| Site visit by NCATE Board of Examiners | May 2001 | NCATE Board of Examiners Report | May 2001 |
| Annual determination of accreditation status by the State Board for Educator Certification (SBEC) | September 2001 | Memorandum from the Executive Director of SBEC indicating accreditation status | October 2001 |
| Evaluate future needs and opportunities for the College of Education | September 2001 | Texas Commitment to Prairie View A&M University Strategic Plan | July 2001 |
| Action by the NCATE Unit Accreditation Board | October 2001 | Memorandum of compliance with NCATE standards | November 2001 |
| Evaluate all academic programs | November 2001 | Annual academic department reports | November 2001 |
| Progress Report | December 2001 | Report to the Coordinating Board | December 2001 |
| Progress Report | June 2002 | Report to the Coordinating Board | June 2002 |
| Faculty Recruitment | September 2002 | Faculty numbers and credentials are appropriate for the needs of the College | August 2002 |
| Progress Report | December 2002 | Report to the Coordinating Board | January 2003 |
| Determine non-substantive programmatic changes | January 2003 | University Academic/Graduate Council approval | January 2003 |
| Determine substantive programmatic changes | May 2003 | University Academic/Graduate Council approval | February 2003 |
| Progress Report | June 2003 | Report to the Coordinating Board | July 2003 |
| Prepare any proposals requiring approval by the Board of Regents | September 2003 | Board of Regents approval | NA |
| Progress Report | December 2003 | Report to the Coordinating Board | January 2004 |
| Prepare any proposals requiring approval by the Coordinating Board | January 2004 | Coordinating Board approval (if needed) | NA |
| Progress Report | June 2004 | Report to the Coordinating Board | July 2004 |
| Progress Report | December 2004 | Report to the Coordinating Board | December 2004 |
| Progress Report | June 2005 | Report to the Coordinating Board | June 2005 |
| Progress Report | December 2005 | Report to the Coordinating Board | December 2005 |
| Site Visit by NCATE | April 2006 | NCATE Board of Examiner’s Report | June 2006 |
| Rejoinder to NCATE Board of Examiner’s Report | June 2006 | Rejoinder to NCATE Board of Examiner’s Report | July 2006 |
| Progress Report | June 2006 | Report to the Coordinating Board |  |
| Progress Report | December 2006 | Report to the Coordinating Board |  |
| Progress Report | June 2007 | Report to the Coordinating Board |  |
| Component fully implemented | August 2007 | Texas Commitment to Prairie View A&M University Strategic Plan with accomplishments identified |  |

# Plan Component: 7.1 Develop new BS in Construction Science.

| Designated Institution Staff: |  |
| --- | --- |
| Name | Dr. Ikhlas Sabouni |
| Title | Dean, School of Architecture |
| Address | Prairie View A&M University |
| Phone | 936-261-9810 |
| Fax | 936-261-9826 |
| E-mail | isabouni@pvamu.edu |

| Designated Board Staff: |  |
| --- | --- |
| Name | Dr. Roger Alford |
| Title | Program Director, Universities and Health-Related Institutions Division |
| Address | Texas Higher Education Coordinating Board |
| Phone | 512-427-6216 |
| Fax | 512-427-6168 |
| E-mail | Roger.alford@thecb.state.tx.us |

| Funding: |  |
| --- | --- |
| Appropriated 2002 (millions) | $ 0.50 |
| Appropriated 2003 (millions) | $ 0.50 |
| Appropriated 2004 (millions) | $ 0.00 |
| Appropriated 2005 (millions) | $ 0.00 |
| Appropriated 2006 (millions) | $ 0.00 |
| Expended as of 8/31/06 | $ (0.80) |
| FY 04 Budget Reallocation | $ (0.12) |
| FY 05 Budget Reallocation | $ 0.00 |
| Appropriated 2007 (millions) | $ 0.00 |
| FY 07 Expended & Committed 12/31 | $ (0.04) |
| Available as of 12/31/06 | 0.04 |

#### Summary

The Construction Science program submitted a proposed change in degree hours in spring 2006 which was subsequently approved by the University Academic Council.  This proposal was the result of the work of Dr. James Smith, PE, for Construction Science in consultation with major construction firms throughout Texas.  The degree program was reduced from 136 hours to 122 hours.  Additionally, changes in courses required were restructured to meet the demands of the industry and the American Council for Construction Education (ACCE).  The program has begun the process to make a formal application for accreditation to the ACCE. In order to meet the demands of the industry that is witnessing increased use of the design/build concept, we have instituted a “Design/Build” course for spring 2007.  Enrollment by architecture and construction science students is on a competitive basis.  Additionally, given the business needs of employers, we have identified ten courses in construction totaling thirty hours that architecture students can take to obtain a second degree.  We are seeing a high level of interest by architectural students for this program.  Finally, we are now planning course offerings in both programs through the 2009-2010 academic year to assist with degree plans and to allow us to offer secondary courses that are beneficial to the students.  Our first graduates are finding good jobs in the construction industry.  For example, one student who was graduated December 2006 and another one who is expected to be graduated May 2007 have received multiple employment offers. Both have executed contracts that have starting salaries in excess of $50,000 and hiring bonuses of $2,000 and $4,000.

Bachelor of Science in Construction Science Degree - Program is in its third year as of 05-06

| CATEGORY | YEAR 3 05 - 06 |
| --- | --- |
| Total Projected Endowment Number 2001 | 55 |
| Total Enrolled Student Numbers Spring 2006 | 46 |
| Graduates Fall 2005 & Spring 2006 | 6 |

Implementation Schedule

| Task | Expected Completion Date | Outcome Documentation | Actual Completion Date |
| --- | --- | --- | --- |
| Assign faculty to the program and assess faculty recruitment needs | November 2000 | Faculty Contracts | November 2000 |
| Prepare program proposal | December 2000 | Program proposal (Draft proposal sent to CB) | December 2000 |
| Submit proposal to the University Academic Council | January 2001 | Academic Council approval | January 2001 |
| Prepare proposal for the Board of Regents | March 2001 | Board of Regents approval | March 2001 |
| Prepare proposal for the Coordinating Board | June 2001 | Coordinating Board approval | June 2002 |
| Faculty Recruitment | August 2001 | Faculty numbers and credentials are appropriate for the needs of the program | June 2002 |
| Accept first students into the program | September 2001 | Student registration information | September 2002 |
| Progress Report | December 2001 | Report to the Coordinating Board | December 2001 |
| Progress Report | June 2002 | Report to the Coordinating Board | June 2002 |
| Progress Report | December 2002 | Report to the Coordinating Board | January 2003 |
| Progress Report | June 2003 | Report to the Coordinating Board | July 2003 |
| Program Evaluated | September 2003 | Student retention and success rates | February 2004 |
| Progress Report | December 2003 | Report to the Coordinating Board | January 2004 |
| Progress Report | June 2004 | Report to the Coordinating Board | July 2004 |
| Progress Report | December 2004 | Report to the Coordinating Board | December 2004 |
| Progress Report | June 2005 | Report to the Coordinating Board | July 2005 |
| Program Evaluated | September 2005 | Student graduation and success rates |  |
| Progress Report | December 2005 | Report to the Coordinating Board | December 2005 |
| Progress Report | June 2006 | Report to the Coordinating Board | July 2006 |
| Progress Report | December 2006 | Report to the Coordinating Board |  |
| Progress Report | June 2007 | Report to the Coordinating Board |  |
| Component fully implemented | September 2007 | Program supported through formula funding |  |

# Plan Component: 7.2 Develop new Master of Architecture.

| Designated Institution Staff: |  |
| --- | --- |
| Name | Dr. Ikhlas Sabouni |
| Title | Dean, School of Architecture |
| Address | Prairie View A&M University |
| Phone | 936-261-9810 |
| Fax | 936-261-9826 |
| E-mail | isabouni@pvamu.edu |

| Designated Board Staff: |  |
| --- | --- |
| Name | Dr. Roger Alford |
| Title | Program Director, Universities and Health-Related Institutions Division |
| Address | Texas Higher Education Coordinating Board |
| Phone | 512-427-6216 |
| Fax | 512-427-6168 |
| E-mail | Roger.alford@thecb.state.tx.us |

| Funding: |  |
| --- | --- |
| Appropriated 2002 (millions) | $ 0.50 |
| Appropriated 2003 (millions) | $ 0.50 |
| Appropriated 2004 (millions) | $ 0.44 |
| Appropriated 2005 (millions) | $ 0.44 |
| Appropriated 2006 (millions) | $ 0.42 |
| Expended as of 8/31/06 | $ (2.03) |
| FY 04 Budget Reallocation | $ (0.07) |
| FY 05 Budget Reallocation | $ (0.11) |
| Appropriated 2007 (millions) | $ 0.37 |
| FY 07 Expended & Committed 12/31 | $ (0.48) |
| Available as of 12/31/06 | $ (0.02) |

#### Summary

During the Spring Semester 2006 the program submitted and was approved for a change in the total number of hours required for a bachelors and masters degree.  The total of 168 hours conforms to directives of the National Architectural Accreditation Board (NAAB).  In April 2006 the program was reviewed by a visiting team from NAAB.  The team’s official report approved by the board in July 2006 granted re-accreditation for another six years.  This is the maximum term allowed.  During the past two years, every masters degree graduate received multiple job offers.  From the graduating classes of May 2005 though August 2006, our graduates have taken positions with leading firms in Dallas, Houston, San Antonio, Phoenix, Chicago, New York, Orlando, Florida and Oakland, California.  The program continues to have strong participation in student groups such as the AIAS and CSI chapters. In June 2006 our students won first place in the Houston AIA Chapter Sandcastle Competition, defeating all other architecture programs in the state and marking our fifth straight win in the context.

Five-year Masters of Architecture Degree - Program is in its fourth year as of 05-06

| CATEGORY | YEAR 4 05 - 06 |
| --- | --- |
| Total Projected Student Number in Proposal | 234 |
| Total Enrolled Student Number Fall 2006 | 276 * |
| Graduates, Fall 2005 & Spring 2006 | 28 |

* Exceeded projections

Implementation Schedule

| Task | Expected Completion Date | Outcome Documentation | Actual Completion Date |
| --- | --- | --- | --- |
| Assign faculty to the program and assess faculty recruitment needs | March 2001 | Faculty Contracts | March 2001 |
| Prepare program proposal | March 2001 | Program proposal (Draft proposal sent to CB) | July 2001 |
| Submit proposal to the University Graduate Council | May 2001 | Graduate Council approval | July 2001 |
| Prepare proposal for the Board of Regents | July 2001 | Board of Regents approval | September 2001 |
| Prepare proposal for the Coordinating Board | October 2001 | Coordinating Board approval | October 2001 |
| Faculty Recruitment | December 2001 | Faculty numbers and credentials are appropriate for the needs of the program | December 2001 |
| Progress Report | December 2001 | Report to the Coordinating Board | December 2001 |
| Accept first students into the program | January 2002 | Student registration information | January 2002 |
| Progress Report | June 2002 | Report to the Coordinating Board | June 2002 |
| Progress Report | December 2002 | Report to the Coordinating Board | January 2003 |
| Program self-study | January 2003 | Application for professional accreditation | January 2003 |
| Progress Report | June 2003 | Report to the Coordinating Board | July 2003 |
| Progress Report | December 2003 | Report to the Coordinating Board | January 2004 |
| Progress Report | June 2004 | Report to the Coordinating Board | July 2004 |
| Progress Report | December 2004 | Report to the Coordinating Board | December 2004 |
| Progress Report | June 2005 | Report to the Coordinating Board | June 2005 |
| Progress Report | December 2005 | Report to the Coordinating Board | December 2005 |
| Progress Report | June 2006 | Report to the Coordinating Board | July 2006 |
| Program Evaluation | October 2006 | Professional accreditation approved |  |
| Progress Report | December 2006 | Report to the Coordinating Board |  |
| Progress Report | June 2007 | Report to the Coordinating Board |  |
| Program Evaluation | September 2007 | Student graduation and success rates |  |
| Progress Report | December 2007 | Report to the Coordinating Board |  |
| Component fully implemented | January 2008 | Program supported through formula funding |  |

# Plan Component: 7.3 Construct new School of Architecture building.

| Designated Institution Staff: |  |
| --- | --- |
| Name | Dr. Ikhlas Sabouni |
| Title | Dean, School of Architecture |
| Address | Prairie View A&M University |
| Phone | 936-261-9810 |
| Fax | 936-261-9826 |
| E-mail | isabouni@pvamu.edu |

| Designated Board Staff: |  |
| --- | --- |
| Name | Ms. Lillian Wanjagi |
| Title | Program Director, Resource Planning |
| Address | Texas Higher Education Coordinating Board |
| Phone | 512-427-6125 |
| Fax | 512-427-6147 |
| E-mail | Lillian.Wanjagi@thecb.state.tx.us |

| Funding: |  |
| --- | --- |
| TRB (millions) | $ 25.20 |
| Expended and committed as of 12/31/05 | $ (24.57) |

Summary

The construction of the new Architecture Building is complete, with the building occupied on August 15, 2005 and classes taught for the fall 2005 semester beginning August 22, 2005.  The Grand Opening and Dedication for the facility was held on October 27, 2005.  The building was featured in the Texas Architect, Architectural Record, Cite, and Civil Engineers Journals.  As part of the Prairie View A&M University 2006 Homecoming, the building was named in the honor of Nathelyne Archie Kennedy, PE, a 1959 graduate of the university’s architecture engineering program.  Mrs. Kennedy was the first African-American female to earn an engineering degree from any university in Texas and to become a licensed Professional Engineer.  As President and Owner of Nathelyne A. Kennedy and Associates, her firm has been involved in numerous major projects across the state.  A Scholarship Endowment has been established for the School in her name.   TAMUS Symposium was conducted in the building this past fall.  The Texas Society of Architects Board also conducted their summer 2006 meeting in the facility.

Implementation Schedule

| Task | Expected Completion Date | Outcome Documentation | Actual Completion Date |
| --- | --- | --- | --- |
| Project Initiation | July 2001 | Form C-1 (PVAMU) | July 2001 |
| Needs Assessment | August 2001 | Preliminary Program of Requirements | August 2001 |
| Send preliminary Program of Requirements to short list of Architect/Engineer Firms | September 2001 | Letters to Architect/Engineer Firms | September 2001 |
| Architect/Engineer Selection | October 2001 | TAMUS F, P&C & PVAMU User Coordinator Form C-31 | October 2001 |
| Program of Requirements | November 2001 | TAMUS F, P &C & PVAMU School of Architecture User Coordinator | October 2001 |
| Negotiate Architect/Engineer Contract | December 2001 | Architect/Engineer Contract | December 2001 |
| Progress Report | December 2001 | Report to the Coordinating Board | December 2001 |
| Initiate Concept Design | January 2002 | Architectural Drawings | January 2002 |
| Approve Concept Design | June 2002 | Letter of Approval | May 2002 |
| Authorize Construction Documents Preparation | June 2002 | Letter of Authorization | July 2002 |
| Progress Report | June 2002 | Report to the Coordinating Board | June 2002 |
| Construction Documents | December 2002 | Architectural & MEP Drawings | December 2002 |
| Progress Report | December 2002 | Report to the Coordinating Board | January 2003 |
| Accept contractor proposals | February 2003 | Proposals received | February 2003 |
| Bidding and Negotiations | March 2003 | TAMUS F, P&C & PVAMU User Coordinator | March 2003 |
| Contract Administration | April 2003 | TAMUS F, P&C & PVAMU User Coordinator | June 2003 |
| Construction Commencement | May 2003 | TAMUS F, P&C & PVAMU User Coordinator | July 2003 |
| Progress Report | June 2003 | Report to the Coordinating Board | July 2003 |
| Progress Report | December 2003 | Report to the Coordinating Board | January 2004 |
| Progress Report | June 2004 | Report to the Coordinating Board | July 2004 |
| Progress Report | December 2004 | Report to the Coordinating Board | December 2004 |
| Construction Complete | February 2005 | TAMUS Form 111300 | August 2005 |
| Install Movable Furnishings | March 2005 | Furnishings installed | August 2005 |
| Beneficial Occupancy | April 2005 | TAMUS Form C-13A |  |

# Plan Component: 8.1 Carry out renovations identified in Master Plan.

| Designated Institution Staff: |  |
| --- | --- |
| Name | Mr. Fred Washington |
| Title | Associate Vice President, Administration and Auxiliary Services |
| Address | Prairie View A&M University |
| Phone | 936-261-2141 |
| Fax | 936-261-2145 |
| E-mail | fewashington@pvamu.edu |

| Designated Board Staff: |  |
| --- | --- |
| Name | Ms. Lillian Wanjagi |
| Title | Program Director, Resource Planning |
| Address | Texas Higher Education Coordinating Board |
| Phone | 512-427-6125 |
| Fax | 512-427-6147 |
| E-mail | lillian.wanjagi@thecb.state.tx.us |

| Funding: |  |
| --- | --- |
| TRB (millions) | $ 15.01 |
| Expended and committed as of 6/30/05 | $ (13.78) |

Summary

Priority Packages 1, 2 and 3 have been completed. Package 3 was completed in May 2006. Package 4, the total replacement of the masonry exterior of the JB Coleman Library has begun.

Implementation Schedule

| Task | Expected Completion Date | Outcome Documentation | Actual Completion Date |
| --- | --- | --- | --- |
| Identify projects | June 2001 | PVAMU Master Plan projects list | June 2001 |
| Initiate FY 2002 projects | June 2006 | PVAMU individual project file |  |
| Progress Report | December 2001 | Report to the Coordinating Board | December 2001 |
| Revalidate update project listing | May 2002 | PVAMU Master Plan projects list | April 2002 |
| Identify projects | June 2002 | PVAMU Master Plan projects list | April 2002 |
| Progress Report | June 2002 | Report to the Coordinating Board | June 2002 |
| Initiate FY 2002 projects | June 2006 | PVAMU individual project file |  |
| Progress Report | December 2002 | Report to the Coordinating Board | January 2003 |
| Revalidate update project listing | May 2003 | PVAMU Master Plan projects list | May 2003 |
| Identify projects | June 2003 | PVAMU Master Plan projects list | June 2003 |
| Progress Report | June 2003 | Report to the Coordinating Board | July 2004 |
| Initiate FY 2002 projects | June 2006 | PVAMU individual project file |  |
| Progress Report | December 2003 | Report to the Coordinating Board | January 2004 |
| Revalidate update project listing | May 2004 | PVAMU Master Plan projects list | May 2004 |
| Identify projects | June 2004 | PVAMU Master Plan projects list | June 2004 |
| Progress Report | June 2004 | Report to the Coordinating Board | July 2004 |
| Progress Report | December 2004 | Report to the Coordinating Board | December 2004 |
| Initiate FY 2002 projects | June 2006 | PVAMU individual project file |  |
| Revalidate update project listing | May 2005 | PVAMU Master Plan projects list | May 2005 |
| Progress Report | June 2005 | Report to the Coordinating Board | July 2005 |
| Component fully implemented | September 2005 | PVAMU Master Plan Completion Document | May 2006 |

# Plan Component: 9.1 Strengthen institutional development office.

| Designated Institution Staff: |  |
| --- | --- |
| Name | Dr. Willie Trotty |
| Title | Vice President for Research and Development |
| Address | Prairie View A&M University |
| Phone | 936-261-1550 |
| Fax | 936-261-1599 |
| E-mail | wftrotty@pvamu.edu |

| Designated Board Staff: |  |
| --- | --- |
| Name | Mr. Jeff Treichel |
| Title | Director, Finance & Resource Planning |
| Address | Texas Higher Education Coordinating Board |
| Phone | 512-427-6122 |
| Fax | 512-427-6147 |
| E-mail | Jeff.Treichel@thecb.state.tx.us |

| Funding: | None Requested |
| --- | --- |
| Appropriated 2002 (millions) | $ 0.00 |
| Appropriated 2003 (millions) | $ 0.00 |
| Appropriated 2004 (millions) | $ 0.00 |
| Appropriated 2005 (millions) | $ 0.00 |
| Appropriated 2006 (millions) | $ |
| Expended as of 8/31/06 | $ 0.00 |
| FY 04 Budget Reallocation | $ 0.00 |
| FY 05 Budget Reallocation | $ 0.00 |
| Appropriated 2007 (millions) | $ 0.00 |
| FY 06 Expended & Committed 12/31 | $ 0.00 |
| Available as of 12/31/06 | $ 0.00 |

Summary

In October 2006, the Office of Research and Development requested a contract extension for Ketchum, Inc. to serve as the Capital Campaign Counsel through December 2007.  During the period July 1 – December 31, 2006, membership for the Cabinet included 20 volunteers, 5 ex-officio participants, the Ketchum consultant and 5 staff.  The Offices of Development and Alumni Relations have worked with Cabinet volunteers and distinguished alumni to plan and host awareness gatherings to solicit campaign support.  During these special events, President George Wright encouraged alumni and friends of the University to contribute to the campaign that is scheduled to closeout with the Alumni/Special Gifts Phase in 2008.  Dr. Willie Trotty, Vice President for Research and Development, and Monica Williams, Associate Vice President for Development, continued to cultivate new relationships in order to garner corporate and private philanthropic support.

In an effort to strengthen university advancement strategies, college deans and selected directors participated in specialized training from an external consultant who is also an instructor at The Fund Raising School in The Center on Philanthropy at Indiana University.  Each participant was encouraged to design a development plan that identified prospective donors who would support individual colleges’ and ancillary units’ unfunded priorities.  Ms. Williams continued to work with Ketchum, Inc. and the University’s prospect researcher to maximize gifts from pacesetter and major gifts prospects.  Particular attention has been given to the cultivation and solicitation of planned giving.

As of December 2006, a total of $18,895,922.85 has been raised to support campaign initiatives.  Seventeen formal requests for funding were submitted during this semi-annual period; $543,749.83 was received from July 1 – December 31, 2006. Additionally, a request for $500,000 to support an endowed chair in business was submitted.

Implementation Schedule

| Task | Expected Completion Date | Outcome Documentation | Actual Completion Date |
| --- | --- | --- | --- |
| Evaluate future needs and opportunities for the Development Office | June 2001 | Development Office Strategic Plan incorporating these ideas | June 2001 |
| Proceed with plans for a Capital Campaign | July 2001 | Signed contract with campaign council including specific details of planned use of funds | December 2002 |
| Launch an Internal and External Public Relations Campaign | July 2001 | Public Relations Plan and Schedule of Related Activities | October 2002 |
| Solicitation of campaign leadership from Corporate Cluster, faculty and staff | August 2001 | Public notice naming campaign chair and leadership team | September 2003 |
| Hire additional development staff | September 2001 | Written justification for hiring individuals for Development Office | August 2003 |
| Research to identify 200-250 donor prospects and develop appropriate solicitation strategies | December 2001 | Database file identifying prospects and potential gifts including criteria used to identify these potential donors; appropriate solicitation strategies documented in memo format and approved by an appropriate University official | December 2003 |
| Progress Report | December 2001 | Report to the Coordinating Board | December 2001 |
| Progress Report | June 2002 | Report to the Coordinating Board | June 2002 |
| Progress Report | December 2002 | Report to the Coordinating Board | January 2003 |
| Expand and strengthen gift acceptance and acknowledgement | February 2003 | Letters used to acknowledge and thank donors for gifts | February 2003 |
| Progress Report | June 2003 | Report to the Coordinating Board | July 2003 |
| Establish a campaign and development budget | November 2003 | Details of the campaign documented and approved by an appropriate University official; approved University budget documents | December 2003 |
| Establish a Planned Giving Program | November 2003 | Announcement posted on the University website and in brochures and pamphlets | March 2004 |
| Progress Report | December 2003 | Report to the Coordinating Board | January 2004 |
| Progress Report | June 2004 | Report to the Coordinating Board | July 2004 |
| Progress Report | December 2004 | Report to the Coordinating Board | December 2004 |
| Progress Report | June 2005 | Report to the Coordinating Board | July 2005 |
| Continued Assessment of Effectiveness and use of data to strengthen the development function | August 2005 | Reports to the President, Development Council and Stakeholders | August 2005 |
| Progress Report | December 2005 | Report to the Coordinating Board | December 2005 |
| Progress Report | June 2006 | Report to the Coordinating Board | July 2006 |
| Continued Assessment of Effectiveness and use of data to strengthen the development function | August 2006 | Reports to the President, Development Council and Stakeholders |  |
| Progress Report | December 2006 | Report to the Coordinating Board |  |
| Progress Report | June 2007 | Report to the Coordinating Board |  |
| Continued Assessment of Effectiveness and use of data to strengthen the development function | August 2007 | Reports to the President, Development Council and Stakeholders |  |
| Component fully implemented | August 2007 | Office of Research and Development Annual Report |  |

# Plan Component: 10.1 Create 12 endowed chairs for new and existing programs.

| Designated Institution Staff: |  |
| --- | --- |
| Name | Dr. Joahanne Thomas-Smith |
| Title | Provost and Senior Vice President for Academic and Student Affairs |
| Address | Prairie View A&M University |
| Phone | 936-261-2174 |
| Fax | 936-261-2176 |
| E-mail | ejthomas-smith@pvamu.edu |

| Designated Board Staff: |  |
| --- | --- |
| Name | Mr. Jeff Treichel |
| Title | Director, Finance & Resource Planning |
| Address | Texas Higher Education Coordinating Board |
| Phone | 512-427-6122 |
| Fax | 512-427-6147 |
| E-mail | Jeff.Treichel@thecb.state.tx.us |

| Funding: |  |
| --- | --- |
| Appropriated 2002 (millions) | $ 1.00 |
| Appropriated 2003 (millions) | $ 1.00 |
| Appropriated 2004 (millions) | $ 0.88 |
| Appropriated 2005 (millions) | $ 0.87 |
| Appropriated 2006 (millions) | $ 0.53 |
| Expended as of 8/31/06 | $ (4.06) |
| FY 04 Budget Reallocation | $ 0.00 |
| FY 05 Budget Reallocation | $ (0.22) |
| Appropriated 2007 (millions) | $ 0.53 |
| FY 07 Expended & Committed 12/31 | $ 0.00 |
| Available as of 12/31/06 | $ 0.53 |

Summary

Establishing the twelve (12) endowed chairs in the following disciplines remains a priority: computer science (1), electrical engineering (1), biology (1), business (2), architecture (1), juvenile justice (2), educational leadership (1), history/political science (1), and nursing (2). The required matching funds have been identified for four (4) of the twelve (12) endowed chairs:  architecture (1), biology (1), educational leadership (1), and nursing (1).   The Office of Research and Development is continuing its efforts to acquire support for the remaining eight (8) endowed chairs. The University’s capability of supporting the salary requirement that exceeds interest income can be better assessed after the current legislative session ends. It is expected that the first chairs to be filled will be in educational leadership and juvenile justice.  It should be noted that the College of Education is undergoing a change in leadership which could affect the time required to identify and fill the endowed professorship.

Implementation Schedule

| Task | Expected Completion Date | Outcome Documentation | Actual Completion Date |
| --- | --- | --- | --- |
| Evaluate needs for endowed chairs | September 2001 | Texas Commitment to Prairie View A&M University Strategic Plan | July 2001 |
| Progress Report | December 2001 | Report to the Coordinating Board | December 2001 |
| Progress Report | June 2002 | Report to the Coordinating Board | June 2002 |
| Proceed with plans for a Capital Campaign | July 2002 | Signed contract with campaign council including specific details of planned use of funds | December 2002 |
| Begin fund-raising | December 2002 | Endowed Chair Fund-Raising Plan and action plan for fund-raising activities | January 2005 |
| Progress Report | December 2002 | Report to the Coordinating Board | January 2003 |
| Progress Report | June 2003 | Report to the Coordinating Board | July 2003 |
| Identify funding for 4 Chairs | September 2003 | Capital Campaign budget specifically identifying funding sources | January 2005 |
| Endowed Chair recruitment | September 2003 | Four faculty members hired into endowed chairs positions |  |
| Progress Report | December 2003 | Report to the Coordinating Board | January 2004 |
| Progress Report | June 2004 | Report to the Coordinating Board | July 2004 |
| Progress Report | December 2004 | Report to the Coordinating Board | January 2005 |
| Progress Report | June 2005 | Report to the Coordinating Board | July 2005 |
| Identify funding for 4 Chairs | September 2005 | Capital Campaign budget specifically identifying funding sources |  |
| Endowed Chair recruitment | September 2005 | Four faculty members hired into endowed chairs positions |  |
| Progress Report | October 2005 | Report to the Coordinating Board | October 2005 |
| Progress Report | December 2005 | Report to the Coordinating Board | December 2005 |
| Progress Report | June 2006 | Report to the Coordinating Board | July 2006 |
| Progress Report | December 2006 | Report to the Coordinating Board |  |
| Progress Report | June 2007 | Report to the Coordinating Board |  |
| Identify funding for 4 Chairs | September 2007 | Capital Campaign budget specifically identifying funding sources |  |
| Component fully implemented | September 2007 | Four faculty members hired into endowed chairs positions |  |

# Plan Component: 11.1 Develop new PhD program in Juvenile Forensic Psychology.

| Designated Institution Staff: |  |
| --- | --- |
| Name | Dr. H.Elaine Rodney |
| Title | Dean, College of Juvenile Justice and Psychology |
| Address | Prairie View A&M University |
| Phone | 936-261-5205 |
| Fax | 936-261-5252 |
| E-mail | herodney@pvamu.edu |

| Designated Board Staff: |  |
| --- | --- |
| Name | Dr. Roger Alford |
| Title | Program Director, Universities and Health-Related Institutions Division |
| Address | Texas Higher Education Coordinating Board |
| Phone | 512-427-6216 |
| Fax | 512-427-6168 |
| E-mail | Roger.alford@thecb.state.tx.us |

| Funding: |  |
| --- | --- |
| Appropriated 2002 (millions) | $ 0.00 |
| Appropriated 2003 (millions) | $ 0.00 |
| Appropriated 2004 (millions) | $ 0.67 |
| Appropriated 2005 (millions) | $ 0.66 |
| Appropriated 2006 (millions) | $ 0.64 |
| Expended as of 8/31/06 | $ (0.87) |
| FY 04 Budget Reallocation | $ (0.14) |
| FY 05 Budget Reallocation | $ (0.17) |
| Appropriated 2007 (millions) | $ 0.64 |
| FY 07 Expended & Committed 12/31 | $ (0.37) |
| Available as of 12/31/06 | $ 1.06 |

Summary

Fourteen students are currently enrolled in the Clinical Adolescent Psychology degree program, with three on leave of absence and expected to return fall 2007.  Two students completed their course work and will take their comprehensive examination in the spring.  Two students applied for clinical internships and five took clinical practicum.  Four students presented papers at scholarly conferences; two had articles accepted for publication. Twelve students are engaged in research activities and six students taught undergraduate courses as part of their assistantships.

Three experienced adjunct professors, who have published over 160 articles, were hired this fall.  Contracts are being extended to add two full time faculty members for the fall.  An advisory board consisting of three, has been formed to help us prepare for accreditation.  They are Dr. Lynn Rehm – University of Houston, Dr. James Lewis – Yale University, and Dr. Pauline Clansey – chair of the State

Board of Licensed Psychologists.

Implementation Schedule

| Task | Expected Completion Date | Outcome Documentation | Actual Completion Date |
| --- | --- | --- | --- |
| Accept contractor proposals | November 2003 | Proposal received | October 2004 |
| Bidding and Negotiations | December 2003 | TAMUS F, P&C & PVAMU User Coordinator | November 2004 |
| Contract Administration | January 2004 | TAMUS F, P&C & PVAMU User Coordinator | November 2004 |
| Assign faculty to the program and assess faculty recruitment needs | September 2004 | Faculty Contracts | July 2003 |
| Prepare program proposal | October 2004 | Program proposal | February 2003 |
| Progress Report | June 2004 | Report to the Coordinating Board | July 2004 |
| Progress Report | December 2004 | Report to the Coordinating Board | December 2004 |
| Progress Report | June 2005 | Report to the Coordinating Board | June 2004 |
| Submit proposal to the University Graduate Council | September 2005 | Graduate Council approval | May 2003 |
| Progress Report | December 2005 | Report to the Coordinating Board | December 2003 |
| Prepare proposal for the Board of Regents | January 2006 | Board of Regents approval | September 2003 |
| Prepare proposal for the Coordinating Board | April 28, 2006 | Proposal submitted to the Coordinating Board | October 2003 |
| Progress Report | June 2006 | Report to the Coordinating Board | June 2004 |
| First Proposal Review | October 2006 | Out-of-State Reviewers Report | April 2004 |
| Progress Report | December 2006 | Report to the Coordinating Board | December 2004 |
| Second Proposal Review by the Coordinating Board | January 2007 | Coordinating Board approval | April 2004 |
| Progress Report | June 2007 | Report to the Coordinating Board | June 2004 |
| Prepare substantive change request for SACS | July 2007 | SACS approval | May 2004 |
| Progress Report | December 2007 | Report to the Coordinating Board | April 2003 |
| Faculty Recruitment | June 2008 | Faculty numbers and credentials are appropriate for the needs of the program | February 2004 |
| Progress Report | June 2008 | Report to the Coordinating Board | June 2004 |
| Accept first students into the program | September 2008 | Student registration information | August 2004 |
| Progress Report | December 2008 | Report to the Coordinating Board | December 2004 |
| Progress Report | June 2009 | Report to the Coordinating Board | June 2005 |
| Progress Report | December 2009 | Report to the Coordinating Board | December 2005 |
| Progress Report | June 2010 | Report to the Coordinating Board | July 2006 |
| Program Evaluation | September 2010 | Student retention and success rates | June 2006 |
| Progress Report | October 2010 | Report to the Coordinating Board |  |
| Progress Report | December 2010 | Report to the Coordinating Board |  |
| Progress Report | June 2011 | Report to the Coordinating Board |  |
| Progress Report | December 2011 | Report to the Coordinating Board |  |
| Progress Report | June 2012 | Report to the Coordinating Board |  |
| Program Evaluation | September 2012 | Student graduation and success rates |  |
| Component fully implemented | September 2012 | Program supported through formula funding |  |

# Plan Component: 11.2 New building for juvenile justice-related programs.

| Designated Institution Staff: |  |
| --- | --- |
| Name | Mr. Fred Washington |
| Title | Associate Vice President, Administration and Auxiliary Services |
| Address | Prairie View A&M University |
| Phone | 936-261-2141 |
| Fax | 936-261-2145 |
| E-mail | fewashington@pvamu.edu |

| Designated Board Staff: |  |
| --- | --- |
| Name | Ms. Lillian Wanjagi |
| Title | Program Director, Resource Planning |
| Address | Texas Higher Education Coordinating Board |
| Phone | 512-427-6125 |
| Fax | 512-427-6147 |
| E-mail | lillian.wanjagi@thecb.state.tx.us |

| Funding: |  |
| --- | --- |
| TRB (millions) | $ 16.00 |
| Expended and committed as of 6/30/05 | $ (6.89) |

Summary

Construction of the new Juvenile Justice Building is complete. Furniture was moved into the building in August and September 2006, and the College of Juvenile Justice and Psychology moved their faculty and staff into the new building at the same time. The building dedication ceremony took place in October 2006.

Construction is proceeding ahead of schedule, with final completion scheduled for June 2006, pending any weather days that may be added to the contract time.  Occupancy could occur as early as July 2006.

.  Since that time, they have mobilized onto the site, and have poured structural concrete up to and including the second floor slab.  Construction is proceeding ahead of schedule, with final completion scheduled for June 2006, pending any weather days that may be added to the contract time.  Occupancy could occur as early as July 2006.

Implementation Schedule

| Task | Expected Completion Date | Outcome Documentation | Actual Completion Date |
| --- | --- | --- | --- |
| Project Initiation | July 2002 | Form C-1 (PVAMU) | July 2002 |
| Needs Assessment | August 2002 | Preliminary Program of Requirements | August 2002 |
| Send preliminary Program of Requirements to short list of Architect/Engineer Firms | September 2002 | Letters to Architect/Engineer Firms | September 2002 |
| Architect/Engineer Selection | November 2002 | TAMUS F, P&C & PVAMU User Coordinator Form C-31 | November 2002 |
| Program of Requirements | November 2002 | TAMUS F, P &C & PVAMU College of Nursing User Coordinator | November 2002 |
| Negotiate Architect/Engineer Contract | December 2002 | Architect/Engineer Contract | December 2002 |
| Progress Report | December 2002 | Report to the Coordinating Board | January 2003 |
| Initiate Concept Design | January 2003 | Architectural Drawings | February 2003 |
| Approve Concept Design | May 2003 | Letter of Approval | April 2003 |
| Authorize Construction Documents Preparation | May 2003 | Letter of Authorization | September 2003 |
| Progress Report | June 2003 | Report to the Coordinating Board | July 2003 |
| Construction Documents | September 2003 | Architectural & MEP Drawings | June 2004 |
| Accept contractor proposals | November 2003 | Proposals received | October 2004 |
| Bidding and Negotiations | December 2003 | TAMUS F, P&C & PVAMU User Coordinator | November 2004 |
| Progress Report | December 2003 | Report to the Coordinating Board | January 2004 |
| Contract Administration | January 2004 | TAMUS F, P&C & PVAMU User Coordinator | November 2004 |
| Construction Commencement | February 2004 | TAMUS F, P&C & PVAMU User Coordinator | February 2005 |
| Progress Report | June 2004 | Report to the Coordinating Board | July 2004 |
| Progress Report | December 2004 | Report to the Coordinating Board | December 2004 |
| Progress Report | June 2005 | Report to the Coordinating Board | July 2005 |
| Construction Complete | September 2005 | TAMUS Form 111300 | July 2006 |
| Install Movable Furnishings | October 2005 | Furnishings installed | July 2006 |
| Beneficial Occupancy | November 2005 | TAMUS Form C-13A | August 2006 |

# Plan Component: 12.1 Develop new PhD in Educational Leadership.

| Designated Institution Staff: |  |
| --- | --- |
| Name | Dr. Paul Mehta |
| Title | Dean, College of Education |
| Address | Prairie View A&M University |
| Phone | 936-261-3600 |
| Fax | 936-857-2911 |
| E-mail | mpmehta@pvamu.edu |

| Designated Board Staff: |  |
| --- | --- |
| Name | Dr. Roger Alford |
| Title | Program Director, Universities and Health-Related Institutions Division |
| Address | Texas Higher Education Coordinating Board |
| Phone | 512-427-6216 |
| Fax | 512-427-6168 |
| E-mail | Roger.alford@thecb.state.tx.us |

| Funding: |  |
| --- | --- |
| Appropriated 2002 (millions) | $ 0.60 |
| Appropriated 2003 (millions) | $ 0.60 |
| Appropriated 2004 (millions) | $ 0.00 |
| Appropriated 2005 (millions) | $ 0.00 |
| Appropriated 2006 (millions) | $ 0.00 |
| Expended as of 8/31/06 | $ (1.20) |
| FY 04 Budget Reallocation | $ 0.00 |
| FY 05 Budget Reallocation | $ 0.00 |
| Appropriated 2007 (millions) | $ 0.00 |
| FY 07 Expended & Committed 12/31 | $ 0.00 |
| Available as of 12/31/06 | 0.00 |

Summary

The Ph.D. program in Educational Leadership has been fully implemented with three cohort groups in place with an enrollment of fifty five (55) students.  One of the students from the first cohort group received her Ph.D. degree in December 2006.  A few other students from this cohort group are expected to receive their degrees in May and August 2007.  Members of all three cohort groups continue to publish their research in refereed scholarly journals.  Applications are being accepted for the fourth cohort group.  The department lost one of the original Ph.D. faculty members through resignation but was replaced by another faculty member.  A search is under way for two additional Ph.D. faculty members.

Implementation Schedule

| Task | Expected Completion Date | Outcome Documentation | Actual Completion Date |
| --- | --- | --- | --- |
| Assign faculty to the program and assess faculty recruitment needs | July 2001 | Faculty Contracts | August 2001 |
| Prepare program proposal | August 2001 | Program proposal (Draft proposal sent to CB) | September 2001 |
| Submit proposal to the University Graduate Council | September 2001 | Graduate Council approval | September 2001 |
| Prepare proposal for the Board of Regents | November 2001 | Board of Regents approval | December 2001 |
| Prepare proposal for the Coordinating Board | December 2001 | Final Proposal submitted to the Coordinating Board | December 2001 |
| Progress Report | December 2001 | Report to the Coordinating Board | December 2001 |
| First Proposal Review | May 2002 | Out-of-State Reviewers Report | May 2002 |
| Progress Report | June 2002 | Report to the Coordinating Board | July 2002 |
| First Reading at CB | July 2002 | Initial Approval of program | July 2002 |
| Second Proposal Review by the Coordinating Board | October 2002 | Final Coordinating Board approval | January 2003 |
| Prepare substantive change request for SACS | December 2002 | SACS approval | May 2004 |
| Faculty Recruitment | December 2002 | Faculty numbers and credentials are appropriate for the needs of the program | August 2004 |
| Progress Report | December 2002 | Report to the Coordinating Board | January 2003 |
| Accept first students into the program | January 2003 | Student registration information | August 2004 |
| Progress Report | June 2003 | Report to the Coordinating Board | July 2003 |
| Progress Report | December 2003 | Report to the Coordinating Board | January 2004 |
| Progress Report | June 2004 | Report to the Coordinating Board | July 2004 |
| Program Evaluation | September 2004 | Panel of Evaluators Report | September 2004 |
| Progress Report | December 2004 | Report to the Coordinating Board | December 2004 |
| Progress Report | June 2005 | Report to the Coordinating Board | June 2005 |
| Progress Report | December 2005 | Report to the Coordinating Board | December 2005 |
| Progress Report | June 2006 | Report to the Coordinating Board | July 2006 |
| Program Evaluation | September 2006 | Student graduation and success rates |  |
| Component fully implemented | September 2006 | Program supported through formula funding |  |
| Component fully implemented | June 2006 | All OCR funds will be expended by August 31, 2006 | June 2006 |

# Plan Component: 12.2 Develop new MS in Computer Science.

| Designated Institution Staff: |  |
| --- | --- |
| Name | Dr. Milton R. Bryant |
| Title | Dean, College of Engineering |
| Address | Prairie View A&M University |
| Phone | 936-261-9900 |
| Fax | 936-261-9946 |
| E-mail | mrbryant@pvamu.edu |

| Designated Board Staff: |  |
| --- | --- |
| Name | Dr. Roger Alford |
| Title | Program Director, Universities and Health-Related Institutions Division |
| Address | Texas Higher Education Coordinating Board |
| Phone | 512-427-6216 |
| Fax | 512-427-6168 |
| E-mail | Roger.alford@thecb.state.tx.us |

| Funding: |  |
| --- | --- |
| Appropriated 2002 (millions) | $ 0.40 |
| Appropriated 2003 (millions) | $ 0.40 |
| Appropriated 2004 (millions) | $ 0.35 |
| Appropriated 2005 (millions) | $ 0.35 |
| Appropriated 2006 (millions) | $ 0.32 |
| Expended as of 8/31/06 | $ (1.04) |
| FY 04 Budget Reallocation | $ (0.12) |
| FY 05 Budget Reallocation | $ (0.09) |
| Appropriated 2007 (millions) | $ 0.29 |
| FY 07 Expended & Committed 12/31 | $ (0.10) |
| Available as of 12/31/06 | $ 0.76 |

Summary

Six (6) graduate students were in the MS in Computer Science program in fall 2006 and two new students have joined the program in spring 2007.  In summer 2006 one student graduated with a MS in Computer Science. He is pursuing a Ph.D. in Computer Science at UT Dallas. Three students are scheduled to graduate in spring 2007.  The historic retention rate since 2002 has been over 90%. Some of the current projects/theses are in the process of being published. One graduate student is actively participating in research grants in the department.  In the fall 2006, two assistantships/scholarships were offered for conducting research and for teaching assistants under the supervision of faculty members.

During the last six months, the following efforts were made for recruiting more graduate students: (1) Quarter page advertisement for both programs (CS & CIS) was placed in the Winter06/Spring07 Diversity in Technology Minority College issue. The circulation will promote both the Graduate Programs to 60,000 female and multicultural engineering and computer science majors at 145 Colleges and 50 Minority sponsored career fairs; (2) During July 2006, an electronic mailing of the MS programs’ color brochure was sent to faculty of HBCU colleges and universities nationwide, as well as international colleges and universities. During this process, we contacted 470 HBCU faculty members, 40 HBCU colleges and universities, and 20 international colleges and universities. An email about the programs was also sent to over 1000 faculty members of CS programs throughout the country; (3) Brochures placed at three national CS related conferences; (4) Three CS graduate courses are in the process of being available to be offered completely online.

For the next six months, the department will continue to recruit students, maintain the laboratory facilities, continue using the distance learning facilities, and offer more web based and evening courses.

Implementation Schedule

| Task | Expected Completion Date | Outcome Documentation | Actual Completion Date |
| --- | --- | --- | --- |
| Assign faculty to the program and assess faculty recruitment needs | August 2001 | Faculty Contracts | June 2001 |
| Prepare program proposal | November 2001 | Program proposal (Draft proposal sent to CB) | July 2001 |
| Submit proposal to the University Graduate Council | December 2001 | Graduate Council approval | July 2001 |
| Progress Report | December 2001 | Report to the Coordinating Board | December 2001 |
| Prepare proposal for the Board of Regents | January 2002 | Board of Regents approval | October 2001 |
| Prepare proposal for the Coordinating Board | April 2002 | Coordinating Board approval | April 2002 |
| Progress Report | June 2002 | Report to the Coordinating Board | June 2002 |
| Faculty Recruitment | August 2002 | Faculty numbers and credentials are appropriate for the needs of the program | June 2002 |
| Accept first students into the program | September 2002 | Student registration information | September 2002 |
| Progress Report | December 2002 | Report to the Coordinating Board | January 2003 |
| Progress Report | June 2003 | Report to the Coordinating Board | July 2003 |
| Progress Report | December 2003 | Report to the Coordinating Board | January 2004 |
| Progress Report | June 2004 | Report to the Coordinating Board | July 2004 |
| Program Evaluation | October 2004 | Student retention and success rates | October 2004 |
| Progress Report | December 2004 | Report to the Coordinating Board | January 2005 |
| Progress Report | June 2005 | Report to the Coordinating Board | July 2005 |
| Progress Report | December 2005 | Report to the Coordinating Board | December 2005 |
| Progress Report | June 2006 | Report to the Coordinating Board | June 2006 |
| Progress Report | December 2006 | Report to the Coordinating Board |  |
| Progress Report | June 2007 | Report to the Coordinating Board |  |
| Progress Report | December 2007 | Report to the Coordinating Board |  |
| Progress Report | June 2008 | Report to the Coordinating Board |  |
| Program Evaluation | September 2008 | Student graduation and success rates |  |
| Component fully implemented | September 2008 | Program supported through formula funding |  |

# Plan Component: 12.3 Develop new MS in Information Systems.

| Designated Institution Staff: |  |
| --- | --- |
| Name | Dr. Milton R. Bryant |
| Title | Dean, College of Engineering |
| Address | Prairie View A&M University |
| Phone | 936-261-9900 |
| Fax | 936-261-9946 |
| E-mail | mrbryant@pvamu.edu |

| Designated Board Staff: |  |
| --- | --- |
| Name | Dr. Roger Alford |
| Title | Program Director, Universities and Health-Related Institutions Division |
| Address | Texas Higher Education Coordinating Board |
| Phone | 512-427-6216 |
| Fax | 512-427-6168 |
| E-mail | Roger.alford@thecb.state.tx.us |

| Funding: |  |
| --- | --- |
| Appropriated 2002 (millions) | $ 0.70 |
| Appropriated 2003 (millions) | $ 0.70 |
| Appropriated 2004 (millions) | $ 0.61 |
| Appropriated 2005 (millions) | $ 0.07 |
| Appropriated 2006 (millions) | $ 0.53 |
| Expended as of 8/31/06 | $ (2.34) |
| FY 04 Budget Reallocation | $ (0.17) |
| FY 05 Budget Reallocation | $ (0.02) |
| Appropriated 2007 (millions) | $ 0.53 |
| FY 07 Expended & Committed 12/31 | $ (0.48) |
| Available as of 12/31/06 | $ 0.13 |

Summary

Thirteen (13) graduate students were in the Computer Information Systems (CIS) MS program in fall 2006 and one new student has joined in spring 2007. In summer 2006, two students graduated with a MS in Computer Information Systems. One student has a job in the industry (Google) and another student is pursuing a graduate degree at UT Dallas. One student is expected to graduate in spring 2007 semester.  The historic retention rate since 2002 has been over 90%.  In fall 2006, four assistantships were given to graduate students for conducting research and for teaching assistants under the supervision of faculty members.  For spring 2007, one graduate course is being offered totally online via distance learning technology (WebCT).

During the last six months, the following efforts were made for recruiting more graduate students: (1) Quarter page advertisement for both programs (CS & CIS) was placed in the Winter06/Spring07 Diversity in Technology Minority College issue. The circulation will promote both the Graduate Programs to 60,000 female and multicultural engineering and computer science majors at 145 Colleges and 50 Minority sponsored career fairs; (2) During July 2006, an electronic mailing of the MS programs’ color brochure was sent to faculty of HBCU colleges and universities nationwide, as well as international colleges and universities. During this process, we contacted 470 HBCU faculty members, 40 HBCU colleges and universities, and 20 international colleges and universities. An email about the programs was also sent to over 1000 faculty members of CS programs throughout the country; (3) Brochures placed at three national CS related conferences; (4) Six CIS graduate courses are in the process of being available to be offered completely online.

Focusing on the next six months, the college plans to recruit more graduate students, maintain the laboratory facilities, continue using the distance learning facilities, and offer more web based and evening courses.

Implementation Schedule

| Task | Expected Completion Date | Outcome Documentation | Actual Completion Date |
| --- | --- | --- | --- |
| Assign faculty to the program and assess faculty recruitment needs | August 2001 | Faculty Contracts | June 2001 |
| Prepare program proposal | November 2001 | Program proposal (Draft proposal sent to CB) | July 2001 |
| Submit proposal to the University Graduate Council | December 2001 | Graduate Council approval | July 2001 |
| Progress Report | December 2001 | Report to the Coordinating Board | December 2001 |
| Prepare proposal for the Board of Regents | January 2002 | Board of Regents approval | October 2001 |
| Prepare proposal for the Coordinating Board | April 2002 | Coordinating Board approval | April 2002 |
| Progress Report | June 2002 | Report to the Coordinating Board | June 2002 |
| Faculty Recruitment | August 2002 | Faculty numbers and credentials are appropriate for the needs of the program | June 2002 |
| Accept first students into the program | September 2002 | Student registration information | September 2002 |
| Progress Report | December 2002 | Report to the Coordinating Board | January 2003 |
| Progress Report | June 2003 | Report to the Coordinating Board | July 2003 |
| Progress Report | December 2003 | Report to the Coordinating Board | January 2004 |
| Progress Report | June 2004 | Report to the Coordinating Board | July 2004 |
| Progress Report | December 2004 | Report to the Coordinating Board | January 2005 |
| Progress Report | June 2005 | Report to the Coordinating Board | July 2005 |
| Program Evaluation | October 2005 | Student retention and success rates (Achievements report) | February 2006 |
| Progress Report | December 2005 | Report to the Coordinating Board | December 2005 |
| Progress Report | June 2006 | Report to the Coordinating Board | July 2006 |
| Progress Report | December 2006 | Report to the Coordinating Board |  |
| Progress Report | June 2007 | Report to the Coordinating Board |  |
| Program Evaluation | July 2007 | Student graduation and success rates |  |
| Progress Report | December 2007 | Report to the Coordinating Board |  |
| Progress Report | June 2008 | Report to the Coordinating Board |  |
| Component fully implemented | September 2008 | Program supported through formula funding |  |

# Plan Component: 13.1 Delete language in the statutory mission Texas Education Code, Section 87.104.

| Designated Institution Staff: |  |
| --- | --- |
| Name | Mr. Frank Jackson |
| Title | Governmental Relations Officer |
| Address | Prairie View A&M University |
| Phone | 936-261-2122 |
| Fax | 936-261-2137 |
| E-mail | fdjackson@pvamu.edu |

| Designated Board Staff: |  |
| --- | --- |
| Name | Dr. Roger Alford |
| Title | Program Director, Universities and Health-Related Institutions Division |
| Address | Texas Higher Education Coordinating Board |
| Phone | 512-427-6216 |
| Fax | 512-427-6168 |
| E-mail | Roger.alfordl@thecb.state.tx.us |

| Funding: | None Requested |
| --- | --- |
| Appropriated (millions) | $ 0.00 |
| Expended as of12/31/04 | $ 0.00 |
| Committed as of 12/31/04 | $ 0.00 |
| Committed as of 6/30/05 | $ 0.00 |

Summary

Exclusionary and race-specific language has been removed via legislation from the statutory mission statement of Prairie View A&M University.  Task completed.

Implementation Schedule

| Task | Expected Completion Date | Outcome Documentation | Actual Completion Date |
| --- | --- | --- | --- |
| Work with legislature to amend legislation | June 2001 | Legislation enacted | June 2001 |
| Component fully implemented | June 2001 | Amended mission in place | June 2001 |

# Plan Component: 13.2 Delete race specific or exclusionary language in the institutional mission statement.

| Designated Institution Staff: |  |
| --- | --- |
| Name | Mr. Frank Jackson |
| Title | Governmental Relations Officer |
| Address | Prairie View A&M University |
| Phone | 936-857-4298 |
| Fax | 936-857-2598 |
| E-mail | fdjackson@pvamu.edu |

| Designated Board Staff: |  |
| --- | --- |
| Name | Dr. Roger Alford |
| Title | Program Director, Universities and Health-Related Institutions Division |
| Address | Texas Higher Education Coordinating Board |
| Phone | 512-427-6216 |
| Fax | 512-427-6168 |
| E-mail | Roger.alfordl@thecb.state.tx.us |

| Funding: | None Requested |
| --- | --- |
| Appropriated 2004 (millions) | $ 0.00 |
| Expended as of 12/31/04 | $ 0.00 |
| Committed as of 12/31/04 | $ 0.00 |
| Committed as of 6/30/05 | $ 0.00 |

Summary

A proposal to delete race-specific and exclusionary language from the institutional mission statement of Prairie View A&M University has been approved by the Texas A&M University System Board of Regents.  The proposal was approved at the July 2002 meeting of the Texas Higher Education Coordinating Board.  The institution’s mission has now been changed as prescribed in the Priority Plan.  Task completed.

Implementation Schedule

| Task | Expected Completion Date | Outcome Documentation | Actual Completion Date |
| --- | --- | --- | --- |
| Craft new mission language | June 2001 | New institutional mission | June 2001 |
| Prepare proposal for the Board of Regents | August 2001 | Board of Regents approval | December 2001 |
| Component fully implemented | October 2001 | Coordinating Board approval | July 2002 |

# Additional Plan Components Funded by the Texas State Legislature

## Plan Component: 14.1 Develop new MS in Accounting.

| Designated Institution Staff: |  |
| --- | --- |
| Name | Dr. Munir Quddus |
| Title | Dean, College of Business |
| Address | Prairie View A&M University |
| Phone | 936-261-9200 |
| Fax | 936-261-9241 |
| E-mail | muquddus@pvamu.edu |

| Designated Board Staff: |  |
| --- | --- |
| Name | Dr. Roger Alford |
| Title | Program Director, Universities and Health-Related Institutions Division |
| Address | Texas Higher Education Coordinating Board |
| Phone | 512-427-6216 |
| Fax | 512-427-6168 |
| E-mail | Roger.alford@thecb.state.tx.us |

| Funding: |  |
| --- | --- |
| Appropriated 2002 (millions) | $ 0.00 |
| Appropriated 2003 (millions) | $ 0.30 |
| Appropriated 2004 (millions) | $ 0.26 |
| Appropriated 2005 (millions) | $ 0.26 |
| Appropriated 2006 (millions) | $ 0.24 |
| Expended as of 8/31/06 | $ (0.90) |
| FY 04 Budget Reallocation | $ (0.05) |
| FY 05 Budget Reallocation | $ (0.07) |
| Appropriated 2007 (millions) | $ 0.26 |
| FY 07 Expended & Committed 12/31 | $ (0.21) |
| Available as of 12/31/06 | $ 0.09 |

#### Summary

By December 2006, the program admitted roughly 27 students of which eight have graduated from this program.  Dr. Brian Lee, the newly appointed Coordinator of the MSA Program, has moved aggressively to increase enrollment.  He is engaged during the regular semesters and in summer to assist the Director of Graduate Programs in Business in recruiting and retaining students in the MSA program.  His charge is to grow the program to at least 30 students by fall 2007.  A new staff (Recruitment and Placement Officer) position has been advertised from higher designated tuition.  The Accounting faculty members are working with the Texas CPA Society to strengthen the program. ACCT 5163 (Law and Ethics in Accounting) has been approved by the Texas CPA for the program. A strategic planning document on this was submitted in December 2005 by Dean Quddus to President Wright and Provost Thomas-Smith.  Mrs. Mary Lee Hodge, Vice President for Business Affairs, provided feedback to this document.

Implementation Schedule

| Task | Expected Completion Date | Outcome Documentation | Actual Completion Date |
| --- | --- | --- | --- |
| Prepare program proposal | November 2002 | Program proposal (Draft Proposal to CB) | November 2002 |
| Submit proposal to the University Graduate Council | December 2002 | Graduate Council approval | February 2003 |
| Progress Report | December 2002 | Report to the Coordinating Board | January 2003 |
| Prepare proposal for the Board of Regents | January 2003 | Board of Regents approval | March 2003 |
| Progress Report | June 2003 | Report to the Coordinating Board | July 2003 |
| Faculty Recruitment | August 2003 | Faculty numbers and credentials are appropriate for the needs of the program | August 2003 |
| Progress Report | December 2003 |  | January 2004 |
| Accept first students into the program | June 2004 | Student registration information | August 2003 |
| Progress Report | June 2004 | Report to the Coordinating Board | June 2004 |
| Progress Report | December 2004 | Report to the Coordinating Board | December 2004 |
| Progress Report | June 2005 | Report to the Coordinating Board | June 2005 |
| Progress Report | December 2005 | Report to the Coordinating Board | January 2006 |
| Progress Report | June 2006 | Report to the Coordinating Board | June 16, 2006 |
| Program Evaluation | October 2006 | Student retention and success rates |  |
| Progress Report | December 2006 | Report to the Coordinating Board |  |
| Progress Report | June 2007 | Report to the Coordinating Board |  |
| Progress Report | December 2007 | Report to the Coordinating Board |  |
| Progress Report | June 2008 | Report to the Coordinating Board |  |
| Program Evaluation | July 2008 | Student graduation and success rates |  |
| Progress Report | December 2008 | Report to the Coordinating Board |  |
| Progress Report | June 2009 | Report to the Coordinating Board |  |
| Progress Report | December 2009 | Report to the Coordinating Board |  |
| Progress Report | June 2010 | Report to the Coordinating Board |  |
| Component fully implemented | September 2010 | Program supported through formula funding |  |

## Plan Component: 14.2 Develop new MS in Community Development.

| Designated Institution Staff: |  |
| --- | --- |
| Name | Dr. Ikhlas Sabouni |
| Title | Dean, School of Architecture |
| Address | Prairie View A&M University |
| Phone | 936-261-9810 |
| Fax | 936-261-9826 |
| E-mail | isabouni@pvamu.edu |

| Designated Board Staff: |  |
| --- | --- |
| Name | Dr. Roger Alford |
| Title | Program Director, Universities and Health-Related Institutions Division |
| Address | Texas Higher Education Coordinating Board |
| Phone | 512-427-6216 |
| Fax | 512-427-6168 |
| E-mail | Roger.alford@thecb.state.tx.us |

| Funding: |  |
| --- | --- |
| Appropriated 2002 (millions) | $ 0.40 |
| Appropriated 2003 (millions) | $ 0.40 |
| Appropriated 2004 (millions) | $ 0.00 |
| Appropriated 2005 (millions) | $ 0.00 |
| Appropriated 2006 (millions) | $ 0.00 |
| Expended as of 8/31/06 | $ (0.80) |
| FY 04 Budget Reallocation | $ 0.00 |
| FY 05 Budget Reallocation | $ 0.00 |
| Appropriated 2007 (millions) | $ 0.00 |
| FY 07 Expended & Committed 12/31 | 0.00 |
| Available as of 12/31/06 | 0.00 |

Summary

The Community Development program continues to grow as planned, with sixty-one (67) students enrolled at the masters level in fall 2006.  The students and faculty have been instrumental in developing collaborative partnerships between the University and its surrounding communities. Students’ research projects and community development projects have assisted area communities to attract developers and investors to create economic development in their communities. In addition, as a means to develop professionally, community development students have established student chapters of professional organizations (Association of Fundraising Professionals and Community Development Graduate Students Association), and in the process of establishing student chapters for the American Planning Association and the National Historic Preservation Society to help in their professional development. Because of this program’s interdisciplinary approach, students have conducted studies that address social, economic and physical needs of communities.  Starting fall 2007, the Community Development program will offer an international community development track. This new track will be used to promote and develop the foundation for an international community development doctoral program. Also this new track will be used to attract international students seeking knowledge and skills in the field of community development, along with preparing Prairie View A&M students to go to other countries to help in their development. The proposal for this new track has created a great deal of interest by other disciplines’ graduate program as means to form collaborative partnership in pursuing research grant opportunities.  Graduates of this program have either started their own development firms (20%), or are working for a home developer (20%), or are working for a governmental agency’s community and housing development department (50%) or are pursuing doctoral degrees (10%).

Masters of Community Development Degree - Program is in its fifth year as of 05-06

| CATEGORY | YEAR 5 05 - 06 |
| --- | --- |
| Total Projected Student Number in Proposal | 20 |
| Total Enrolled Student Number Fall 2006 | 69 * |
| Graduates, Fall 2005 & Spring 2006 | 25 |

* Exceeded projections

Implementation Schedule

| Task | Expected Completion Date | Outcome Documentation | Actual Completion Date |
| --- | --- | --- | --- |
| Prepare program proposal | November 2002 | Program proposal (Draft proposal to CB) | April 2001 |
| Submit proposal to the University Graduate Council | December 2002 | Graduate Council approval | May 2001 |
| Progress Report | December 2002 | Report to the Coordinating Board | January 2003 |
| Prepare proposal for the Board of Regents | January 2003 | Board of Regents approval | July 2001 |
| Prepare proposal for the Coordinating Board | April 2003 | Coordinating Board approval | September 2001 |
| Progress Report | June 2003 | Report to the Coordinating Board | July 2003 |
| Faculty Recruitment | August 2003 | Faculty numbers and credentials are appropriate for the needs of the program | August 2001 |
| Progress Report | December 2003 | Report to the Coordinating Board | January 2004 |
| Accept first students into the program | June 2004 | Student registration information | September 2001 |
| Progress Report | June 2004 | Report to the Coordinating Board | July 2004 |
| Progress Report | December 2004 | Report to the Coordinating Board | December 2004 |
| Progress Report | June 2005 | Report to the Coordinating Board | July 2005 |
| Progress Report | December 2005 | Report to the Coordinating Board | December 2005 |
| Progress Report | October 2006 | Report to the Coordinating Board | July 2006 |
| Progress Report | June 2006 | Report to the Coordinating Board |  |
| Progress Report | December 2006 | Report to the Coordinating Board |  |
| Progress Report | June 2007 | Report to the Coordinating Board |  |
| Progress Report | December 2007 | Report to the Coordinating Board |  |
| Progress Report | June 2008 | Report to the Coordinating Board |  |
| Program Evaluation | July 2008 | Student graduation and success rates |  |
| Progress Report | December 2008 | Report to the Coordinating Board |  |
| Progress Report | June 2009 | Report to the Coordinating Board |  |
| Progress Report | December 2009 | Report to the Coordinating Board |  |
| Progress Report | June 2010 | Report to the Coordinating Board |  |
| Component fully implemented | September 2010 | Program supported through formula funding |  |

## Plan Component: 14.3 Create the Community and Urban Rural Enhancement Studies (CURES) Center.

| Designated Institution Staff: |  |
| --- | --- |
| Name | Dr. Ikhlas Sabouni |
| Title | Dean, School of Architecture |
| Address | Prairie View A&M University |
| Phone | 936-261-9810 |
| Fax | 936-261-9826 |
| E-mail | isabouni@pvamu.edu |

| Designated Board Staff: |  |
| --- | --- |
| Name | Ms. Natalie Coffey |
| Title | Program Director, Participation and Success |
| Address | Texas Higher Education Coordinating Board |
| Phone | 512-427-6227 |
| Fax | 512-427-6522 |
| E-mail | Natalie.Coffey@thecb.state.tx.us |

| Funding: |  |
| --- | --- |
| Appropriated 2002 (millions) | $ 0.20 |
| Appropriated 2003 (millions) | $ 0.20 |
| Appropriated 2004 (millions) | $ 0.00 |
| Appropriated 2005 (millions) | $ 0.00 |
| Appropriated 2006 (millions) | $ 0.00 |
| Expended as of 8/31/06 | $ (0.20) |
| FY 04 Budget Reallocation | $ 0.00 |
| FY 05 Budget Reallocation | $ 0.00 |
| Appropriated 2007 (millions) | $ 0.00 |
| FY 07 Expended & Committed 12/31 | $ (0.06) |
| Available as of 12/31/06 | 0.14 |

Summary

The Community Urban and Rural Enhancement Service Center (CURES) continues its active collaboration with area community preservation associations and specifically will be involved in the complete restoration process of historic homes and churches in Houston’s Freedmen's Town National Historic District.  A major new project involving students is the RBH Yates Museum Internship Program, which will have student interns work with RBHY consultants Stephen Fox (Rice U. Architectural Historian and fellow of Anchorage Foundation), Dr. Carol McDavid (Archaeologist & Co-Director of YCAP), David Bruner MA (Archaeologist & Co-Director of YCAP), and others.  Immediate needs under the internship program include: complete architectural design & engineering for pier & beam foundations of four historic homes by March 1st; obtain permits & repair foundation of four historic homes; complete architectural historic documentation (photos & video) and plans, and submit application to the US Dept. of Interior; complete structural engineering recommendation for stabilization of one historic church; density survey of current development vs. 1870 to 1900 historic district urban design; green space vs. covered & changes in population demographics.

Implementation Schedule

| Task | Expected Completion Date | Outcome Documentation | Actual Completion Date |
| --- | --- | --- | --- |
| Evaluate current and future needs and opportunities for community outreach | October 2001 | Texas Commitment to Prairie View A&M University Strategic Plan | July 2001 |
| Acquire equipment and hire consultants | December 2001 | Equipment is in place and consultants are working on identified projects | December 2001 |
| Progress Report | December 2001 | Report to the Coordinating Board | December 2001 |
| Faculty Recruitment | March 2002 | Faculty numbers and credentials are appropriate for the needs of CURES | March 2002 |
| Staff Recruitment | March 2002 | Staff numbers and credentials are appropriate for the needs of CURES | March 2002 |
| Progress Report | June 2002 | Report to the Coordinating Board | June 2002 |
| Component fully implemented | September 2002 | Texas Commitment to Prairie View A&M University Strategic Plan with accomplishments identified | January 2003 |

## Plan Component: 14.4 Faculty recruitment, retention and development.

| Designated Institution Staff: |  |
| --- | --- |
| Name | Dr. Joahanne Thomas-Smith |
| Title | Provost and Senior Vice President for Academic and Student Affairs |
| Address | Prairie View A&M University |
| Phone | 936-261-2174 |
| Fax | 936-261-2176 |
| E-mail | ejthomas-smith@pvamu.edu |

| Designated Board Staff: |  |
| --- | --- |
| Name | Ms. Natalie Coffey |
| Title | Program Director, Participation and Success |
| Address | Texas Higher Education Coordinating Board |
| Phone | 512-427-6227 |
| Fax | 512-427-6522 |
| E-mail | Natalie.Coffey@thecb.state.tx.us |

| Funding: |  |
| --- | --- |
| Appropriated 2002 (millions) | $ 1.50 |
| Appropriated 2003 (millions) | $ 1.50 |
| Appropriated 2004 (millions) | $ 1.31 |
| Appropriated 2005 (millions) | $ 1.31 |
| Appropriated 2006 (millions) | $ 0.85 |
| Expended as of 8/31/06 | $ (5.35) |
| FY 04 Budget Reallocation | $ (1.05) |
| FY 05 Budget Reallocation | $ 0.00 |
| Appropriated 2007 (millions) | $ 0.69 |
| FY 07 Expended & Committed 12/31 | $ (0.68) |
| Available as of 12/31/06 | 0.08 |

Summary

Tenured and tenured track faculty have broad access to faculty development.  To a limited extent, new faculty have been provided research support packages upon arrival. A decision was made in 2003-2004 to allocate funding for faculty development excluding pursuit of terminal degrees.  Almost without exception, vacant faculty positions have been filled by persons who already hold the terminal degree.  In disciplines where faculty salaries are highly competitive, some salary adjustments have been made.

#### Implementation Schedule

| Task | Expected Completion Date | Outcome Documentation | Actual Completion Date |
| --- | --- | --- | --- |
| Determine faculty recruitment priorities | September 2001 | Faculty recruitment plan | September 2001 |
| Create instruments for evaluation of faculty development needs | November 2001 | Faculty assessment instruments | September 2001 |
| Create faculty merit pay evaluation instruments | December 2001 | Faculty merit pay evaluation instruments | September 2001 |
| Progress Report | December 2001 | Report to the Coordinating Board | December 2001 |
| Initiate searches for faculty in all areas identified | February 2002 | General advertisement for faculty positions in the Chronicle for Higher Education | March 2001 |
| Carry out faculty assessment for development needs | March 2002 | Completed faculty assessment forms | December 2001 |
| Carry out faculty merit pay evaluations | April 2002 | Completed faculty merit pay evaluation forms | December 2001 |
| Progress Report | June 2002 | Report to the Coordinating Board | June 2002 |
| Hire tenure-track faculty with appropriate credentials | September 2002 | Faculty contracts | August 2001 |
| Apply faculty merit pay increases | September 2002 | Faculty contracts | December 2001 |
| Re-evaluate faculty recruitment needs | December 2002 | Revised faculty recruitment plan |  |
| Progress Report | December 2002 | Report to the Coordinating Board | January 2003 |
| Enroll three faculty members in PhD programs | January 2003 | Faculty development contracts |  |
| Carry out targeted faculty recruitment searches | February 2003 | Advertisements for faculty positions in scholarly and professional journals |  |
| Carry out faculty assessment for development needs | March 2003 | Completed faculty assessment forms |  |
| Carry out faculty merit pay evaluations | April 2003 | Completed faculty merit pay evaluation forms | July 2003 |
| Progress Report | June 2003 | Report to the Coordinating Board | July 2003 |
| Hire tenure-track faculty with appropriate credentials | September 2003 | Faculty contracts | September 2003 |
| Apply faculty merit pay increases | September 2003 | Faculty contracts | January 2004 |
| Component fully implemented | September 2003 | 90% of all faculty have terminal degrees appropriate to the teaching discipline | September 2005 |
| Support for ABD Faculty with Terminal Degree completion | August 2005 | Number and percent increase in Terminally degreed nursing faculty |  |
| Increase workshops and seminars for faculty instructional improvement | August 2009 | Student retention increases |  |

## Plan Component: 14.5 Create the Texas Institute for the Preservation of History and Culture.

| Designated Institution Staff: |  |
| --- | --- |
| Name | Dr. Ikhlas Sabouni |
| Title | Dean, School of Architecture |
| Address | Prairie View A&M University |
| Phone | 936-261-9810 |
| Fax | 936-261-9826 |
| E-mail | isabouni@pvamu.edu |

| Designated Board Staff: |  |
| --- | --- |
| Name | Ms. Natalie Coffey |
| Title | Program Director, Participation and Success |
| Address | Texas Higher Education Coordinating Board |
| Phone | 512-427-6227 |
| Fax | 512-427-6522 |
| E-mail | Natalie.Coffey@thecb.state.tx.us |

| Funding: |  |
| --- | --- |
| Appropriated 2002 (millions) | $ 0.25 |
| Appropriated 2003 (millions) | $ 0.25 |
| Appropriated 2004 (millions) | $ 0.00 |
| Appropriated 2005 (millions) | $ 0.00 |
| Appropriated 2006 (millions) | $ 0.00 |
| Expended as of 8/31/06 | $ (0.29) |
| FY 04 Budget Reallocation | $ (0.07) |
| FY 05 Budget Reallocation | $ 0.00 |
| Appropriated 2007 (millions) | $ 0.00 |
| FY 07 Expended & Committed 12/31 | $ (0.10) |
| Available as of 12/31/06 | 0.04 |

TIPHC was hired in early September of this year, the Institute has

Summary

The Institute continues to meet its objectives and was awarded a grant by the Brown Foundation in the amount of $500,000 to be used to conduct research, exhibits, lecture series, and media productions that will exhibit and document the contributions of African American to the State of Texas.  Another $500,000 was awarded to the School of Architecture to be used for an Endowed Chair with expertise in Architecture History and Historical Preservation.  This will be matched with $500,000 from the OCR allocations for university Endowed Chairs.  Advertisement for this position is in progress.  This individual will provide leadership and vast opportunities for research and service.  Similarly, the TIPHC Gallery, traveling exhibits, and video productions will be developed in the coming month for schools and the general public in the state of Texas. The Institute is continuing to seek additional outside funding sources to continue its contribution in preserving history and culture.  Some of the Programs/Publications and Exhibits that are in progress and have been funded by the Brown Foundation are:  Forever Free (February –March 2007); Oral History (Publication/February 2007; Exhibit/April 2007); Change Matters: People and the Environment (January/February 2007); and Historical Black Cemetery (Publication/March 2007; Exhibit/May 2007).

Implementation Schedule

| Task | Expected Completion Date | Outcome Documentation | Actual Completion Date |
| --- | --- | --- | --- |
| Evaluate current and future needs and opportunities for collection and preservation of Texas historical artifacts | October 2001 | Texas Commitment to Prairie View A&M University Strategic Plan | July 2001 |
| Acquire equipment and hire consultants | December 2001 | Equipment is in place and consultants are working on identified projects | December 2001 |
| Progress Report | December 2001 | Report to the Coordinating Board | December 2001 |
| Faculty Recruitment | March 2002 | Faculty numbers and credentials are appropriate for the needs of the Institute | March 2002 |
| Staff Recruitment | March 2002 | Staff numbers and credentials are appropriate for the needs of the Institute | December 2002 |
| Progress Report | June 2002 | Report to the Coordinating Board | June 2002 |
| Component fully implemented | September 2002 | Texas Institute for the Preservation of History and Culture strategic plan with accomplishments identified | January 2003 |

Plan Component: 15.1 Texas Undergraduate Medical Academy

| Designated Institution Staff: |  |
| --- | --- |
| Name | Dr. Dennis E. Daniels |
| Title | Director, Undergraduate Medical Academy |
| Address | Prairie View A&M University |
| Phone | 936-261-3070 |
| Fax | 936-261-3089 |
| E-mail | dedaniels@pvamu.edu |

| Designated Board Staff: |  |
| --- | --- |
| Name | Roger Alford |
| Title | Program Director, Universities and Health-Related Institutions Division |
| Address | Texas Higher Education Coordinating Board |
| Phone | 512-427-6216 |
| Fax | 512-427-6168 |
| E-mail | roger.alford@thecb.state.tx.us |

| Funding: |  |
| --- | --- |
| Appropriated 2002 (millions) | $ 0.00 |
| Appropriated 2003 (millions) | $ 0.00 |
| Appropriated 2004 (millions) | $ 0.00 |
| Appropriated 2005 (millions) | $ 0.00 |
| Appropriated 2006 (millions) | $ 1.28 |
| Expended as of 8/31/06 | $ (2.10) |
| FY 04 Budget Reallocation | $ 0.98 |
| FY 05 Budget Reallocation | $ 0.98 |
| Appropriated 2007 (millions) | $ 1.28 |
| FY 07 Expended & Committed 12/31 | $ (1.35) |
| Available as of 12/31/06 | 1.07 |

Summary

The Undergraduate Medical Academy is currently completing the second year of a $340,000 grant to evaluate the partnership with the Texas A&M HSC – College of Medicine and assist with the development of distance educational opportunities. The first graduate of the UMA (Mina Rosenthal-Eames) completed her studies in May 2006. She is currently a first year student at the University of Texas at Houston.

Eleven students are in the midst of the application process for entrance to Texas medical schools for the fall 2007 semester. All students have received interview for entrance to medical school. The second cohort of students is engaged in MCAT preparation for the spring 2007 examination period. The science faculty will be joining the UMA and Prairie View A&M University during the spring 2007 semester.

Implementation Schedule

| Task | Expected Completion Date | Outcome Documentation | Actual Completion Date |
| --- | --- | --- | --- |
| Review legislative intent | September 2003 | Copy of HB 85 | September 2003 |
| Establish organizational structure | September 2003 | A copy of the organizational structure of the Academy | September 2003 |
| Allocate space for the Medical Academy | September 2003 | Coordinating Board Approval | September 2003 |